## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2021-02-05 | February 2021 Review | New approval | Local road maintenance | Emergency works | Auckland Transport | E/W - Auckland Region - 25-29 June 2020 Weather Event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | This is an emergency work activity and because they are unforeseen events, no assessment profile is required to support the funding of this application. This activity is recommended for approval due to the: • unexpected, major and short duration natural event which occurred in 25-29 June 2020; and • type of damage that has reduced customer levels of service significantly below those that existed prior to the event and has resulted in unforeseen, significant exposure | 2610790 | 1331503 |  |  |  |  | 141.2717 | 271657 |  | 108311
2021-02-17 | February 2021 Review | New approval | Local road improvements | Road improvements | Auckland Transport | Brownfields Growth | Indicative Business Case | Brownfields Growth | H_L | H_L | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This activity aligns with the GPS and regional strategic priorities  This activity is urgent  Funding is available | 410000 | 209100 |  | 1 | 1 | 1 | E.700962.01.01, E700962.01.02, E.700962.01.03 | 275308 |  | 109173
2021-02-22 | February 2021 Review | Cost Increase | Local road improvements | Road improvements | Auckland Transport | Streetlighting Upgrade LED | Implementation | Streetlighting Update V Lights - IMP | M_H | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The assessment profile for this activity has used the 15-18 and 18 -21 Transport Agency’s Investment Assessment Framework assessment profile of Medium for strategic fit, High for effectiveness and a Low for efficiency; and a High results alignment and Low efficiency using the 2018-21 Investment Assessment Framework. This road improvement project is aligned with Auckland Transport’s Asset Management Plan and contributes to the Transport Agency’s Investment Assessment Framework, which is intended to give effect to the Government Policy Statement, and contributes to the purpose of the Land Transport Management Act (LTMA) by: a. Reducing electricity usage and the whole of life costs of street light luminaires; and b. Delivering safety benefits for road users and pedestrians. | 0 | 937366 |  | 5 | 2.1 | 2.1 | 324.2605 | 260547 |  | 109973
2021-02-11 | February 2021 Review | New approval | Local road improvements | Road improvements | Christchurch City Council | AAC High Street (Cashel to Tuam) | Construction |  | H_L | HHH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Payback for Northern Arterial Project | 0 |  |  | 3 | 2.9 | 2.9 |  | 233357 |  | 108309
2021-02-18 | February 2021 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Christchurch City Council | Cluster 1 - PT Facilities: Northlands Hub | Construction |  | HHH | HMH | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the completion of a bus lane for a core route in Christchurch’s bus network. • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – This is essentially a completed project and is just a wash up of final costs, therefore the project remains valid and supportable | 601876 | 306957 |  | 6.2 | -0.4 | 6.8 | 17152 | 233368 |  | 108174
2021-02-18 | February 2021 Review | Cost Increase | Promotion of road safety and demand management | Travel demand management | Environment Canterbury | On Demand Public Transport Timaru | Implementation | Implementation | H_L | H_VH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables a single stage business case to be completed that will enable multimodal access to a new housing development in Tauranga and to a key employment destination (the Tauriko Business Estate). The key benefits include improved safety, improved multimodal accessibility, and the unlocking of urgently needed housing supply in Tauranga. • The BCR will be calculated as part of the business case process. • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – valid and supportable | 587000 | 299370 |  | 1 | 0 | 0 | Trial | 267447 |  | 109881
2021-02-01 | February 2021 Review | New approval | Local road improvements | New roads | Hamilton City Council | 2018-28 Rotokauri Growth - Arterials designation | Pre-implementation* | Investigation | H_L* | V_VH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | 1. Greenfields Housing Development in high growth areas is an issue of national significance, and therefore needs to be prioritised. 2. The possiblity of CIP's participation to fund the transport infrastructure presensts a good return on investment for the NZTA and the Crown. 3. CIP's interest in this activity reflects strong potential for market uptake of housing in the area. 4. There is a case for urgency - CIP require as much certainty as possible by march 2020 (See 'Timing/Urgency' sectiona bove). 5. The DBC is the appropriate next pahse - revisiting previous NZTA decisions with a wide optioneering exercise is unnecessary given options around the arterial are fairy constrained. Equally, given costs for the pre-implementation phase are still vague, the CBD pahse is the opportuniy to agree the full work programme and costs for subsequent phases. | 2890000 | 1473900 | that the detailed business case is approved by waka Kotahi before lodgement of Notice of Requirement. | 3.9 | 3.9 | 3.9 |  | 257336 |  | 109159
2021-02-25 | February 2021 Review | New approval | Local road improvements | New roads | Hamilton City Council | 2018-28 Rototuna Growth - Borman Rd East/Horsham Downs | Pre-implementation* | Design | H_L* | VHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This funding is for the pre-implementation phase of an investment that provides improved access for the residents of Te Manatu to the new Rototuna town centre and schools. • We note that the BCR is 1.05 • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – Residential growth in Hamilton and use of biking as a mode of transport have continued unabated post COVID. Arataki V2’s Regional Summary for the Waikato states that growth in Hamilton will continue, however may be slowed by COVID. • It is expected that this funding request remains valid post-COVID. | 544000 | 277440 |  | 1 | 1.1 | 1.1 |  | 257326 |  | 109733
2021-02-25 | February 2021 Review | New approval | Local road improvements | Property purchase (local roads) | Hamilton City Council | 2018-28 Rototuna Growth - Borman Rd East/Horsham Downs | Property |  | H_L* | VHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This funding is for the pre-implementation phase of an investment that provides improved access for the residents of Te Manatu to the new Rototuna town centre and schools. • We note that the BCR is 1.05 • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – Residential growth in Hamilton and use of biking as a mode of transport have continued unabated post COVID. Arataki V2’s Regional Summary for the Waikato states that growth in Hamilton will continue, however may be slowed by COVID. • It is expected that this funding request remains valid post-COVID. | 206000 | 105060 |  | 1 | 1.1 | 1.1 |  | 257329 |  | 109732
2021-02-10 | February 2021 Review | Cost Increase | Local road maintenance | Emergency works | Kaikoura District Council | Kaikoura Nov 2016 EQ | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per advice from Senior Programme Manager T&C, Investment Advisor requested that KDC decrease funding phase to match accurate spend for 20/21. $290,000 decrease for this phase because the date of the phase ending June 2021. funds are associated to clearance valley access phase increase $290,000. | 290000 | 275500 |  |  |  |  | Clarence Valley Access | 266303 |  | 109868
2021-02-18 | February 2021 Review | New approval | Walking and cycling improvements | Cycling facilities | Kaipara District Council | Mangawhai Shared Path | Implementation | Mangawhai Shared Path - Phase 1 | H_L | V_VH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This approval enables a business case to provide the funding for investigation and design to progress a shared path for a community that’s experiencing significant growth • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – valid and supportable | 5900000 | 3658000 |  | 1.1 | 1.1 | 1.1 | Shared Path LTP 0 | 270522 |  | 104715
2021-02-16 | February 2021 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Kapiti Coast District Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | A business case for LCLR activities is not required but close prioritisation and alignment with each Councils’ respective AMP and is actively managed by System Management Investment Advisor’s. • We note that the generic rating for cost benefit appraisal for low cost, low risk programmes is medium (https://www.nzta.govt.nz/assets/planningand-investment/nltp/IAF-for-GPS-2018.pdf ) • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – System management investment advisors have confirmed deliverability and continued local share availability for all activities listed in respective activity list and therefore can be considered valid in the post-Covid-19 environment. | 637767 | 325261 |  |  |  |  | Construction | 253896 |  | 108030
2021-02-22 | February 2021 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (Northland) | EW SH11 Lemons Hill Slip Repair | Construction |  | ___ |  | N |  | Declined | Declined by regional office | The requirements of section 20 of the Land Transport Management Act 2003 have not been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -34 | -34 | [5 empty] | 263838 | 60049073 | 110099
2021-02-10 | February 2021 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (Northland) | EW SH11 Lemons Hill Slip Repair | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2 | -2 | [5 empty] | 263838 | 60049073 | 109888
2021-02-12 | February 2021 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Construction | Transmission Gully - PPP component | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.4 | 1.4 | 60218421 | 203538 | 60218421 | 109852
2021-02-22 | February 2021 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (West Coast) | SH7 Ahaura River Bridge Replacement | Pre-implementation* | Design | HMPV_EoL | HMPV_EoL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 94 | 94 |  |  | 0 | 0 | 60032293 | 232576 | 60032293 | 110095
2021-02-05 | February 2021 Review | Cash flow adjustment | Local road improvements | Resilience improvements | Gisborne District Council | Resilience Improvements (Preventative Maintenance) 2015/18 | Construction |  | HML | MMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  |  |  | Construction | 244968 |  | 109675
2021-02-05 | February 2021 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Auck Accelerated Prog: Southern Corridor Improvements | Repayment | Repayment | HHH | HHH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 13 | 0 | 6 |  | 245968 |  | 109855
2021-02-22 | February 2021 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Canterbury) | SH1 Rakaia to Ashburton CI - Stage 2 | Pre-implementation* |  | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.6 | 0 | 1.6 |  | 231724 | 60056839 | 110014
2021-02-22 | February 2021 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Gisborne) | SH2 Inter-Regional Connections (Waioeka Gorge) | Detailed Business Case | Detailed Business Case | H_L* | H_L* | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  | 1.1 | 1 | 1 | Detailed Business Case | 250523 | 60051147 | 109954
2021-02-22 | February 2021 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Gisborne) | SH35 and connecting routes: Resilience | Implementation | PGF | H_L* | H_L* | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1 | 1 | 1 |  | 267791 | 60051600 | 110013
2021-02-22 | February 2021 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Gisborne) | SH35 and connecting routes: Resilience | Pre-implementation* | PGF | H_L* | H_L* | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1 | 1 | 1 |  | 264778 | 60051589 | 110012
2021-02-05 | February 2021 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Southland) | SH1S Bluff Highway/Elles Road I/S Improvement | Implementation | Implementation | MML* | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1 |  | 1.2 | 2.4 | 2.4 | 60029942 | 267450 | 60029942 | 109712
2021-02-12 | February 2021 Review | Cash flow adjustment | State highway maintenance | Sealed pavement maintenance | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Implementation | Maintenance and Operations payments | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.4 | 1.4 |  | 243429 |  | 109832
2021-02-16 | February 2021 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Masterton District Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | A business case for LCLR activities is not required but close prioritisation and alignment with each Councils’ respective AMP and is actively managed by System Management Investment Advisor’s. • We note that the generic rating for cost benefit appraisal for low cost, low risk programmes is medium (https://www.nzta.govt.nz/assets/planningand-investment/nltp/IAF-for-GPS-2018.pdf ) • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – System management investment advisors have confirmed deliverability and continued local share availability for all activities listed in respective activity list and therefore can be considered valid in the post-Covid-19 environment. | 1400000 | 826000 | [5 empty] | 257251 |  | 107410
2021-02-23 | February 2021 Review | Cost Decrease | External funding | Cycling facilities | NZTA (Wellington) | Petone to Melling Walking Cycling Link | Implementation | Implementation - UCF | HML | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -150 | -150 |  | 2.5 | 0 | 2.5 |  | 251716 |  | 109515
2021-02-05 | February 2021 Review | Cost Decrease | Local road maintenance | Emergency works | Auckland Transport | E/W Rural South Auckland 24 December 2018 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -984273 | -501979 |  |  |  |  | 141.2673 | 267281 |  | 109792
2021-02-22 | February 2021 Review | Cost Increase | Local road maintenance | Cycle path maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme has been changed to reflect learnings from the 2021-24 AMP and start the improvement programme early to deliver data improvement and lead into the pavements programme as indicated in the 2021-24 AMP. $100k remains in WC140 and no claims to date that could be released at a later date. | 10276 | 5241 | [5 empty] | 254676 |  | 108959
2021-02-10 | February 2021 Review | Cost Decrease | Local road maintenance | Emergency works | Kaikoura District Council | Kaikoura Nov 2016 EQ | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -290000 | -275500 |  |  |  |  | Initial Reinstatement (2) | 250096 |  | 109869
2021-02-12 | February 2021 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Otago) | EW Central Otago Flood Event 3.2.2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -14765 | -14765 | [5 empty] | 270686 | 60057366 | 109935
2021-02-12 | February 2021 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Otago) | EW Central Otago Flood Event 6.12.2019 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -6149 | -6149 |  |  |  |  | Construction | 270685 | 60057360 | 109934
2021-02-22 | February 2021 Review | Cost Increase | Local road maintenance | Footpath maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme has been changed to reflect learnings from the 2021-24 AMP and start the improvement programme early to deliver data improvement and lead into the pavements programme as indicated in the 2021-24 AMP. $100k remains in WC140 and no claims to date that could be released at a later date. | 35000 | 17850 | [5 empty] | 264112 |  | 108959
2021-02-22 | February 2021 Review | Cost Increase | Local road maintenance | Network and asset management | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme has been changed to reflect learnings from the 2021-24 AMP and start the improvement programme early to deliver data improvement and lead into the pavements programme as indicated in the 2021-24 AMP. $100k remains in WC140 and no claims to date that could be released at a later date. | 503266 | 256666 | [5 empty] | 254679 |  | 108959
2021-02-22 | February 2021 Review | Cost Increase | Local road maintenance | Operational traffic management | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme has been changed to reflect learnings from the 2021-24 AMP and start the improvement programme early to deliver data improvement and lead into the pavements programme as indicated in the 2021-24 AMP. $100k remains in WC140 and no claims to date that could be released at a later date. | 22000 | 11220 | [5 empty] | 254675 |  | 108959
2021-02-22 | February 2021 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme has been changed to reflect learnings from the 2021-24 AMP and start the improvement programme early to deliver data improvement and lead into the pavements programme as indicated in the 2021-24 AMP. $100k remains in WC140 and no claims to date that could be released at a later date. | 132000 | 67320 | [5 empty] | 254669 |  | 108959
2021-02-22 | February 2021 Review | Cost Increase | Local road maintenance | Traffic services renewals | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme has been changed to reflect learnings from the 2021-24 AMP and start the improvement programme early to deliver data improvement and lead into the pavements programme as indicated in the 2021-24 AMP. $100k remains in WC140 and no claims to date that could be released at a later date. | 31862 | 16249 | [5 empty] | 254686 |  | 108959
2021-02-05 | February 2021 Review | Cost Decrease | Local road maintenance | Emergency works | Wairoa District Council | Emergency Works November 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | -190000 |  |  |  |  | Clean-Up/Design/Repair | 275284 |  | 109735
2021-02-05 | February 2021 Review | Cost Decrease | Local road maintenance | Emergency works | Wellington City Council | Emergency Works July/August 2017 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | -1557983 |  |  |  |  | -2 | 268054 |  | 109762
2021-02-22 | February 2021 Review | Cost Decrease | Local road maintenance | Environmental maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -10000 | -5100 | [5 empty] | 254673 |  | 108959
2021-02-23 | February 2021 Review | Cost Increase | Promotion of road safety and demand management | Promotion, education and advertising | NZ Transport Agency | National Road Safety Advertising &Education Programme2018-21 | Implementation |  | HH | HH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This additional funding approval will enable Bikes in Schools to meet the current demand in 2020/21, as this year’s budget is already fully allocated to schools. Additional funding of $800,000 for this year will provide approx. 6,270 additional students with access to Bikes in Schools and approx. 16 additional schools with Bikes in Schools • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – valid and supportable - This funding variation request remains valid in a postCOVID environment as demand for Bikes in Schools has continued to increase, despite the COVID restrictions earlier in the year. The Bike On NZ Charitable Trust who manage the programme have reported ongoing demand, with schools continuing to make enquiries and express interest in developing projects. Bikes in Schools involves the building of a bike track within school grounds which provides students and the community with a local facility to ride bikes and develop their skills on a regular basis, which remains valid in a post-COVID world. | 61039 | 61039 |  |  |  |  | 80002046 / 80002039 | 261098 |  | 110137
2021-02-05 | February 2021 Review | Cost Decrease | Local road maintenance | Footpath maintenance | Palmerston North City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -400000 | -204000 | [5 empty] | 264121 |  | 109856
2021-02-22 | February 2021 Review | Cost Increase | Promotion of road safety and demand management | Promotion, education and advertising | NZ Transport Agency | National Road Safety Advertising &Education Programme2018-21 | Implementation |  | MM | HM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This additional funding approval will enable Bikes in Schools to meet the current demand in 2020/21, as this year’s budget is already fully allocated to schools. Additional funding of $800,000 for this year will provide approx. 6,270 additional students with access to Bikes in Schools and approx. 16 additional schools with Bikes in Schools • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – valid and supportable - This funding variation request remains valid in a postCOVID environment as demand for Bikes in Schools has continued to increase, despite the COVID restrictions earlier in the year. The Bike On NZ Charitable Trust who manage the programme have reported ongoing demand, with schools continuing to make enquiries and express interest in developing projects. Bikes in Schools involves the building of a bike track within school grounds which provides students and the community with a local facility to ride bikes and develop their skills on a regular basis, which remains valid in a post-COVID world. | 394000 | 394000 |  |  |  |  | 80002029 / 80002121 /800002045 / 80002239 / 80002241 /80002368 | 261157 |  | 109776
2021-02-17 | February 2021 Review | Support for strategic case |  |  | NZ Transport Agency | Road to Zero vision | Support for Strategic Case |  | V__ | H__ | N | 1 | Supported | Supported by Senior Manager System Planning (Transport Services) | This is not a funding decision | 0 | [6 empty] | 270060 |  | 108488
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Auckland) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2281698 | -2281698 | [5 empty] | 255179 | 60050081 | 110140
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (BOP) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1472582 | -1472582 | [5 empty] | 254906 | 60050078 | 110141
2021-02-10 | February 2021 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | Muriwai Rd Intersection Improvements | Property |  | MHH | MHH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Property - The following list identifies the unavoidable additional work required to support the project outcomes: Waimauku Primary School was sold to Iwi and leased back to the Ministry of Educaiton. This necessitated two acquisitions. The veterinary clinic at 1 Sarah Todd Lane purchased additional land from an adjoining land owner, and undertook an extension. This required significant additional expense in professional fees to resolve compensation. The property at 906 State Highway 16 had land acquired in 2003 by the former Rodney District Council for an earlier intersection design. This necessitated two acquisitiions. The Waikauku Bowling Club property was sold to Auckland Council, and the property at 3 Waikauku Station Road was sold. Both these transactions occured after the designation was granted and befor ethe acquisitions commenced. Property values have increase substantially over the period of negotiations. Contingency - We have recently become aware that RSA has lodged a complaint with Auckland Council related to Historic encroachment of the RSA boundary. Given the road is now a State Highway and sits with the NZTA, we have allowed a further $50k contingency in current forecasts for any likely additional property costs. | 8849 | 8849 |  | 5.2 | 5.2 | 5.2 | 60455022 | 247030 | 60455022 | 109952
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Gisborne) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -4068509 | -4068509 | [5 empty] | 254599 | 60050097 | 110143
2021-02-12 | February 2021 Review | Cost Increase | Rapid Transit | Rapid Transit Infrastructure | NZTA (Auckland) | City Centre to Mangere Light Rail | Detailed Business Case | Business case RT improvements | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Trsf funds from PreImp to cover DBC for 2019/20 Spend. | 18531380 | 18531380 |  | 2 | 1 | 1 | 60051244 | 264606 | 60051244 | 109866
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Manawatu/Whanganui) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -43839 | -43839 | [5 empty] | 254619 | 60050109 | 110145
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Marlborough) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3097852 | -3097852 |  |  |  |  | Minor Improvements Programme | 254546 | 60050121 | 110146
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Nelson) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -436835 | -436835 | [5 empty] | 257706 | 60050117 | 110147
2021-02-12 | February 2021 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (BOP) | Weigh Right Paengaroa | Implementation |  | HHH | HHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In terms of the 2015 RLTP – this is just a change in the cost and status of an existing activity – so no action required. | 2113570 | 2113570 |  |  | 14 | 14 | 60048361 | 262618 | 60048361 | 109997
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Otago) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1725149 | -1725149 | [5 empty] | 254829 | 60050133 | 110149
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Southland) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -461050 | -461050 | [5 empty] | 254850 | 60050137 | 110150
2021-02-24 | February 2021 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Taranaki) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1134578 | -1134578 | [5 empty] | 254961 | 60050105 | 110151
2021-02-24 | February 2021 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Canterbury) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | LCLR update on 24/02/2021 as requested by Transport Services. Details in infohub https://infohub.nzta.govt.nz/otcs/cs.dll/link/48478061 | 1561597 | 1561597 | [5 empty] | 254769 | 60050129 | 110142
2021-02-24 | February 2021 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Hawkes Bay) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | That the Senior Manager OPPP, Transport Services: • Endorsed the price level adjustment and recommends that the Chief Financial Officer approves funding to the NZ Transport Agency, for Safety Boost Extension (Boost 2)in accordance with Attachment 1 for an increase of $6,882,275 at a FAR of 100% ($6,882,275 out of the NLTF) for implementation from the Local Road, Regional and State Highway improvements activity class, thereby increasing the approved total cost from $19,629,937 to $26,512,212, with the following conditions precedent o confirmation that the $6,882,275 is within the approved allocation for low cost low risk and Deferred (Revise and resubmit) ☐ Declined  NZ TRANSPORT AGENCY VARIATION: PRICE LEVEL/SCOPE/COST ADJUSTMENT // 6 o that the low cost low risk governance group confirms that they support this funding approval and that this allocation of outcomes under low cost low risk will align with the GPS priorities. | 2414734 | 2414734 | [5 empty] | 254933 | 60050101 | 110144
2021-02-25 | February 2021 Review | New approval | State highway maintenance | Emergency works | NZTA (Northland) | EW Northland Drought 20200214 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | New approval that meets all NZTA EW guidelines & processes | 371569 | 371569 |  |  |  |  | Construction | 270845 | 60058345 | 110162
2021-02-24 | February 2021 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Northland) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | LCLR update on 24/02/2021 as requested by Transport Services. Details in infohub https://infohub.nzta.govt.nz/otcs/cs.dll/link/48478061 | 751688 | 751688 | [5 empty] | 255137 | 60050014 | 110148
2021-02-15 | February 2021 Review | Cost Increase | External funding | Road improvements | NZTA (Northland) | SH1 Akerama Curves Realign & PL | Construction | Construction | MMM | HMH | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer 2017/18 Spend from NLTF Funding to Crown Funding to match Eric's drawdown. | 5241783 | 5241783 |  | 4.2 | 2.5 | 2.5 | 60202847 | 174509 |  | 110034
2021-02-12 | February 2021 Review | Cost Increase | External funding | Road improvements | NZTA (Northland) | SH1 Akerama Curves Realign & PL | Construction | Construction | MMM | HMH | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Spend for 2019/20 in SAP is $418,791. Transferred $59,309 from Implementation NLTF funding. | 368817 | 368817 |  | 4.2 | 2.5 | 2.5 | 60202847 | 174509 |  | 109871
2021-02-05 | February 2021 Review | New approval | State highway maintenance | Emergency works | NZTA (Otago) | EW Otago Region HR 20210102 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) |  | 1795 | 1795 | [5 empty] | 275704 | 60060194 | 109882
2021-02-22 | February 2021 Review | Cost Decrease | Local road maintenance | Minor events | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This is to cover 2019/20 Spend. | -343481 | -175175 | [5 empty] | 254678 |  | 108959
2021-02-11 | February 2021 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Otago) | EW Otago Region HR 20210102 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Initial application approved by KL should be $1.6M and not $1.6k. Funding application approved by Wayne. | 1698206 | 1698206 | [5 empty] | 275704 | 60060194 | 109883
2021-02-05 | February 2021 Review | Cost Decrease | State highway improvements | New roads | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Implementation | Construction - PPP Component | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -51678588 | -51678588 |  | 1.1 | 1.1 | 1.1 | 60216907 | 202325 | 60046661 | 109854
2021-02-26 | February 2021 Review | Cost Decrease | State highway improvements | New roads | NZTA (Taranaki) | SH3 Mt Messenger Bypass | Construction | Construction | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -6168609 | -6168609 |  | 1.1 | 0.5 | 0.5 | 60038700 | 260256 |  | 110194
2021-02-15 | February 2021 Review | Cost Increase | External funding | Replacement of bridges and other structures | NZTA (Otago) | Kawarau Falls Bridge | Construction | Kawarau Falls Construction | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer 2017/18 Spend from NLTF funding to Crown Funding to match Eric's drawdown. | 1986394 | 1986394 |  | 1.5 | 1.5 | 1.5 | 60214785 | 213147 |  | 110036
2021-02-26 | February 2021 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Taranaki) | SH3 Mt Messenger Bypass | Pre-implementation* | 1513501 | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move funding allocation of $6,012,290 from proj 60038700 to this project (60038688) to cover overspend and forecast through end of this financial year. Construction delayed requiring interphase transfer. | 4615758 | 4615758 |  | 1.1 | 0.5 | 0.5 | 60038688 | 265641 | 60038688 | 110166
2021-02-12 | February 2021 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Hawkes Bay) | Weigh Right Napier Port | Implementation | Construction/Implementation (C) | HHH | HHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Requested by Roger Burn / Martin Shearman. | -2113121 | -2113121 |  |  | 14 | 14 | 60032036 | 250274 | 60032036 | 109998
2021-02-05 | February 2021 Review | Cost Decrease | Local road improvements | New traffic management facilities | Rotorua Lakes Council | LED Conversion of Streetlights that are CMS capable | Construction | Implimentation | M_H | H_VH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2011605 | -1709864 |  | 99 | 1.4 | 1.4 |  | 267992 |  | 109694
2021-02-24 | February 2021 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Tasman) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | LCLR update on 24/02/2021 as requested by Transport Services. Details in infohub https://infohub.nzta.govt.nz/otcs/cs.dll/link/48478061 | 675963 | 675963 | [5 empty] | 257705 | 60050125 | 110152
2021-02-22 | February 2021 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | Gisborne District Council | Road Safety Promotion 2018-21 | Implementation |  | MM | MM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -150000 | -112500 |  |  |  |  | RSCS 2018-21 | 255223 |  | 109992
2021-02-22 | February 2021 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | NZ Transport Agency | National Road Safety Advertising &Education Programme2018-21 | Implementation |  | HH | HH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -161039 | -161039 |  |  |  |  | 80002046 / 80002039 | 261098 |  | 109778
2021-02-02 | February 2021 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Waikato) | EW East Waikato Slip Hvy Rain 20200531 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updating for SAP expenditure for 19/20. Expenditure of $489,052 incurred in 19/20 | 3105 | 3105 | [5 empty] | 270844 | 60057372 | 109794
2021-02-22 | February 2021 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | NZ Transport Agency | National Road Safety Advertising &Education Programme2018-21 | Implementation |  | HH | HH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -790000 | -790000 |  |  |  |  | 80002026 / 80002032 / 80002041 | 256597 |  | 109773
2021-02-22 | February 2021 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | NZ Transport Agency | National Road Safety Advertising &Education Programme2018-21 | Implementation |  | MH | MH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -90000 | -90000 |  |  |  |  | 80002035 | 261119 |  | 109777
2021-02-24 | February 2021 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Waikato) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | LCLR update on 24/02/2021 as requested by Transport Services. Details in infohub https://infohub.nzta.govt.nz/otcs/cs.dll/link/48478061 | 9794967 | 9794967 | [5 empty] | 254650 | 60050092 | 110153
2021-02-22 | February 2021 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | NZ Transport Agency | National Road Safety Advertising &Education Programme2018-21 | Implementation |  | HH | HH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -500000 | -500000 |  |  |  |  | WBS 80002238 | 261100 |  | 109775
2021-02-22 | February 2021 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | NZ Transport Agency | National Road Safety Advertising &Education Programme2018-21 | Implementation |  | HH | HH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1000000 | -1000000 |  |  |  |  | 80002028 | 260177 |  | 109774
2021-02-22 | February 2021 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | Queenstown-Lakes District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -29536 | -15063 | [5 empty] | 257441 |  | 110074
2021-02-04 | February 2021 Review | Cost Increase | External funding | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Implementation | Construction implementation | HLL | MML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer spend from Construction NLTF to Imp-Construction Crown funding for 2019/20. This is to correct & align with the crown funding drawdown. Requested by Martin Shearman. | 19292851 | 19292851 |  | 2.5 | 0.8 | 0.8 | 60038686 | 246371 | 60038686 | 109874
2021-02-24 | February 2021 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Wellington) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | LCLR update on 24/02/2021 as requested by Transport Services. Details in infohub https://infohub.nzta.govt.nz/otcs/cs.dll/link/48478061 | 5247237 | 5247237 | [5 empty] | 254662 | 60050113 | 110154
2021-02-26 | February 2021 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Wellington RoNS (2)-Wellington Inner-City (Tunnel to Tunnel) | Property |  | HHL | HHL | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Project Close- we are applying the EOY process for closed projects that have overspent up to $50K. | 1543 | 1543 |  |  | 1.4 | 1.4 | NB Includes pre-2013 costs which are missing in SAP | 198626 | 60416722 | 110094
2021-02-24 | February 2021 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (West Coast) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | LCLR update on 24/02/2021 as requested by Transport Services. Details in infohub https://infohub.nzta.govt.nz/otcs/cs.dll/link/48478061 | 253817 | 253817 | [5 empty] | 254958 | 60050141 | 110155
2021-02-16 | February 2021 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Porirua City Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | To complete twelve (12) projects within Porirua City. Further details are outlined in the LCLR template titled 07 - 2020_21 - Budget - LTP - AMP - Transport Forecast - LCLR 13.08.2020 For Waka Kotahi' with funding assistance requested for those projects with a status of 'In Planning (Agreed)' or 'in Construction (Agreed). All of these projects are well advanced and we expect delivery by June 2021. | 3206323 | 1795541 | [5 empty] | 254463 |  | 107366
2021-02-12 | February 2021 Review | Cost Decrease | Rapid Transit | Rapid Transit Infrastructure | NZTA (Auckland) | City Centre to Mangere Light Rail | Pre-implementation* | Pre-Implementation- RT improvements | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Trsf funds from PreImp to cover DBC for 2019/20 Spend. | -18531380 | -18531380 |  | 2 | 1 | 1 | 60052230 | 266501 | 60052230 | 109867
2021-02-16 | February 2021 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Tasman District Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | New projects for approval: - Motupipi cycle bridge - Motueka Town Centre upgrade (advancing design from future years - to align with NZTA High St project) - Berryfield/Lower Queen St intersection (advancing from future years - due to growth) Cost increases on existing projects (incl some COVID-costs): - Champion/Salisbury safe cycle crossings - Ellis St undergrounding - Lord Rutherford-Ellis intersection improvement - Mission Bridge - New footpaths | 1756703 | 895919 | [5 empty] | 256817 |  | 108188
2021-02-15 | February 2021 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Otago) | Kawarau Falls Bridge | Implementation | Kawarau Bridge Falls - NLTF Funding | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1986394 | -1986394 |  | 1.5 | 1.5 | 1.5 |  | 264227 | 60214785 | 110035
2021-02-22 | February 2021 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Northland) | SH1N Callaghan Rd | Implementation |  | HHH | HHL | N | 1 | Declined | Not recommended by national office | The requirements of section 20 of the Land Transport Management Act 2003 have not been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -71939 | -71939 |  |  |  |  | 60044406 | 250292 | 60044406 | 110100
2021-02-19 | February 2021 Review | New approval | Walking and cycling improvements | Cycling facilities | Tauranga City Council | Totara Street Safety Improvements | Pre-implementation* | Pre-Implementation | H_L | HM*L* | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the construction of the Totara Street Safety Improvements, providing the necessary infrastructure for people to safely cycle from Coronation Park to Hewletts Rd (SH2). • We note that the BCR is 2.3. • The requirements of section 20 of the Land Transport Management Act 2003 have been met. Deferred (Revise and resubmit) ☐ Declined ☐ NZ TRANSPORT AGENCY IQA & FUNDING REQUEST // 10 • Post Covid-19 effect – This activity remains valid in a post-Covid world | 94000 | 47940 |  | 2.3 | 0 | 2.6 |  | 270683 |  | 108896
2021-02-18 | February 2021 Review | Cost Increase | Local road improvements | New roads | Tauranga City Council | Western Corridor Growth Management - Tauriko West DBC | Detailed Business Case | Detailed design and business case | H_L* | VM*L | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables a single stage business case to be completed that will enable multimodal access to a new housing development in Tauranga and to a key employment destination (the Tauriko Business Estate). The key benefits include improved safety, improved multimodal accessibility, and the unlocking of urgently needed housing supply in Tauranga. • The BCR will be calculated as part of the business case process. • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – valid and supportable. | 152375 | 77712 |  | 1 | 0 | 0 |  | 259256 |  | 109993
2021-02-05 | February 2021 Review | Cost Increase | Local road maintenance | Emergency works | Thames-Coromandel District Council | June 2018 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Colville Rd 12.6km site is more complex and therefore more costly than originally thought. Works are scheduled to be completed in this FY. An out of cycle budget request has been approved by Council for the TCDC share. The report outlining this request is attached. Please note the total costs referred to in the request for June 2018 event include this item and the 51% FAR item in TIO which has a 20/21 allocation of $920,958. | 559183 | 397020 |  |  |  |  | Event response and reinstatement (2) | 270884 |  | 109812
2021-02-15 | February 2021 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Northland) | SH1 Akerama Curves Realign & PL | Implementation | Imp - NLTF Funding | MMM | HMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -5241783 | -5241783 |  | 4.2 | 2.5 | 2.5 | 60202847 | 264233 | 60202847 | 110033
2021-02-04 | February 2021 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Northland) | SH1 Akerama Curves Realign & PL | Implementation | Imp - NLTF Funding | MMM | HMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -60851 | -60851 |  | 4.2 | 2.5 | 2.5 | 60202847 | 264233 | 60202847 | 109870
2021-02-05 | February 2021 Review | Cost Increase | Local road maintenance | Emergency works | Thames-Coromandel District Council | Queens Birthday Weekend - 31 May to 1 June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Colville Rd 16.169km site is more complex and expensive than originally estimated. Revised estimate is based on improved understanding following site testing & investigation allowing more accurate estimating. The increase at this site is greater than the overall budget increase request due to savings at other sites which have offset the need for further funding. | 117780 | 83624 | [5 empty] | 270880 |  | 109814
2021-02-04 | February 2021 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Construction | Construction - NLTF funding | HLL | MML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | An out of cycle budget request was approved by Council for the TCDC share. This request is attached as supporting information. | -19292851 | -19292851 |  | 2.5 | 0.8 | 0.8 | Construction-60038686 | 263999 |  | 109875
2021-02-05 | February 2021 Review | Cost Increase | Local road maintenance | Emergency works | Thames-Coromandel District Council | September 2019 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Cost for replacement of Stargazers Bridge on School of Mines Lane, Kuaotunu has exceeded estimate. Additional costs include temporary bridge to allow winter access, scour protection works & land acquisition. An out of cycle budget request for the increase has been approved by Council for the TCDC share. A copy of the request is attached as supporting information. | 467292 | 331778 |  |  |  |  | Response and reinstatement | 269111 |  | 109813
2021-02-05 | February 2021 Review | Cost Decrease | State highway maintenance | Sealed pavement maintenance | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Construction | Implementation - Maintenance and Operations Payeme | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -11119151 | -11119151 |  | 1.1 | 1.1 | 1.1 | Construction | 263236 |  | 109853
2021-02-16 | February 2021 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Timaru District Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | A business case for LCLR activities is not required but close prioritisation and alignment with each Councils’ respective AMP and is actively managed by System Management Investment Advisor’s. • We note that the generic rating for cost benefit appraisal for low cost, low risk programmes is medium (https://www.nzta.govt.nz/assets/planningand-investment/nltp/IAF-for-GPS-2018.pdf ) • The requirements of section 20 of the Land Transport Management Act 2003 have been met. • Post Covid-19 effect – System management investment advisors have confirmed deliverability and continued local share availability for all activities listed in respective activity list and therefore can be considered valid in the post-Covid-19 environment. | 2025463 | 1032986 | [5 empty] | 256296 |  | 109636
2021-02-05 | February 2021 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Palmerston North City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -800000 | -408000 | [5 empty] | 253557 |  | 109856
2021-02-22 | February 2021 Review | Cost Decrease | Local road maintenance | Sealed road pavement rehabilitation | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -189000 | -96390 | [5 empty] | 254683 |  | 108959
2021-02-22 | February 2021 Review | Cost Decrease | Local road maintenance | Sealed road resurfacing | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -150000 | -76500 | [5 empty] | 254681 |  | 108959
2021-02-22 | February 2021 Review | Cost Decrease | Local road maintenance | Traffic services maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -57000 | -29070 | [5 empty] | 254674 |  | 108959
2021-02-22 | February 2021 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Waikato District Council | Huntly Station (Start Up Rail Service) | Construction | Huntly Above Track Infrastructure | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Above track infrastructure (station facilities) Feb 2021 Cost scope adjustment as endorsed by B Dowsett Dec 2020 | 182409 | 138631 |  | 0.5 | 0.5 | 0.5 |  | 266431 |  | 109996
2021-02-22 | February 2021 Review | Cost Decrease | Transitional Rail | Transitional Rail Infrastructure | Waikato District Council | Huntly Station (Start Up Rail Service) | Construction | Huntly Below Track (plus platform) | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Feb 2021 Cost scope adjustment as endorsed by B Dowsett Dec 2020 | -567412 | -567412 |  | 0.5 | 0.5 | 0.5 |  | 266430 |  | 109995
2021-02-09 | February 2021 Review | New approval | Public transport | Public transport infrastructure and major renewals | Waimakariri District Council | Park and Ride Facilities | Implementation |  | H_L | H_L | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Part of NZTAs HOV lane supporting infrastructure | 2820000 | 1438200 |  | 2 | 0 | 0 |  | 271683 |  | 108554
2021-02-09 | February 2021 Review | New approval | Public transport | Public transport infrastructure and major renewals | Waimakariri District Council | Park and Ride Facilities | Pre-implementation* |  | H_L | H_L | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Part of NZTAs HOV lane supporting infrastructure | 600000 | 306000 |  | 2 | 0 | 0 |  | 271682 |  | 108553