## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2022-01-26 | January 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Gisborne) | EW Gisborne SH2 SH35 HR 20211105 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | all paperwork and approvals in order | 970324 | 970324 | [5 empty] | 280216 | 60066096 | 116325
2022-01-21 | January 2022 Review | New approval | Road to Zero | Road improvements | NZ Transport Agency | Safe Vehicles Programme 21-24 | Single-Stage Business Case | Safe Vehicles Programme SSBC | MHVH | MHVH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Encourage consumers to make smart vehicle purchase decisions that help avoid crashes and make them and their passengers safer in the event of a crash, hence aligns with the GPS objectives. | 6105000 | 6105000 |  |  | 17 | 17 | Completed 2021 | 277396 |  | 115915
2022-01-28 | January 2022 Review | New approval | State highway improvements | Road improvements | NZTA (Wellington) | Wellington Port Access Improvements | Indicative Business Case | IBC Wellington Port Access Improvements | HHM | VHML | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Transport connections to the proposed MUFP are needed to enable the port to perform its function and mitigate any effects to the transport network as endorsed by Nat Mgr programme & Stds and approved funding by CFO. | 514080 | 439080 |  |  | 1 | 1 | 60027702 | 231317 | 60027702 | 116038
2022-01-17 | January 2022 Review | New approval | Road to Zero | Road policing | NZ Transport Agency | Road Safety Partnership Programme 2021-24 | Implementation |  | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Programme developed by Waka Kotahi and NZ Police in consultation with Te ManatÅ« Waka Ministry of Transport. | 1243500000 | 1243500000 |  |  | 1 | 1 |  | 270363 |  | 116265
2022-01-14 | January 2022 Review | New approval | Road to Zero | Road policing | NZ Transport Agency | Tackling Unsafe Speeds | Pre-implementation* | Safety camera IBC and DBC | VH_L | VHHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | The benefits of the TUS programme will be: â€¢ a reduction in speed related DSIs (main benefit) â€¢ a reduction in ongoing compliance costs for RCAs and the regulator through coordinated and streamlined processes and consultation requirements for speed limit changes, resulting in less effort required to change limits â€¢ improved road safety outcomes for all parties because of a consistent whole-of-network approach to speed management. | 10700000 | 10700000 |  |  | 1.3 | 1.3 | WBS80002655 - Richard Stewart | 280055 |  | 116207
2022-01-25 | January 2022 Review | New approval | Public transport infrastructure | Technology to improve effectiveness of public transport systems | Auckland Transport | Community Connect - Auckland Trial | Implementation | Community Connect - Set Up Costs | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | 100% Crown funded. Refer attached signed agreement in supporting information. | 4380948 | 4380948 |  |  |  |  | 554.2774 | 277400 |  | 115645
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Bridge and structures renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -575000 | -293250 | [5 empty] | 274717 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Cycle path maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 21890 | 11163 | [5 empty] | 274704 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Cycle path renewal | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 167134 | 85238 | [5 empty] | 274720 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Drainage renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 565594 | 288453 | [5 empty] | 274714 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Ashburton District Council | EW Rain Event July 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -74264 | -37875 |  |  |  |  | Reinstatement | 279132 |  | 116125
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Environmental maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -591571 | -301702 | [5 empty] | 274707 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Environmental renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -9039 | -4609 | [5 empty] | 274718 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Footpath maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 477467 | 243509 | [5 empty] | 274705 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Footpath renewal | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 8821 | 4500 | [5 empty] | 274721 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Network and asset management | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -1117766 | -570060 | [5 empty] | 274711 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Network operations | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 1868002 | 952681 | [5 empty] | 274709 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Network service maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -322909 | -164684 | [5 empty] | 274708 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road improvements | New traffic management facilities | Rotorua Lakes Council | LED Conversion of Streetlights that are CMS capable | Construction | Implimentation | M_H | H_VH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Complete | -207317 | -116098 |  |  | 1.4 | 1.4 |  | 267992 |  | 116083
2022-01-26 | January 2022 Review | Cost Decrease | Rail network | Rail network and asset management | NZ Transport Agency | KiwiRail RNIP - National Freight Network & PT Infrastructure | Implementation | National Freight Network | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Ministerial appropriation. | 0 | -834400000 |  |  | 1 | 1 |  | 277493 |  | 116345
2022-01-21 | January 2022 Review | Cost Decrease | Public transport infrastructure | Rapid Transit Infrastructure | Tauranga City Council | Te Papa Spatial Framework - Rapid Transit | Indicative Business Case | IBC | H_L* | H_L* | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Complete | -32346 | -32346 |  |  | 3.3 | 3.3 | Te Papa IBC Phase | 268751 |  | 116084
2022-01-19 | January 2022 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | SH10 Kaeo Bridge upgrade | Implementation | NLTF-SH Improvements | HHL | MHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Construction costs have risen between 15 and 30% Includes contingency for delays and escalation. | 5400000 | 5400000 |  |  | 0.6 | 0.6 | 60038592 | 269811 | 60038592 | 115447
2022-01-21 | January 2022 Review | Cost Decrease | Local road improvements | Road improvements | Grey District Council | LED Street Light Conversion | Implementation | LED Supply and Installation | M_H | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Claiming complete no further work required. | -65799 | -41453 |  |  | 1 | 99 |  | 263979 |  | 116082
2022-01-26 | January 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH30: Te Teko to Awakeri, NSRRP | Implementation | Construction | H_H | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | surplus to close the project | -486643 | -486643 |  |  | 1.2 | 1.2 | 60028350 | 232366 | 60028350 | 116286
2022-01-17 | January 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | TNP SH29 Tauriko West Network Connection | Detailed Business Case | TNP SH29 Tauriko West Network Connections | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Scope change to take account of local council future transport development | 1835192 | 1835192 |  |  | 0 | 1.7 | 60041684 | 248953 | 60041684 | 115954
2022-01-21 | January 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | SH1 (Cambridge to Piarere) ST Improvements, NSRRP | Implementation | NLTF-SH Improvements | H_M | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus $15,884 so project can then be closed | -17155 | -17155 |  |  | 1.2 | 1.2 | 60218171 | 278784 | 60218171 | 116271
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 1017014 | 518677 | [5 empty] | 274702 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -367677 | -187516 | [5 empty] | 274700 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 802762 | 409408 | [5 empty] | 274715 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 1691686 | 862760 | [5 empty] | 274713 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Structures component replacements | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 370463 | 188937 | [5 empty] | 274716 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Structures maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -38798 | -19786 | [5 empty] | 274703 |  | 116127
2022-01-21 | January 2022 Review | Cost Increase | Local road maintenance | Traffic services renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | 697740 | 355848 | [5 empty] | 274719 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Unsealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -1181170 | -602396 | [5 empty] | 274701 |  | 116127
2022-01-21 | January 2022 Review | Cost Decrease | Local road maintenance | Unsealed road metalling | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contract extension cost increases in 2021/22 and 2022/23. Advanced w/c 216 for No 4 Road structures replacements due to planned pavement rehabilitation and widening works. | -1395628 | -711770 | [5 empty] | 274712 |  | 116127