## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2022-02-24 | February 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | NZTA (Otago) | SH6 SH8B SH8 Gibbston to Clyde Corridor Imps | Construction | Nevis Bluff cycle connection - construction | VHML | MML | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | Enables the new Kawarau Gorge cycle trail to pass safely around the SH6 Nevis Bluff section, and honours an open letter of commitment to the Trust signed by MBIE, NZ Transport Agency and NZ Cycle Trails. BCR is 9.7 | 2592000 | 2592000 |  |  | 9.7 | 0.4 | Nevis Bluff cycle connection - construct | 266625 | 60052351 | 116695
2022-02-04 | February 2022 Review | New approval | Local road maintenance | Emergency works | Auckland Transport | E/W - West Auckland - 31 August 2021 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | As approved by NM, Prog & Standards | 3671659 | 1872546 |  |  |  |  | 141.28 | 279955 |  | 115913
2022-02-09 | February 2022 Review | New approval | Local road maintenance | Emergency works | Central Hawkes Bay District Council | E/W Kairakau Road Slip November 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | That the National Manager Maintenance & Operations: Approves Central Hawkes Bay District Council Emergency Works at a total cost $1,700,000 (NLTF share $1,147,061) to enable CHBDC to proceed with construction of a short slip by-pass road as the most cost-effective reinstatement option following a severe rain event that moved down the coast from Gisborne into the Hawke's Bay between the 3 he 6 November 2021. As required under Business rule BR166 | 1139691 | 695212 |  |  |  |  | construction | 280315 |  | 115926
2022-02-22 | February 2022 Review | New approval | Local road maintenance | Emergency works | Gisborne District Council | 20 June 2021 Weather Event | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | That the National Manager, Programme and Standards, Transport Services: APPROVE emergency works funding (between $5m and $15m) to Gisborne District Council for the project at a cost of $6,454,838 at an enhanced funding assistance rate of 88% (NLTF share $5,680,257). NB - Enhanced FAR policy is applied on a year by year basis & future FARs (eg 2020/23 is not known yet) so not correct to assume 88%. 67% is system generated & this is what is being approved. IA should not be assuming FAR% for future years and future approval papers should reflect this. | 6454838 | 4660741 |  |  |  |  | Emergency Works: 20 June 2021 Flood Damage | 279377 |  | 115326
2022-02-10 | February 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW SH4 Burrells Road Washout 20210821 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | The Work has already been completed. Any opportunity to comment on suitability of repair options has been lost. It looks like the event has triggered qualification through the â€œhave reduced, or will reduce within a 12 month period, levels of transport service significantly below those that existed prior to the eventâ€ It is recommend a lesson learnt exercises for this event. | 838425 | 838425 | [5 empty] | 279376 | 60064543 | 116326
2022-02-11 | February 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Tasman) | EW Tasman Flood 20210717 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Record floods around the Top of the South Island and West Coast leading to widespread slips, drop-outs and inundation around the region. This application is for works from the initial response and through the early recovery through to 18th September 2021. Further applications will be required for the larger sites and options reports will be submitted. See email attached for approval by Wayne (SMSM - TS) | 3240000 | 3240000 | [5 empty] | 278814 | 60063027 | 116405
2022-02-18 | February 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (West Coast) | EW SH73 Otira Shelter Rockfall 20211017 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | all paperwork attached and approved. | 156600 | 156600 | [5 empty] | 280257 | 60066144 | 116626
2022-02-18 | February 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (West Coast) | EW WC SH6 Fox Hills US 20210615 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | all paperwork approved and attached. | 145745 | 145745 | [5 empty] | 278214 | 60061898 | 116625
2022-02-23 | February 2022 Review | New approval | Local road maintenance | Emergency works | Selwyn District Council | EW - May 2021 Heavy Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | Refer to funding paper and supporting documents. Addressing the immediate response and reinstatement of levels of service because of the significant impact of natural events; and Maintaining appropriate customer levels of service, to provide safe and resilient access to social and economic opportunities, including tourism and freight movements. | 3900000 | 2769000 |  |  |  |  | Phase 2 - Reinstatement | 280435 |  | 116685
2022-02-28 | February 2022 Review | New approval | Public transport services | Passenger services - bus | Environment Canterbury | Timaru On Demand Service | Implementation | Implementation | HHM | VHHVH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Important trial to continue innovations and improve efficiencies | 3600000 | 1836000 |  |  |  | 2 | implementation | 278077 |  | 116468
2022-02-01 | February 2022 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | One Network Framework | Programme business case |  | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The ONF will re-focus the way RCAs and Waka Kotahi deliver strategic outcomes and operate their networks now and for the future as endorsed by NM, Prog & Standards and approved by CFO. | 2000000 | 2000000 | [5 empty] | 280299 |  | 115927
2022-02-22 | February 2022 Review | New approval | Road to Zero | Road improvements | NZ Transport Agency | SIP - Programme Management | Pre-implementation* | SIP Programme Management | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Required to establish programme management practices (including Governance, Management, Financial management, tools and systems) within the Speed and Infrastructure programme. | 24000000 | 24000000 |  |  | 2.2 | 2.2 | 60063778 | 277979 |  | 115893
2022-02-22 | February 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Auckland) | AHB Edge Barrier Strengthening | Implementation | AHB west edge barrier strengthening R2Z | HHVL | HHL | N | 9 | Approved | Approved by Chief Financial Officer (CFO) | Safety improvements to the existing barrier which is currently substandard. | 2916000 | 2916000 |  |  |  | 0.8 |  | 279118 | 60063777 | 114086
2022-02-02 | February 2022 Review | New approval | State highway improvements | Road improvements | NZTA (BOP) | SH2 Hewletts Road Sub area Access | Single-Stage Business Case | Indicative and Detail Business Case phase | VHHL | HML | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | This activity; - Is aligned to the GPS - Gives effect to the UFTI and WBOP Transport System Plan - Is urgent | 1080000 | 1080000 |  |  |  | 2.7 |  | 277415 | 60061770 | 115688
2022-02-17 | February 2022 Review | New approval | State highway improvements | Road improvements | NZTA (Marlborough) | SH1 SH62 Spring Creek Intersection RAB | Implementation | SH Improvements | MHM | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Remaining funds moved from Regional Improvements to SH Improvements | 168489 | 168489 |  |  | 1.5 | 1.5 | SAP Item 60217472 | 280096 | 60217472 | 115588
2022-02-04 | February 2022 Review | New approval | State highway improvements | Road improvements | NZTA (Southland) | Edendale Realignment | Implementation |  | MHM | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project nearly complete. Moving remaining funds to SH Improvements AC | 259702 | 259702 |  |  | 1.2 | 1.2 |  | 278941 | 60211840 | 116490
2022-02-18 | February 2022 Review | New approval | Local road improvements | Road improvements | Western BoP District Council | Omokoroa Road Corridor Improvements | Implementation | RP 2180 - 3700 (LR) | MHL | HHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Remaining funds being moved to the LR Improvements activity class. | 5138000 | 2620380 |  |  | 0 | 1.1 |  | 280177 |  | 115709
2022-02-08 | February 2022 Review | New approval | Local road improvements | Road improvements | Whangarei District Council | Maunu Road/Central Ave/Walton St/Water St Intersection Imp | Implementation | Maunu/Central Intersection | HMM | HHM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Improved network efficiency by reduction of intersection delay in peak periods. | 2394000 | 1268820 |  |  | 0 | 3.8 |  | 260579 |  | 116266
2022-02-21 | February 2022 Review | New approval | Investment management (incl. Transport Planning) | Transport model development | Waikato Regional Council | Rebuild of Waikato Regional Transport Model (WRTM) NEW | Programme business case |  | H__ | V__ | N |  | Approved | Approved by Chief Financial Officer (CFO) | The suite of models within the region are used for a range of activities from high level strategic network planning, to plan changes, to corridor design and network management. They are the only available tools for consideration of future changes to land use and transport. They underpin every investment decision from an intersection upgrade all the way up to a new network of cycling/PT. | 3357913 | 1156212 | [5 empty] | 277842 |  | 116386
2022-02-18 | February 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Central Isthmus & Sandringham | Detailed Business Case | Cycling Investment - Central & Sandringham - DBC | HHM | HMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, the completion of this activity is indicated to slip, so this is a cost neutral cashflow change. | 0 | 0 |  |  | 0 | 3.2 | 452.2613 | 261280 |  | 116505
2022-02-18 | February 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - City Centre & Fringe | Detailed Business Case | Cycling Investment - City Centre and Fringe - DBC | HHM | HMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, the completion of this activity is indicated to slip, so this is a cost neutral cashflow change. | 0 | 0 |  |  | 0 | 3.2 | 452.2613 | 261263 |  | 116506
2022-02-16 | February 2022 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Opotiki District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Street lighting infill project progressing ahead of schedule | 0 | 0 | [5 empty] | 276334 |  | 116605
2022-02-16 | February 2022 Review | Cash flow adjustment | Walking and cycling improvements | Low cost / low risk improvements | Opotiki District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Motu Trails project progressing ahead of schedule | 0 | 0 | [5 empty] | 276332 |  | 116604
2022-02-16 | February 2022 Review | Cash flow adjustment | Local road maintenance | Minor events | Opotiki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Movement of funds to align with the revised MOR programme | -36676 | -27507 | [5 empty] | 273686 |  | 116606
2022-02-18 | February 2022 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | TNFG - North West HIF | Repayment | TNFG - Redhills HIF Repayment (NLTF) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This is correcting the repayment phase for Redhills to align with the cashflow adjustments currently being requested. | 0 | 0 |  |  | 5 | 1.4 | 323.2665 | 266462 |  | 116512
2022-02-18 | February 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Northland) | SH1 Loop Road North to Smeatons Hill Safety Improvement | Property | NLTF-SH Improvements | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | $1,531,366 in June 2022; $1,531,366 in June 2023 | 0 | 0 |  |  | 0 | 1.2 | 60437382 | 278792 | 60437382 | 116532
2022-02-18 | February 2022 Review | Cash flow adjustment | External funding | Resilience improvements | NZTA (Taranaki) | RIO SH43 Manawawiri Stream Culvert IMPR | Pre-implementation* |  | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Close this Project Phase | 0 | 0 |  |  |  |  | Design | 269736 | 60056103 | 116535
2022-02-18 | February 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Lincoln Road Corridor Improvement | Pre-implementation* | Lincoln Road Corridor Imp-Design | HHVH | HHVH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | AT has indicated slippage in delivery of this activity and is cash flowing money further out - (cost neutral overall). | 0 | 0 |  |  | 7.5 | 7.5 | 324.2191 | 219098 |  | 116507
2022-02-18 | February 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | Auckland Transport | Safe Speeds Programme | Pre-implementation* | Speed Mgmt - Pre-Imp- R2Z | VH_VH | VHHVH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This phase is more advanced than expected when the CSA was completed and therefore we are seeking a cost neutral cashflow adjustment to realign spend based on current forecast. | 0 | 0 |  |  | 0 | 12 | 324.2696 | 279201 |  | 116470
2022-02-18 | February 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Ashley to Belfast - (William St to Saltwater Creek) | Pre-implementation* | SH1 Ashley to Belfast Saltwater-William | HHL | HHH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflowing $175K from 2024 to 2022 for design | 0 | 0 |  |  | 0 | 1.6 |  | 278548 | 60062295 | 116530
2022-02-17 | February 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Taranaki) | SH3/3A Waitara to Bell Block | Detailed Business Case | Waitara to Bell Block Route Imp: SH3/3A to Waitara | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Future spend against SH Improvements AC. | -1 | -1 |  |  | 1.1 | 1.1 | 60041305 | 232681 | 60041305 | 115592
2022-02-16 | February 2022 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Opotiki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Movement of funds to align with the revised MOR programme | 49533 | 37150 | [5 empty] | 273682 |  | 116606
2022-02-16 | February 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Opotiki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Movement of funds to align with the revised MOR programme | -61700 | -46276 | [5 empty] | 273695 |  | 116606
2022-02-16 | February 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Opotiki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Movement of funds to align with the revised MOR programme | 171723 | 128792 | [5 empty] | 273693 |  | 116606
2022-02-16 | February 2022 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | Opotiki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Movement of funds to align with the revised MOR programme | -122880 | -92160 | [5 empty] | 273681 |  | 116606
2022-02-04 | February 2022 Review | Cost Decrease | Local road maintenance | Bridge and structures renewals | Tararua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cist neutral | -1052238 | -728173 | [5 empty] | 274211 |  | 116205
2022-02-18 | February 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | SH16 Central Auckland Connection (CMJ/I) | Property |  | H_H | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -31009 | -31009 |  |  | 0 | 7743 | 60031726 | 247090 | 60031726 | 116536
2022-02-18 | February 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Manawatu/Whanganui) | Manawatu River Bridge SH3 Ashhurst Cycle/walkway | Single-Stage Business Case | Single Stage Business Case | VHHL | MHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -34141 | -34141 |  |  | 1.7 | 1.7 |  | 268601 | 60034090 | 116539
2022-02-16 | February 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Northland) | EW SH01N Otonga Drought/Flood 20200211 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This project is technically complete and 21/22 funds surplused. | -141418 | -141418 | [5 empty] | 270842 | 60058332 | 116603
2022-02-18 | February 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Taranaki) | EW SH43 Hospital Hill | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close $230,962 Surplus | -249439 | -249439 | [5 empty] | 265881 | 60051201 | 116538
2022-02-18 | February 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Taranaki) | EW SH43 Pohokura Culvert | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close $89,459 surplus | -96616 | -96616 | [5 empty] | 269517 | 60055773 | 116540
2022-02-04 | February 2022 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Manawatu District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Standard cost scope adjustment as project brought with no additional cost. | 0 | 3175 | [5 empty] | 276218 |  | 116366
2022-02-28 | February 2022 Review | Cost Increase | Public transport infrastructure | Low cost / low risk public transport improvements | Gisborne District Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Endorse the cost adjustment and recommend that the Chief Financial Officer approve funding to Gisborne District Council for Public Transport infrastructure LCLR program for an increase of $37,131 at a funding assistance rate of 68% ($25,250 out of the NLTF) for Public Transport Infrastructure from Low Cost low Risk thereby increasing the approved total cost from $440,000.00 to $477,13.00 | 37133 | 25250 | [5 empty] | 276130 |  | 116285
2022-02-04 | February 2022 Review | Cost Increase | Local road maintenance | Minor events | Tararua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cist neutral | 0 | 900 | [5 empty] | 274200 |  | 116205
2022-02-15 | February 2022 Review | Cost Increase | Local road maintenance | Network and asset management | Auckland Transport | COVID-19 impact on Maintenance costs | Implementation | COVID-19 cost impact 2021 - NLTF | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Additional funds agreed by CE and CFO due to extended lockdown period. | 34698 | 34698 |  |  |  |  | 151.2794 | 279398 |  | 116583
2022-02-15 | February 2022 Review | Cost Increase | Local road maintenance | Network and asset management | Hauraki District Council | COVID-19 TTM costs | Implementation | COVID-19 cost impact 2021 NLTF | H_L | HHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Both CE and CFO agree that NLTF will cover this cost (see attached email). | 154394 | 154394 | [5 empty] | 279395 |  | 116545
2022-02-15 | February 2022 Review | Cost Increase | Local road maintenance | Network and asset management | Kaipara District Council | COVID-19 TTM costs | Implementation | COVID-19 cost impact 2021 NLTF | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Additional funds agreed by CE and CFO due to extended lockdown period. | 54519 | 54519 | [5 empty] | 279396 |  | 116584
2022-02-15 | February 2022 Review | Cost Increase | Local road maintenance | Network and asset management | Waikato District Council | COVID-19 TTM costs | Implementation | COVID-19 cost impact 2021 NLTF | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Additional funds agreed by CE and CFO due to extended lockdown period. | 20006 | 20006 | [5 empty] | 279397 |  | 116585
2022-02-18 | February 2022 Review | Cost Decrease | Debt Funding | New roads | Auckland Transport | TNFG - North West HIF | Implementation | TNFG - NW HIF - Redhills (IMP) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | AT's Board has now confirmed continuation of the Redhills activity using the HIF. This is based on the lastest indicative forecast (but may be subject to change as discussions are being finalised with developers) | -6306331 | -6306331 |  |  | 5 | 1.4 | 323.264 | 263982 |  | 116510
2022-02-04 | February 2022 Review | Cost Increase | State highway improvements | New roads | NZTA (Taranaki) | SH3 Mt Messenger Bypass | Construction | Construction | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update Admin rate | 11321290 | 11321290 |  |  | 0.5 | 0.5 | 60038700 | 260256 | 60038700 | 116486
2022-02-04 | February 2022 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (Hawkes Bay) | Weigh Right Napier Port | Implementation | Construction/Implementation (C) | H_H | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update Admin rate. | 172412 | 172412 |  |  | 14 | 14 | 60032036 | 250274 | 60032036 | 116487
2022-02-18 | February 2022 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | Auckland Transport | Future Ferry Development | Programme business case |  | V_L | V_L | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity has now been completed and supported by Waka Kotahi's Board in November 2021, so the balance of this activity is now surplus. | -292915 | -149387 |  |  |  |  | 4.2692 | 269233 |  | 116513
2022-02-04 | February 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (BOP) | Weigh Right Tauranga Port | Property |  | H_VH | H_VH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update Admin rate. | 29000 | 29000 |  |  | 14 | 14 |  | 260623 | 60047945 | 116488
2022-02-04 | February 2022 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Property | Property | H_M | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase for project is closing and returning surplus of $2244 | -2368 | -2368 |  |  | 1.5 | 1.5 | 60465152 | 212337 | 60465152 | 116445
2022-02-04 | February 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | RIO SH02 College Rd-Silverstream IMPR | Property |  | L_M | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | updating historical $$ to match SAP | 61954 | 61954 |  |  | 1 | 1 | 60423452 | 247470 | 60423452 | 116485
2022-02-04 | February 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | RIO SH02 College Rd-Silverstream IMPR | Property |  | L_M | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | additional acquisition fund of 4,134$ to close the project | 22815 | 22815 |  |  | 1 | 1 | 60423452 | 247470 | 60423452 | 116473
2022-02-18 | February 2022 Review | Cost Increase | Debt Funding | Property purchase (local roads) | Auckland Transport | TNFG - North West HIF | Property | TNFG - NW HIF - Redhills (PROP) | HHH | H_H | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | AT's Board has now confirmed continuation of the Redhills activity using the HIF. This is based on the lastest indicative forecast (but may be subject to change as discussions are being finalised with developers). It is noted that this remains balanced between the Redhills IMP and Redhills PROP phases, however this phase has increased and the IMP phase has decreased. This has been discussed with Waka Kotahi who are comfortable for the change between the phases as long as the values remain within the original total approval for Redhills. | 6306331 | 6306331 |  |  | 5 | 1.4 | 332.264 | 263983 |  | 116511
2022-02-22 | February 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | DELETE - LGWM CS South West CBD | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds being moved to correct work category | -3173968 | -3173968 |  |  | 1.2 | 1 |  | 280369 | 60066167 | 116682
2022-02-15 | February 2022 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Implementation | SH26 Onetai Stream Bridge Replacement | H_PV_EoL | MMH | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Increased bid costs | 526419 | 526419 |  |  | 0 | 0 |  | 231694 | 60052985 | 115889
2022-02-15 | February 2022 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Pre-implementation* | SH26 Onetai Stream Bridge Replacement | H_PV_EoL | MMH | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Increased bid costs | 193814 | 193814 |  |  | 0 | 0 |  | 231693 | 60052984 | 115888
2022-02-18 | February 2022 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | Lake Road Corridor Improvements | Detailed Business Case | Lake Rd Corridor improvements (IBC) | HML | MML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is now complete so the balance of the activity is being declared surplus. | -385862 | -196790 |  |  | 0 | 1.3 | 324.2467 | 246712 |  | 116543
2022-02-18 | February 2022 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | Murphys Road Culvert Improvements | Construction | Murphys Rd Culvert Improvements - Construction | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is nearly complete and so a partial surplus is declared at this time for some of the residual. Final costs will be confirmed once the last minor works are completed. | -450000 | -229500 |  |  | 1 | 1 | 324.219 | 218991 |  | 116542
2022-02-03 | February 2022 Review | Cost Increase | Local road improvements | Road improvements | Christchurch City Council | AAC High Street (Cashel to Tuam) | Construction |  | H_L | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Part of refunding Cranford Street local share | 0 | 323511 |  |  | 2.9 | 2.9 |  | 233357 |  | 115423
2022-02-03 | February 2022 Review | Cost Increase | Local road improvements | Road improvements | Christchurch City Council | Accelerated LED Conversion Programme | Implementation |  | M_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Part of refunding Cranford Street local share | 0 | 39373 |  |  | 0 | 0 | Normal FAR | 262816 |  | 116469
2022-02-03 | February 2022 Review | Cost Decrease | Local road improvements | Road improvements | Christchurch City Council | Accelerated LED Conversion Programme | Implementation |  | M_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduced FAR as part of Cranford Street local share | 0 | -572233 |  |  | 0 | 0 | Normal FAR | 262816 |  | 115422
2022-02-03 | February 2022 Review | Cost Increase | Local road improvements | Road improvements | Christchurch City Council | Christchurch Northern Corridor - Local Share Activity | Implementation |  | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Offset not required for 2021/22 | 11955456 | 11955456 |  |  | 2.3 | 2.3 |  | 262719 |  | 116268
2022-02-03 | February 2022 Review | Cost Decrease | Local road improvements | Road improvements | Christchurch City Council | Corridor 2 - Inters Improvement:Lower Styx/Marshland | Construction | Intersection and bridge improvements | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduced FAR as part of Cranford Street local share | 0 | -2131067 |  |  | 1.1 | 1.1 |  | 226230 |  | 115426
2022-02-21 | February 2022 Review | Cost Increase | External funding | Road improvements | Kaipara District Council | PGF - Pouto Rd Seal Extensions | Pre-implementation* | Stage 2 Investigation | H_H | VH_VH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Incorrect FAR, prior increase approved by MBIE. | 0 | 310000 |  |  | 1 | 1 | Stage 2 Investigation | 269895 |  | 116662
2022-02-02 | February 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Northern Corridor Improvements (NCI) | Construction | Construction - Main | H_M | H_M | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Provides a risk budget for the final completion of the NCI project as approved by the Board with delegation to release passed to CFO. | 12220000 | 12220000 |  |  | 3 | 3 | 60027507 | 254897 | 60027507 | 115703
2022-02-18 | February 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH29A Maungatapu Median Barrier Extension | Construction |  | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -60024 | -60024 |  |  | 2.2 | 2.2 | 60043427 | 250094 | 60043427 | 116533
2022-02-24 | February 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (BOP) | SH33 (Te Ngae Junction to Paengaroa), NSRRP | Implementation |  | H_H | HHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | The Stage 3 safety improvements along the SH33 corridor will be completed providing DSI savings in line with the Toward Zero objectives delivering a consistent 34km safer route for road users between the eastern end of the SH2 Tauranga Eastern Link (TEL) and the SH30/SH33 Intersection north-east of Rotorua. | 4921891 | 4921891 |  |  | 1.2 | 1.2 |  | 278523 | 60062268 | 116288
2022-02-18 | February 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH5/SH30 Hemo Road/Old Taupo Road Safety Improvements | Construction | Construction | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -16416 | -16416 |  |  | 2 | 2 | 60032988 | 231379 | 60032988 | 116537
2022-02-04 | February 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Ashley to Belfast SSI (William St to SH71) | Pre-implementation* | R2Z | M_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | surplus to close the phase | -247802 | -247802 |  |  | 0 | 1.6 | R2Z | 278547 | 60062299 | 116426
2022-02-04 | February 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Hawkes Bay) | Prebensen Hyderabad Intersection upgrade | Pre-implementation* | Pre Implementation - 324 | M_H | MHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -994 | -994 |  |  | 14.6 | 14.6 |  | 270291 | 60214527 | 116389
2022-02-04 | February 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Hawkes Bay) | RIO SH02 College Rd-Silverstream IMPR | Implementation | Construction | L_M | M_M | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | interphase from construction to property and preimp due to additional property acquisition move 61,579$ to property receive 22,815$ preimp receive 38,764$ | -61579 | -61579 |  |  | 1 | 1 | 60207438 | 269700 | 60207438 | 116472
2022-02-18 | February 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Hawkes Bay) | RIO SH02 College Rd-Silverstream IMPR | Pre-implementation* | Design updates | L_M | M_M | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -38766 | -38766 |  |  | 1 | 1 |  | 269697 | 60056023 | 116541
2022-02-04 | February 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Hawkes Bay) | RIO SH02 College Rd-Silverstream IMPR | Pre-implementation* | Design updates | L_M | M_M | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | interphase 38,764$ from construction to close the preimp phase | 38766 | 38766 |  |  | 1 | 1 |  | 269697 | 60056023 | 116474
2022-02-18 | February 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Hawkes Bay) | RIO SH02 College Rd-Silverstream IMPR | Pre-implementation* | Design updates | L_M | M_M | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstating surplus as actual expenditure of $38,764 in 2022 | 38764 | 38764 |  |  | 1 | 1 |  | 269697 | 60056023 | 116622
2022-02-17 | February 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Marlborough) | SH1 SH62 Spring Creek Intersection RAB | Implementation | Old Regional Improvements AC | MHM | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplused funds from obsolete Activity Class, move to SH Improvements | -160064 | -160064 |  |  | 1.5 | 1.5 | SAP Item 60217472 | 277152 |  | 115505
2022-02-18 | February 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Nelson - SH6/SH62 | Implementation | R2Z | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | 662k can be surplused now - contigency not required with construction substantially completed in 2021 | -715062 | -715062 |  |  | 0 | 1.6 |  | 278554 | 60062291 | 116528
2022-02-18 | February 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Nelson - SH6/SH62 | Pre-implementation* | R2Z | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | pre-impl phase complete | -4152 | -4152 |  |  | 0 | 1.6 |  | 278555 | 60062292 | 116529
2022-02-01 | February 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Otago) | Dunedin City and Hospital | Detailed Business Case | Single Stage DBC for arterial roading component | HML | HLL | N | 6 | Approved | Approved by Chief Financial Officer (CFO) | Cost scope adjustment for SH88 SSBC of $704,774 (includes 8% admin) approved by delegations and awaiting Board sign off before commencing. SH88 SSBCto consider future location of SH88 in response to New Dunedin Hospital development | 704774 | 704774 |  |  | 0 |  |  | 266665 | 60052443 | 115692
2022-02-09 | February 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Otago) | Visiting Driver Signature Project Otago | Implementation | Implementation | M_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | These funds were surplused as project was meant to be closed. However surplused funds is now required to finish this project. | 216000 | 216000 |  |  | 6.9 | 6.9 | 60029890 | 233468 |  | 116525
2022-02-04 | February 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH1 South-East Hamilton Improvements | Construction | SH1 Cobham/Cambridge Improvements Construction | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update Admin rate. | 232200 | 232200 |  |  | 5.9 | 5.9 | 60033606 | 239051 | 60033606 | 116489
2022-02-18 | February 2022 Review | Cost Decrease | Local road improvements | Road improvements | Western BoP District Council | Omokoroa Road Corridor Improvements | Construction | RP 2180 - 3700 | MHL | HHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This phase was originally approved under the Regional Improvements activity class which finished at the end of the 2018-21 NLTP. The remaining funds are being moved to a new phase under LR Improvements, and this phase will be corrected to show the first 2 year's spend in Regional Improvements AC. | -5138000 | -2620380 |  |  | 0 | 1.1 |  | 264883 |  | 115710
2022-02-04 | February 2022 Review | Cost Increase | Local road maintenance | Structures component replacements | Tararua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cist neutral | 1052238 | 728173 | [5 empty] | 274210 |  | 116205