## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2022-03-18 | March 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW Mana/Whang Regionwide HR 20220206 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | This application covers the initial response to reopen roads and attend to the removal of the debris/detritus/trees remaining roadside following the event of Waitangi Weekend. Two sites require a planned approach to reinstate the damaged infrastructure on SH3 and SH54. Both have last traffic lanes and structural/drainage facilities as a result of the heavy rains. This region was one of many that received damage that resulted in wide spread clean-up. WK. | 846720 | 846720 | [5 empty] | 280680 | 60066615 | 116949
2022-03-18 | March 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW Manawatu SH54 HR 20211215 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | Approved by Rob Service - System Manager | 187833 | 187833 | [5 empty] | 280456 | 60066423 | 116947
2022-03-24 | March 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Taranaki) | EW SH45 HR 20220204 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | Losing access to SH45 and SH3 creates longer travel times for motorists. There was a significant risk to safety caused by this event. | 908212 | 908212 | [5 empty] | 280701 | 60066723 | 117028
2022-03-16 | March 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast Bonar Crk HR 20211205 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | The damaged assets will be able to be returned to original condition/normal level of service | 1841172 | 1841172 | [5 empty] | 280575 | 60066516 | 116624
2022-03-10 | March 2022 Review | New approval | Local road maintenance | Emergency works | Opotiki District Council | Emergency Works - Opotiki District Council - Feb 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | High rainfall has caused riverbank scour encroaching into roads and cycleway, bridge abutment scour, road pavement scour to parts of the Opotiki network. Installation of rip rap at Otara road sites to protect bank from future river encroachment. Tutaetoko bridge east abutment and pier protection, pavement repairs, stabilise and repair of slumps. Transport levels of service will reduce significantly below those that existed prior to the event within a 12 month period if repairs are not carried now. This single application covers the initial response and permanent reinstatement. BR164 approval paper attached | 236326 | 177245 |  |  |  |  | Reinstatement and Repair | 280719 |  | 116684
2022-03-03 | March 2022 Review | New approval | Local road maintenance | Emergency works | Tararua District Council | Event November 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Supported as per regional comment | 639982 | 447987 |  |  |  |  | Event November 2020 - Cost Scope Adjustment | 279979 |  | 115381
2022-03-04 | March 2022 Review | New approval | Local road maintenance | Emergency works | Wairoa District Council | Emergency Works September 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Recommended as per Regional Office comments | 1871004 | 1777454 |  |  |  |  | Clean-Up and Construction | 280176 |  | 115697
2022-03-29 | March 2022 Review | New approval | Local road maintenance | Emergency works | Waitomo District Council | EW - Waitomo DC February 2022 Cyclone Dovi | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | Between Friday 11 February to Saturday 12 February, Cyclone Dovi struck the west coast of the Waitomo District and produced a very heavy rain band on a concentrated path. (>1 in 250 year storm return period) Recommendation That the Regional Manager â€“ Maintenance and Operations: Approves: Waitomo District Councilâ€™s Emergency Works Initial Response request at a total cost of $600,000. Waitomo DC has suffered no previous storm damage claimable from WC 141 this financial year. The net NLTF Share for the Initial Response of this event is $450,000 at normal FAR of 75%. Notes: This cost relates to the initial response only, to make safe, provide temporary access and clean up of the transport network. Notes: Initial rough order cost for the Emergency Works Permanent Reinstatement is estimated in the vicinity of $16,130,000. This will be subject to a second paper with the prerequisite Council and Waka Kotahi assurance processes occurring first. Breakdown of FAR calculation is attached in TIO. The current estimated net NLTF Share for this event is in the vicinity of $15.2m with majority of funding at 95% FAR and some at 75%. This estimate is likely to be revised once site visits have been carried out and lower cost options have been determined. | 600000 | 450000 |  |  |  |  | Initial Response | 280998 |  | 117003
2022-03-10 | March 2022 Review | New approval | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Investment in the Funding Allocation System (IFAS) | Implementation | 2021-24 NLTP 3 year programme | HHVH | HHVH | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | Nationally delivered activity to support NLTP Development and Management. | 160000000 | 160000000 |  |  | 1 | 1 |  | 278317 |  | 116834
2022-03-24 | March 2022 Review | New approval | Local road improvements | New roads | Hamilton City Council | 2018-28 Rototuna Growth - Borman Rd East/Horsham Downs | Implementation | Construction | HML | MHM | N | 6 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | This investment provides improved access for housing and improving active mode access to the Rototuna schools & community facilities. The BCR is 1.0 This investment complies with Section 20 of the LTMA. | 20558080 | 8882201 | Subject to the condition subsequent that if any other crown funding is granted for this project then it will be treated as a third party contribution and the NLTF share will be recalculated, unless Waka Kotahi agrees that funding may be used as local share. Subject to the condition subsequent that Hamilton City Council delivers the scope and outcomes of 2018-28 Rototuna Growth - Borman Rd East/Horsham Downs with Waka Kotahi funding assistance capped at the NLTF share of $8,882,201. Any increases in costs are at Councilâ€™s risk and are not eligible for further NLTF subsidy. |  | 1.1 | 1.1 |  | 257327 |  | 116465
2022-03-12 | March 2022 Review | New approval |  | Property purchase (State highways) | NZTA (Auckland) | 20Connect (Southern and Eastern Airport Access Imps) | Property | 20Connect (Airport Access Imps) - 331 | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixng wc to 331 | 8967500 | 8967500 |  |  | 1.4 | 1 |  | 280899 | 60060541 | 116849
2022-03-12 | March 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Auckland) | SH1 Dome Valley Safety Improvements | Property | RTZ | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc from 324 to 331 | 274889 | 274889 |  |  | 0 | 1 |  | 280898 | 60062157 | 116846
2022-03-12 | March 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (BOP) | W2T Waihi to Omokoroa (Safer Corridor) | Property | Property RTZ 331 | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | fixing wc to 311 | 2077636 | 2077636 |  |  | 0 | 1 |  | 280900 | 60062262 | 116851
2022-03-12 | March 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Marlborough) | SH6 Blenheim to Nelson - SH6/SH62 | Property | RTZ 331 | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc 311 | 90424 | 90424 |  |  | 0 | 1.6 |  | 280901 | 60062293 | 116854
2022-03-13 | March 2022 Review | New approval | Walking and cycling improvements | Property purchase (State highways) | NZTA (Otago) | Wakatipu Walking/Cycling Network Improvements | Property | NZTA Package 331 | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc 311 | 1315186 | 1315186 |  |  | 2.6 | 2.6 |  | 280902 | 60052907 | 116856
2022-03-13 | March 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Taranaki) | SH3/3A Waitara to Bell Block | Property | R2Z 331 | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc 331 | 6914867 | 6914867 |  |  | 1.1 | 1.1 |  | 280905 | 60062276 | 116864
2022-03-13 | March 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Waikato) | SH27 Mangawhero Bridge | Property | RTZ 331 | HML | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | fixing wc to 331 | 32183 | 32183 |  |  | 2.1 | 2.1 |  | 280904 | 60062212 | 116862
2022-03-13 | March 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Wellington) | SH58 Safety Improvements | Property | RTZ 331 | VHHL | HML | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | fixing to wc 331 | 1054442 | 1054442 |  |  | 1.3 | 1.3 |  | 280903 | 60064032 | 116859
2022-03-18 | March 2022 Review | New approval | Local road improvements | Replacement of bridges and other structures | Whanganui District Council | Detailed Business Case - Dublin Street Bridge (71) | Detailed Business Case | Dublin Street Bridge (71) | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This Business Case will develop options to address the Dublin street bridge, Whanganui, which has exceeded end of life (100 years). The bridge has been restricted to certain HCV vehicles with weight restrictions. â€¢ This PoE supports the strategic direction of the GPS in enabling mode shift, improving freight connectivity, improved resilience and supporting climate change (transitioning the transport network to low carbon). â€¢ Carrying out this phase will provide more certainty for the way forward for preimplementation and implementation. â€¢ Delaying the decision on this bridge increases severance of the CBD and residential roads and increases journey times for freight between the east and west. â€¢ Preliminary PVEOL indicates that the bridge should replace in the next 1 â€“ 3 years, a comprehensive PVEOL should be carried out for renewal/business case. â€¢ Note: Preliminary PVEOL indicates maintenance and/or bridge replacement NPV cost of $22M (Bridge replacement in Year 1 - 3) or $30M (Maintain the bridge and then bridge replacement in Year 6 - 10). This will have a significant bearing on the Activity class in subsequent NLTPâ€™s. | 300000 | 181000 |  |  |  | 1 | Dublin Street Bridge (71) | 280778 |  | 116742
2022-03-01 | March 2022 Review | New approval | Road to Zero | Road improvements | NZ Transport Agency | Road to Zero System Management | Implementation | RtZ System Management | VHHL | MHH | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Recommend to implementation | 14580000 | 14580000 |  |  | 8 | 8 | SAP Item ID 60067001 | 277093 |  | 115534
2022-03-21 | March 2022 Review | New approval | State highway improvements | Road improvements | NZ Transport Agency | Safe Network Programme 2018-21 NLTP | Pre-implementation* | SNP-Programme Management (State Highways) | HHL | VHHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Supporting the deliver of the Safe Network Programme. | 10361455 | 10361455 |  |  | 0 | 1.6 |  | 280959 |  | 116950
2022-03-29 | March 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Northland) | SH1 Whangarei to Wellsford - (Central Section) | Implementation |  | VHML | HHM | N | 3 | Approved | Approved by Chief Financial Officer (CFO) |  | 3434400 | 3434400 |  |  | 0 | 1.6 |  | 278315 | 60053476 | 116773
2022-03-29 | March 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Northland) | SH1 Whangarei to Wellsford - (Central Section) | Property |  | VHML | HHM | N | 3 | Approved | Approved by Chief Financial Officer (CFO) |  | 2736670 | 2736670 |  |  | 0 | 1.6 |  | 280683 | 60066689 | 116768
2022-03-07 | March 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Northland) | SH1 Whangarei to Wellsford - (Southern Section) | Implementation |  | HML | HHM | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 1630800 | 1630800 |  |  | 0 | 1.6 |  | 278112 | 60054369 | 115446
2022-03-17 | March 2022 Review | New approval | Road to Zero | Road improvements | Palmerston North City Council | Roberts Line and KB Road - Intersection Safety Improvements | Pre-implementation* | Pre Implementation | VHML | VHHL | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | Endorses the Roberts Line and Kairanga-Bunnythorpe Road - Intersection Safety Improvements safety improvements project and recommends that â€¢ The Chief Financial Officer, Corporate Support, Approve funding to Palmerston North City Council for pre-implementation, and property phases of the Roberts Line and Kairanga-Bunnythorpe Road - Intersection Safety Improvements at a cost of $1.62M [51% FAR, $0.83M from the NLTF]That the National Manager Programme and Standards, Transport Services: | 880000 | 448800 | [5 empty] | 276732 |  | 116269
2022-03-17 | March 2022 Review | New approval | Road to Zero | Road improvements | Palmerston North City Council | Roberts Line and KB Road - Intersection Safety Improvements | Property | Property Purchase | VHML | VHHL | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | That the National Manager Programme and Standards, Transport Services Endorses the Roberts Line and Kairanga-Bunnythorpe Road - Intersection Safety Improvements safety improvements project and recommends that â€¢ The Chief Financial Officer, Corporate Support, Approve funding to Palmerston North City Council for pre-implementation, and property phases of the Roberts Line and Kairanga-Bunnythorpe Road - Intersection Safety Improvements at a cost of $1.62M [51% FAR, $0.83M from the NLTF] | 740000 | 377400 | [5 empty] | 280679 |  | 116544
2022-03-03 | March 2022 Review | New approval | Road to Zero | Safety promotion, education and advertising | NZ Transport Agency | Safe Vehicles Programme 21-24 | Single-Stage Business Case | Safe Vehicles Programme SSBC | MHVH | MHVH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 6105000 | 6105000 |  |  | 17 | 17 | 80002367 | 280826 |  | 116747
2022-03-10 | March 2022 Review | New approval | Investment management (incl. Transport Planning) | Transport model development | NZTA (Waikato) | Rebuild Of Waikato Regional Transport Mo | Programme business case |  | H__ | H__ | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 1090832 | 1090832 |  |  |  |  | Investment Management activity class - Phase | 280318 | 60066190 | 116607
2022-03-23 | March 2022 Review | New approval | Walking and cycling improvements | Walking facilities | NZTA (Otago) | SH6 SH8B SH8 Gibbston to Clyde Corridor Imps | Pre-implementation* | W&C | VHML | MML | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funds from SH improvements to W&C to match SAP | 41255 | 41255 |  |  | 9.7 | 0.4 |  | 281000 | 60056371 | 117004
2022-03-03 | March 2022 Review | New approval | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM ED Central City and SH1 walking cycling and safer speed | Implementation | LGWM C.City & SH1 WC+Safer Speed Implementation | HHM | VHHH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) |  | 2808000 | 2808000 |  |  | 1.2 | 1 |  | 267819 | 60059335 | 116471
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | 0 | 0 | [5 empty] | 272835 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Cycle path maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -6519 | -3325 | [5 empty] | 272822 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -69030 | -35205 | [5 empty] | 272832 |  | 116802
2022-03-18 | March 2022 Review | Cash flow adjustment | Local road maintenance | Emergency works | Gisborne District Council | Emergency Event 10 September 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project completed release excess funds | 0 | 0 |  |  |  |  | Emergency Works 10 Sept 2018 (normal FAR | 267951 |  | 116922
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast Cyclone Fehi February 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $2,190,714 allocation to 2023 | -1 | -1 |  |  |  |  | 60048960 | 264804 | 60048960 | 116793
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast March 20190326 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $2,416,335 allocation to 2023 | 0 | 0 | [5 empty] | 267974 | 60053007 | 116799
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -199313 | -101650 | [5 empty] | 272825 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Footpath maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -80361 | -40984 | [5 empty] | 272823 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Footpath renewal | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -93190 | -47527 | [5 empty] | 272839 |  | 116802
2022-03-01 | March 2022 Review | Cash flow adjustment | Public transport services | Low cost / low risk public transport improvements | Otago Regional Council | Low cost / low risk improvements 2021-24 | Public transport services |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correction in cash flow â€“ error caused through NLTP approval process. | 0 | -1 | [5 empty] | 276336 |  | 116582
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | 790264 | 403035 | [5 empty] | 272829 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Network operations | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -30373 | -15490 | [5 empty] | 272827 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -338872 | -172825 | [5 empty] | 272826 |  | 116802
2022-03-11 | March 2022 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | Matakana Link Road â€“ Repayment | Repayment | MLR - Balancing | H_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update to match project surplus | 0 | 0 |  |  | 0 | 7.7 | 323.2673 | 267305 |  | 116833
2022-03-12 | March 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Gisborne) | Safety Retrofit - Gisborne | Construction | Construction | H_H | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project close - $1 is round error | -1 | -1 |  |  | 0 | 3.6 | 60029065 | 213845 | 60029065 | 116852
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Cambridge Section | Construction | . | H_L | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | to cashflow $3,930,122 from CY to Y1. Reasons for deferment â€“ delivery of draft technical pavement report delayed by 2 months (March 2022). Once report finalised and remedial strategy confirmed it is unlikely any major physical works will commence | 0 | 0 |  |  | 1.4 | 1.4 | 60203948 | 173265 | 60203948 | 116811
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Huntly Section | Construction | Construction | H_L | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow $727,774 from CY to Y1 - Delay to revocation works and unresolved bat consent | -1 | -1 |  |  | 1.8 | 1.8 | 60203871 | 195982 | 60203871 | 116794
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Ngaruawahia Section | Construction |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow $13,505,219 from CY to Y1 - due to delays to pavement repairs (COVID) | -3 | -3 |  |  | 0 | 1 | 60202552 | 173253 | 60202552 | 116810
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | Waikato Expressway RoNS Programme Office | Investigation |  | H_L | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow From CY to Y1 $1,672,009, due to delayed completion of WEX, Benefits realisaiton work has been delayed to next FY | 0 | 0 |  |  | 1.1 |  | 60217091 | 205782 | 60217091 | 116805
2022-03-21 | March 2022 Review | Cash flow adjustment | New & improved infrastructure for State highways | New roads | NZTA (Wellington) | Wellington RoNS 4 Ngauranga to Aotea Quay:Active Traffic Mgt | Investigation |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 1.4 | 1.4 | 60216090 | 194527 | 60216090 | 116820
2022-03-03 | March 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Auckland Transport | AKL Metro Train Capacity - Tranche 3 | Implementation | EMU Rolling Stock (Tranche 3) - IMP | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The contract for the new trains has now been placed and based on discussion with the provider, the milestones have been confirmed. The timing for payments may still change, but this will continue to be monitored and AT will update as required. | 0 | 0 |  |  |  | 2.1 | 563.2605 | 260527 |  | 116730
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 (Cambridge to Piarere) Long Term Improvements | Property | Property Phase C2P | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cash flow $3,497,898 from CY to Y1 - no new acquition required this year | -3 | -3 |  |  | 0 | 0.9 | 60048204 | 252060 | 60048204 | 116798
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH26 Kirikiri Stream Bridge Replacement | Property | SH26 Kirikiri Stream Bridge Replacement-property | M__ | M__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | reforecasting | -1 | -1 |  |  | 99 | 99 | 60462002 | 258937 | 60462002 | 116769
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Rail level crossing warning devices maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -1657 | -845 | [5 empty] | 272828 |  | 116802
2022-03-03 | March 2022 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Otago) | Beaumont bridge replacement | Implementation | Beaumont Construction | H__ | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution based on contractors programme | -2 | -2 |  |  | 0 | 12 | 60217046 | 213142 | 60217046 | 116692
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Kirikiri Stream Bridge Replacement | Implementation | SH 26 Kirikiri Stream Bridge Replacement Construct | M__ | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | reforecasting | -2 | -2 |  |  | 99 | 99 | 60031830 | 256636 | 60031830 | 116771
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Kirikiri Stream Bridge Replacement | Pre-implementation* | SH 26 Kirikiri Stream Bridge Replacement Design | M__ | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | reforecasting | -1 | -1 |  |  | 99 | 99 | 60036888 | 258936 | 60036888 | 116772
2022-03-24 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZ Transport Agency | Road to Zero System Management | Implementation | RtZ System Management | VHHL | MHH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 8 | 8 | SAP Item ID 60067001 | 277093 |  | 117029
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | SH2: Baypark to Bayfair Link Upgrade (was MGI) | Construction | Implementation | H_H | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving Surplus $7,188,713 Contingencies wbs 60033676 from year 21/22 to year 22/23 | 1 | 1 |  |  | 2.5 | 2.5 | 60209881 | 194043 | 60209881 | 116844
2022-03-03 | March 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Canterbury) | NZUP Brougham St Corridor Improvements | Implementation | NZUP Brougham St Corridor Improvements | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Construction to start in 2024 | 0 | 0 |  |  | 4 | 4 | 60056968 | 231610 | 60056968 | 116693
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Rakaia to Ashburton CI - Stage 2 | Pre-implementation* |  | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reactivated phase pending NLTP review | 0 | 0 |  |  | 0 | 1.6 |  | 278557 | 60062300 | 116766
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Templeton to Selwyn River | Pre-implementation* | SH1 Templeton to Selwyn River | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow adjustment requested between future FY's to align with NLTP Variation | 0 | 0 |  |  | 10 | 10 | 41 | 277304 | 60060946 | 116884
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Hawkes Bay) | SH5 Hawkes Bay RB to SH2 | Pre-implementation* | SH5 Hawkes Bay RB to SH2 | HML | VHHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow required between current and future FY's to align with NLTP variation | 0 | 0 |  |  | 10 | 10 | 15 | 277286 | 60060909 | 116882
2022-03-03 | March 2022 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Manawatu/Whanganui) | Accessing Central New Zealand SH3 Napier Road | Detailed Business Case | SH3 (Napier Road) | VHMVH | VHMVH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 10.2 | 10.2 | 60043511 | 241289 | 60043511 | 116534
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | SH3 Whanganui to Bulls | Pre-implementation* | SH3 Whanganui to Bulls | VHMVH | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Casflow adjustment required between future FY's to align with NLTP Variation | 0 | 0 |  |  | 10 | 10 | 10835 | 277365 | 60061089 | 116885
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Marlborough) | SH1 SH62 Spring Creek Intersection RAB | Implementation | SH Improvements | MHM | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | remaining pavement works to be undertaken during NOC work has been postponed to next construction season.Cashflow $141k to 22/23 | 0 | 0 |  |  | 1.5 | 1.5 | SAP Item 60217472 | 280096 | 60217472 | 116821
2022-03-12 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Nelson - SH6/SH62 | Property | R2Z | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc to 311 | 0 | 0 |  |  | 0 | 1.6 |  | 278556 |  | 116853
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Taranaki) | SH3/3A New Plymouth to Hawera | Pre-implementation* | SH3/3A New Plymouth to Hawera | HHVH | VHHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow ajustment between current and fututre FY's to align with NLTP variation | 0 | 0 |  |  | 10 | 10 | 7 | 277292 | 60060921 | 116883
2022-03-21 | March 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Waikato) | NZUP SH1-29 Intersection Improvements | Construction | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cash flow $100,000 from CY to Y2 - No construction start this year. | 0 | 0 |  |  | 2.5 | 2.5 | 60213469 | 240049 | 60213469 | 116797
2022-03-21 | March 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Waikato) | NZUP SH1-29 Intersection Improvements | Pre-implementation* | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cash flow $185,723 from Y2 to CY - more spend due to dealing with unwilling owner preparing for hearings and change to Direct Referral | -2 | -2 |  |  | 2.5 | 2.5 | 60213468 | 240048 | 60213468 | 116796
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 (Cambridge to Piarere) Long Term Improvements | Detailed Business Case | Detailed Business Case - Long-term efficiency | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cash flow $90,000 from CY to Y1 - delays with iwi engagement | -1 | -1 |  |  | 0 | 0.9 | Detailed Business Case - Long-term efficiency | 271020 | 60038160 | 116791
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 (Cambridge to Piarere) Long Term Improvements | Pre-implementation* | Pre-Implementation | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cash flow $1,765,807 from CY to Y2 - Delays with land access and covid for specialist surveys and geotech | -1 | -1 |  |  | 0 | 0.9 | 60044805 | 270103 | 60044805 | 116792
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 (Cambridge to Piarere) ST Improvements, NSRRP | Implementation | NLTF-SH Improvements | H_M | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 1.2 | 1.2 | 60218171 | 278784 | 60218171 | 116822
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 South-East Hamilton Improvements | Construction | SH1 Cobham/Cambridge Improvements Construction | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | reforecast | 0 | 0 |  |  | 5.9 | 5.9 | 60033606 | 239051 | 60033606 | 116775
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Tokoroa to Taupo Safer Corridor | Implementation | R2Z | H_L | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflowing of $14,137,685 from current FY to Y1 as per CY Fcast | 0 | 0 |  |  | 0 | 1.6 |  | 278486 | 60062207 | 116804
2022-03-21 | March 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Wex Rangiriri Section | Construction | Stage 1 | H_L | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cash flow $8,653,793 from CY to Y1 - Final surfacing deferred to next FY and property not yet acquired for Stone access construction | -3 | -3 |  |  | 1.4 | 1.8 | 60212488 | 173312 | 60212488 | 116795
2022-03-21 | March 2022 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Waikato) | SH3 (SH37 to Te Kuiti) , NSRRP | Implementation | SH3 (SH37 to Te Kuiti) , NSRRP | H_H | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 1.6 | 1.6 | 60028039 | 231702 | 60028039 | 116827
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton (corridor improvements) | Implementation | R2Z | VHMM | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | PLA of $1,828,460 to complete construction phase | 1 | 1 |  |  | 0 | 1.6 | SNP-SSI | 278436 | 60056536 | 116777
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Ngaumutawa Intersection | Implementation |  | VHHL | MHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow into future years | 0 | 0 |  |  | 0 | 1.6 |  | 269964 | 60056825 | 116778
2022-03-21 | March 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Norfolk Rd Roundabout | Implementation |  | VHHL | HHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow into future years. | 0 | 0 |  |  | 0 | 1.6 |  | 278534 | 60062285 | 116767
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -133297 | -67981 | [5 empty] | 272820 |  | 116802
2022-03-16 | March 2022 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZ Transport Agency | Road Safety Promotion 2021-24 - Alcohol Interlock | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase detail updated. | 0 | 0 |  |  |  |  | see below | 278433 |  | 116903
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -196229 | -100077 | [5 empty] | 272818 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | 1051885 | 536461 | [5 empty] | 272833 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -351225 | -179125 | [5 empty] | 272831 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -43719 | -22297 | [5 empty] | 272834 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -125404 | -63956 | [5 empty] | 272821 |  | 116802
2022-03-22 | March 2022 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflows to realign difference between requested funding and approved funding, to match work programmes | -172959 | -88209 | [5 empty] | 272837 |  | 116802
2022-03-13 | March 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Otago) | Wakatipu Walking/Cycling Network Improvements | Property | NZTA Package | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc | -1340423 | -1340423 |  |  | 2.6 | 2.6 |  | 257751 |  | 116857
2022-03-03 | March 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Wellington City Council | Wellington Cycle Network - Eastern Package | Pre-implementation* | Evans Bay Parade Stage 2 (NIWA - Cobham) | VHHL | VHHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The project has proved more complex than initially anticipated, which increased the cost of producing the concept designs, and will have follow-on implications for detailed design. | 900000 | 458999 |  |  | 0 | 2.5 | Evan Bay Parade Stage 2 (NIWA - Cobham) | 269571 |  | 115905
2022-03-18 | March 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Christchurch City Council | EW - Banks Peninsula Storm/Flood Damage 29-31 May 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -362566 | -184909 |  |  |  |  | Response and Reinstatement | 278072 |  | 116828
2022-03-29 | March 2022 Review | Cost Increase | Local road maintenance | Emergency works | Far North District Council | EW September/October 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | September & October 2021 FNDC Storm Report updated to include slip on Fairburn Road RP9668. | 660001 | 455400 |  |  |  |  | EW September/October 2021 | 280429 |  | 117005
2022-03-03 | March 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (BOP) | BOPE EW Heavy Rain Event 28-29 April 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close surplus $57,586 | -62194 | -62194 |  |  |  |  | Phase 1 & 2 | 264636 | 60049906 | 116756
2022-03-21 | March 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Otago) | EW SH6 Kawarua Gorge Underslip 20210823 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close Surplus $29,143 | -31475 | -31475 | [5 empty] | 279778 | 60065047 | 116790
2022-03-03 | March 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Otago) | EW SH6 Makarora Storm 20210629 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close Surplus $187K | -202011 | -202011 | [5 empty] | 278943 | 60063178 | 116755
2022-03-18 | March 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Taranaki) | MWT June 2015 Rain Taranaki | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close Surplus | -52013 | -52013 |  |  |  |  | 60035926 | 243748 | 60035926 | 116809
2022-03-03 | March 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Waikato) | EW Coromandel Storm 20200716 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -35429 | -35429 | [5 empty] | 270846 | 60058351 | 116642
2022-03-21 | March 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast, Otira & Westland 20181108 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close Surplus $2,511,357 | -2712266 | -2712266 |  |  |  |  | 60051990 | 266721 | 60051990 | 116776
2022-03-15 | March 2022 Review | Cost Increase | Local road maintenance | Emergency works | Tararua District Council | Event November 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | This is new approval | 1471519 | 1030064 |  |  |  |  | Event November 2020 (2) | 275564 |  | 116746
2022-03-03 | March 2022 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | DOC (Hawkes Bay) | Low cost / low risk improvements 2021-24 | Local road improvements (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Shifting funding to Otago programme. | -20000 | -10200 | [5 empty] | 276059 |  | 116729
2022-03-03 | March 2022 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | DOC (Northland) | Low cost / low risk improvements 2021-24 | Local road improvements (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reducing LCLR provision to shift funding to Otago LCLR. | -50000 | -25500 | [5 empty] | 276073 |  | 116727
2022-03-04 | March 2022 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | DOC (Otago) | Low cost / low risk improvements 2021-24 | Local road improvements (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Shifting funding from DOC programmes Northland ($50k), Taranaki ($50k) and Hawke's Bay ($20k), and bringing forward existing Otago LCLR provision to 2021/22 to fund realignment of Dart Road at Chinamans Bluff. | 120000 | 61200 | [5 empty] | 276078 |  | 116726
2022-03-03 | March 2022 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | DOC (Taranaki) | Low cost / low risk improvements 2021-24 | Road to Zero (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Shifting funding to Otago programme. | -50000 | -50000 | [5 empty] | 276090 |  | 116728
2022-03-18 | March 2022 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Manawatu District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Recommended as per regional office. | 0 | 2880 | [5 empty] | 276218 |  | 116686
2022-03-17 | March 2022 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Rangitikei District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Recommended to enable works programme to be completed in 22/23 yr instead of 21/22 | 0 | -25834 | [5 empty] | 276367 |  | 116722
2022-03-09 | March 2022 Review | Cost Increase | State highway maintenance | Network and asset management | NZTA (Waikato) | Maintenance, Operations and Renewals Programme 2021-24 - AC 9 | State Highways |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Chief Financial Officer approve funding to Waka Kotahi NZ Transport Agency for Rebuild of Waikato Regional Transport Model (WRTM) NEW with total project costs of $1,323,692 at a FAR of 100%. This funding is comprised of $1,090,832 from the Investment Management activity class (AC1, WC002) and $232,860 from the State Highway Maintenance Activity class (AC9, WC151). | 232860 | 232860 | [5 empty] | 273205 |  | 116813
2022-03-11 | March 2022 Review | Cost Decrease | Local road improvements | New roads | Auckland Transport | Matakana Link Road | Implementation | Matakana Link Road - IMP | HHH | MHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Partial surplus of funds. | -7613437 | -7613437 |  |  | 0 | 7.7 | 323.2489 | 248909 |  | 116829
2022-03-11 | March 2022 Review | Cost Increase | Local road improvements | New roads | Auckland Transport | Matakana Link Road â€“ Repayment | Implementation | MLR - Repayment | H_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update to match project surplus | 3730584 | 3730584 |  |  | 0 | 7.7 | 323.2672 | 267243 |  | 116831
2022-03-25 | March 2022 Review | Cost Increase | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Construction | Construction - enabling | H_L | H_L | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 12213275 | 12213275 |  |  | 1.4 | 1.4 | 60216287 | 226528 | 60216287 | 117031
2022-03-03 | March 2022 Review | Cost Decrease | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS 4 Ngauranga to Aotea Quay:Active Traffic Mgt | Construction | Stage 2 and 3 of 4 stages of Construction | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Closed | -7368 | -7368 |  |  | 1.4 | 1.4 | 60216092 | 203531 | 60216092 | 116724
2022-03-10 | March 2022 Review | Cost Increase | Local road improvements | New roads | Tauranga City Council | Western Corridor Growth Management - Tauriko West DBC | Detailed Business Case | Detailed design and business case | VHHL | VHHH | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Rationale for cost increase has been provided and funding availability has been confirmed, and CSA has been endorsed by delegations committee | 278051 | 141806 |  |  | 0 | 1.1 |  | 259256 |  | 116617
2022-03-08 | March 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Property |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updating 2019/20 Actual to match SAP. | 2951437 | 2951437 |  |  | 1.1 | 1.1 | 60464252 | 202324 | 60464252 | 116788
2022-03-08 | March 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Property |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Aligning SAP & TIO. Property phase difference is due to the EOY processing and a subsequent request in TIO which removed funds | 1322466 | 1322466 |  |  | 1.1 | 1.1 | 60464252 | 202324 | 60464252 | 116787
2022-03-18 | March 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Property | Property | H_M | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project close | 295 | 295 |  |  | 1.5 | 1.5 | 60465152 | 212337 | 60465152 | 116823
2022-03-13 | March 2022 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Otago) | Wakatipu Walking/Cycling Network Improvements | Property | NZTA Package 331 | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updating 20/21 year actual after creating new phase for wc331 | 25237 | 25237 |  |  | 2.6 | 2.6 |  | 280902 | 60052907 | 116858
2022-03-25 | March 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Property |  | H_L | H_L | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 2827896 | 2827896 |  |  | 1.4 | 1.4 | 60450642 | 194475 | 60450642 | 117030
2022-03-11 | March 2022 Review | Cost Decrease | Local road improvements | Property purchase (local roads) | Auckland Transport | Matakana Link Road | Property | Matakana Link Road - PROPERTY | HHH | MHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Partial surplus of funds. | -7076989 | -7076989 |  |  | 0 | 7.7 | 332.2492 | 249232 |  | 116830
2022-03-11 | March 2022 Review | Cost Increase | Local road improvements | Property purchase (local roads) | Auckland Transport | Matakana Link Road â€“ Repayment | Property | MLR - Repayment | H_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update to match project surplus | 1213724 | 1213724 |  |  | 0 | 7.7 | 332.2672 | 267244 |  | 116832
2022-03-10 | March 2022 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | DELETE - LGWM CS South West CBD | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Remove 3rd party funding, all funding (including 3rd party) has been moved to phase 280699. | 0 | 1175544 |  |  | 1.2 | 1 |  | 280369 | 60066167 | 116817
2022-03-12 | March 2022 Review | Cost Decrease | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Auckland) | 20Connect (Southern and Eastern Airport Access Imps) | Property | 20Connect (Airport Access Imps) | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing work cat to 331 | -8967500 | -8967500 |  |  | 1.4 | 1 | Property - supporting A2B Route Protection | 275947 |  | 116848
2022-03-25 | March 2022 Review | Cost Increase | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Canterbury) | PT Futures MRT | Indicative Business Case |  | VHLL | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 56870 | 56870 |  |  | 1 | 1 |  | 268114 | 60054249 | 117043
2022-03-03 | March 2022 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Pre-implementation* | SH26 Onetai Stream Bridge Replacement | H_PV_EoL | MMH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move the remaining funds of $26,653 from ID 60059216 to 60052984 to be able to close out the SSBC phase. | 28785 | 28785 |  |  | 0 | 0 |  | 231693 | 60052984 | 116627
2022-03-03 | March 2022 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Single-Stage Business Case | SH26 Onetai Stream Bridge Replacement | H_PV_EoL | MMH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move the remaining funds of $26,653 from ID 60059216 to 60052984 to be able to close out the SSBC phase. | -28786 | -28786 |  |  | 0 | 0 |  | 233000 | 60059216 | 116628
2022-03-21 | March 2022 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (West Coast) | SH6 Taramakau Road Bridge | Implementation | NLTF-SH Improvements | H_M | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -47080 | -47080 |  |  | 1.9 | 1.9 | 60033092 | 278802 | 60033092 | 116770
2022-03-03 | March 2022 Review | Cost Decrease | Local road improvements | Resilience improvements | Auckland Transport | Resilience Imp - Quay Street Seawall Seismic Upgrade | Implementation |  | H_L | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Dec21 programme monitor, this project is substantively complete, with a few minor defects to be resolved and final costs to be confirmed. At this time a partial surplus is being declared. | -6025151 | -4548989 |  |  |  |  | 357.2386 | 238612 |  | 116733
2022-03-21 | March 2022 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Otago) | Katiki Coast Enhanced Resilience Stage 2 | Implementation |  | M_L | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project is practically complete, returning $823,392 surplus | -889263 | -889263 |  |  |  |  | 60047602 | 255756 | 60047602 | 116825
2022-03-18 | March 2022 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | AKL Network Optimisation | Single-Stage Business Case | Auckland Network Optimisation - SSBC | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This SSBC has now been completed and endorsed / supported by the Waka Kotahi Board, so declaring the minor balance surplus. | -481713 | -245674 |  |  |  | 3.2 | 324.2692 | 269231 |  | 116843
2022-03-10 | March 2022 Review | Cost Increase | Local road improvements | Road improvements | Christchurch City Council | Northern Arterial Extension and Cranford Street Upgrade | Implementation | CNC Downstream Effects Projects | H_L | H_M | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Completion of NAE consent requirements - 21/22 Costs part of front loaded payback | 8952900 | 626703 |  |  | 2.3 | 2.3 |  | 268853 |  | 113581
2022-03-21 | March 2022 Review | Cost Increase | Local road improvements | Road improvements | NZ Transport Agency | Safe Network Programme 2018-21 NLTP | Pre-implementation* | SNP-Programme Management (Local Roads) | HHL | VHHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update past years to reflect spend. NB Total within approved funding. | 7126036 | 7126036 |  |  | 0 | 1.6 | 60052632/80002478 | 267001 |  | 116951
2022-03-21 | March 2022 Review | Cost Increase | State highway improvements | Road improvements | NZ Transport Agency | Safe Network Programme 2018-21 NLTP | Pre-implementation* | SNP-Programme Management (State Highways) | HHL | VHHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update to reflect actual spend and the correct SH Improvements shar of approved funding. | 418448 | 418448 |  |  | 0 | 1.6 |  | 280959 |  | 116964
2022-03-21 | March 2022 Review | Cost Decrease | Local road improvements | Road improvements | NZ Transport Agency | Safe Network Programme 2018-21 NLTP | Pre-implementation* | SNP-Programme Management (Local Roads) | HHL | VHHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct year 1 actual spend. | -343978 | -343978 |  |  | 0 | 1.6 | 60052632/80002478 | 267001 |  | 116965
2022-03-03 | March 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZ Transport Agency | Safe Vehicles Programme 21-24 | Single-Stage Business Case | Safe Vehicles Programme SSBC | MHVH | MHVH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -6105000 | -6105000 |  |  | 17 | 17 | Completed 2021 | 277396 |  | 116748
2022-03-12 | March 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Auckland) | SH1 Dome Valley Safety Improvements | Property |  | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | New phase to correct wc324 to 331 | -274889 | -274889 |  |  | 0 | 1 |  | 278476 |  | 116847
2022-03-12 | March 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (BOP) | W2T Waihi to Omokoroa (Safer Corridor) | Property |  | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc to 311 | -2077636 | -2077636 |  |  | 0 | 1 |  | 278526 |  | 116850
2022-03-18 | March 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Construction | 60034104 Construction SP3 | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close , returning surplus | -60430 | -60430 |  |  | 1.5 | 1.5 | 60034104 | 213901 | 60034104 | 116824
2022-03-21 | March 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Ashley to Belfast - (SH71 to Tram Rd) | Implementation |  | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Returning surplus to programme for the phase $616,828 | -666176 | -666176 |  |  | 0 | 1.6 |  | 278552 | 60062296 | 116819
2022-03-18 | March 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Gisborne) | SH35 and connecting routes: Resilience | Implementation | PGF | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer - Pre-implementation costs have been higher than initially estimated. Please transfer $1,573,128 from Implementation phase to Pre-imp phase to match forecast | -1573129 | -1573129 |  |  | 1 | 1 |  | 267791 | 60051600 | 116807
2022-03-18 | March 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Gisborne) | SH35 and connecting routes: Resilience | Pre-implementation* | PGF | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer - Pre-implementation costs have been higher than initially estimated. Please transfer $1,573,128 from Implementation phase to Pre-imp phase to match forecast. | 1573123 | 1573123 |  |  | 1 | 1 |  | 264778 | 60051589 | 116806
2022-03-18 | March 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Hawkes Bay) | SH2 Inter-Reg connections: Passing Opps | Implementation | PGF | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interp transfer - Pre-implementation costs have been higher than initially estimated. Please transfer $618,059 from Implementation phase to Pre-imp phase to match forecast | -618057 | -618057 |  |  | 1 | 0.8 | Implementation | 264871 | 60052056 | 116808
2022-03-18 | March 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Hawkes Bay) | SH2 Inter-Reg connections: Passing Opps | Pre-implementation* | PGF | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer - Pre-implementation costs have been higher than initially estimated. Please transfer $618,059 from Implementation phase to Pre-imp phase to match forecast. | 618059 | 618059 |  |  | 1 | 0.8 | Pre-implementation | 264870 | 60052060 | 116812
2022-03-23 | March 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Otago) | SH6 SH8B SH8 Gibbston to Clyde Corridor Imps | Pre-implementation* | NLTF-SH Improvements | VHML | MML | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funds from SH improvements to W&C to match SAP | -41255 | -41255 |  |  | 9.7 | 0.4 | 60056371 | 254549 |  | 116982
2022-03-13 | March 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Taranaki) | SH3/3A Waitara to Bell Block | Property | NZTA-R2Z | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc to 331 | -6914867 | -6914867 |  |  | 1.1 | 1.1 |  | 278529 |  | 116863
2022-03-25 | March 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Waikato) | SH1 ETA Corridor Improvements | Implementation | NZTA-R2Z | VHML | VHML | N | 3 | Approved | Approved by Chief Financial Officer (CFO) |  | 3202000 | 3202000 |  |  | 2.6 | 2.6 |  | 278477 | 60062184 | 115671
2022-03-13 | March 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Waikato) | SH27 Mangawhero Bridge | Property | property | HML | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc to 331 | -32183 | -32183 |  |  | 2.1 | 2.1 |  | 278480 |  | 116861
2022-03-31 | March 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Waikato) | SH29 Piarere to SH28 | Pre-implementation* | SH29 Piarere to SH28 | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow adjustment required between future FY's to align with NLTP variation | 91000 | 91000 |  |  | 10 | 10 | 38 | 277244 | 60060852 | 116886
2022-03-31 | March 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Waikato) | SH5 Tirau to Tarukenga Marae Rd | Pre-implementation* | SH5 Tirau to Tarukenga Marae Rd | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow adjustment required between current and future FY's to align with NLTP variation | 101100 | 101100 |  |  | 10 | 10 | 35 | 277261 | 60060886 | 116887
2022-03-04 | March 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton (corridor improvements) | Implementation | R2Z | VHMM | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1974735 | 1974735 |  |  | 0 | 1.6 | SNP-SSI | 278436 | 60056536 | 116762
2022-03-04 | March 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Ngaumutawa Intersection | Implementation |  | VHHL | MHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 946676 | 946676 |  |  | 0 | 1.6 |  | 269964 | 60056825 | 116763
2022-03-04 | March 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Norfolk Rd Roundabout | Implementation |  | VHHL | HHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 981703 | 981703 |  |  | 0 | 1.6 |  | 278534 | 60062285 | 116764
2022-03-13 | March 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Wellington) | SH58 Safety Improvements | Property |  | VHHL | HML | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fixing wc to 331 | -1054442 | -1054442 |  |  | 1.3 | 1.3 |  | 279257 |  | 116860
2022-03-30 | March 2022 Review | Cost Decrease | Investment management (incl. Transport Planning) | Transport model development | NZTA (Canterbury) | Christchurch Transport Modelling Suite update | Programme business case |  | H__ | H__ | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | surplus funds due to project closure | -60341 | -60341 | [5 empty] | 266507 | 60053093 | 117125
2022-03-03 | March 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | Auckland Transport | Safer Communities - Mangere Bridge | Implementation | SC - Mangere Bridge - IMP | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Dec21 programme monitor, this activity has been complete. AT are just awaiting final minor costs to be advised and then the project will be closed completely. In the meantime, a surplus is being declared. | -599982 | -305991 |  |  | 0 | 1.4 | 451.2647 | 264650 |  | 116731
2022-03-03 | March 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | Auckland Transport | Safer Communities - Mt Roskill | Implementation | SC - Mt Roskill - IMP | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the Dec21 programme monitor, this activity has indicated that it will come in under-budget. A partial surplus is being declared at this time until final costs have been confirmed. | -1318714 | -672544 |  |  | 0 | 1.8 | 451.2608 | 260797 |  | 116732