## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2022-06-28 | June 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Great North Road Cycleway | Implementation | UCP - Wst Connx - Great North Road | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The reason for change and justification for the recommendation above are this project is: Providing better travel options through its positive impact on access to opportunities as it creates improved cycling links, walking access, public transport access and efficiency to and from the city centre on links which form part of Aucklandâ€™s cycleway network; Increasing the number of cyclists through the construction of cycling infrastructure that is safe and convenient; Improving the perceived and actual safety risks for cyclists through the construction of a safer separated cycle route; and Increasing the delivery of the Auckland Cycle Network through the implementation of a route within an agreed cycling strategic network to improve access and provide greater transport choice. | 25868864 | 13193121 |  |  |  | 2.6 | 452.2777 | 277747 |  | 117862
2022-06-13 | June 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Wellington City Council | WCC Cycleways - Transformational Programme | Single-Stage Business Case | Brooklyn Hill Improvements SSBC | HHL | VHHM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This change is in response to correcting a TIO error where this phase should have been set up under activity 155342. This activity/phase 155342/281661 is replacing this activity. THIS IS A REPLACEMENT TO AN ACTIVITY APPROVED EARLIER BY CFO. | 498000 | 253980 |  |  |  | 3.5 | Brooklyn Hill Improvements SSBC | 281661 |  | 117942
2022-06-10 | June 2022 Review | New approval | Local road maintenance | Emergency works | Buller District Council | EW Buller District Flood Event - February 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Refer to approved report in Supporting Documents | 222500 | 222500 |  |  |  |  | Buller Feb 2022 Flood Event WC141 reinstatement - SPR | 281020 |  | 117304
2022-06-10 | June 2022 Review | New approval | Local road maintenance | Emergency works | Buller District Council | EW Buller District Flood Event - February 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Refer to approved report in Supporting Documents | 1277500 | 1175300 |  |  |  |  | Buller Feb 2022 Flood Event WC141 reinstatement - Local Roads | 281019 |  | 117303
2022-06-02 | June 2022 Review | New approval | Local road maintenance | Emergency works | Central Hawkes Bay District Council | EW CHBDC 20220602 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Funding investment under WC141 required to complete initial response and reinstatement works to prior LOS, on affected local roads | 2868441 | 2323437 |  |  |  |  | construction | 281058 |  | 117264
2022-06-29 | June 2022 Review | New approval | Local road maintenance | Emergency works | Hastings District Council | EW 24-25 March 2022 Significant storm event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Emergency works funding required to reinstate LOS on Local Roads | 1166815 | 630080 |  |  |  |  | Cleanup and recovery | 281212 |  | 117288
2022-06-16 | June 2022 Review | New approval | Local road maintenance | Emergency works | Hurunui District Council | EW Ex Cyclone Dovi, 12-15 February 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Recommendation That the Regional Manager - Maintenance and Operations: Approves Hurunui District Councilâ€™s Emergency Works request at a total cost of $675,100. The total net NLTF Share for this event is $486,072. | 675100 | 486072 | [5 empty] | 281283 |  | 117286
2022-06-17 | June 2022 Review | New approval | Local road maintenance | Emergency works | Masterton District Council | Emergency Works Feb 2022 Cyclone Dovi | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | That Regional Manager, Wellington & Top of the South, Transport Services Approves $839,602 ($485,469 NLTF) at a transitional FAR 57.82% repair of the Masterton District network after Cyclone Dovi. Notes that this approval does not trigger enhanced FAR. However, the approval does not include one repair site at on Homewood Road which required more detailed investigation of options. If included the Homewood Road site may trigger the enhanced FAR in future. | 839602 | 485469 |  |  |  |  | 3116305 | 280827 |  | 116765
2022-06-09 | June 2022 Review | New approval | Local road maintenance | Emergency works | Masterton District Council | Emergency Works Kerosene Ridge Feb 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | That Regional Manager, Wellington & Top of the South, Transport Services Approves $899,452 ($513,688 NLTF) at a transitional FAR 57.11% repair of Masterton District Council Kerosene Ridge slip site damaged in heavy storm event. | 899452 | 513688 |  |  |  |  | 3116305 | 280828 |  | 116758
2022-06-01 | June 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (West Coast) | EW SH67 Reefton HR 20220202 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | All of the works detailed in the report and the schedule have resulted from the heavy rain event and certainly need to be addressed. Funding approval for most of these is recommended as part of this first application, however a few of the higher value jobs are not well supported by robust design/ Geotech reports and/or detailed enough estimates to be certain the solutions are optimal and the costs are reasonable. I recommend the funding for these ones be held back until additional detail is provided. The initial application for $6.15M has therefore been reduced to $3.28M | 3544005 | 3544005 | [5 empty] | 280720 | 60066794 | 117248
2022-06-20 | June 2022 Review | New approval | Local road maintenance | Emergency works | Porirua City Council | Emergency Works - December 2021 - Heavy Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | That the Senior Manager System Management: APPROVE $1,791,125 emergency works funding for Porirua District Council for the Heavy Rain Event December 2021. | 554502 | 304976 |  |  |  |  | Construction Proposal | 280415 |  | 116845
2022-06-08 | June 2022 Review | New approval | Local road maintenance | Emergency works | South Taranaki District Council | August 21 flood event | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | Recommended by regional office | 129073 | 81316 |  |  |  |  | Clean up and reinstatement of flood damage roads | 280376 |  | 116148
2022-06-09 | June 2022 Review | New approval | Local road maintenance | Emergency works | South Taranaki District Council | EW October 21 flood event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Approved by Acting Manager National Maintenance and Ops, Rob Campbell. He is not on list so used SMSM(TS) | 108355 | 68264 |  |  |  |  | Clean up and reinstatement of flood damage roads | 280375 |  | 116149
2022-06-08 | June 2022 Review | New approval | Local road maintenance | Emergency works | South Taranaki District Council | Flood Damage Feb 22 - Waitangi and Dovi | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | As recommended by Regional Office | 937540 | 590650 |  |  |  |  | construction | 280858 |  | 116782
2022-06-17 | June 2022 Review | New approval | Local road maintenance | Emergency works | South Wairarapa District Council | Cape Palliser Rd Swell Damage May 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | x | 358354 | 358354 |  |  |  |  | initial response and reinstate rock revetments | 281619 |  | 117841
2022-06-30 | June 2022 Review | New approval | Local road maintenance | Emergency works | Wellington City Council | Emergency Works Cyclone Dovi Storm Event February 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | That the Regional Manager Wellington/Top of the South, Transport Services: Approves $982,739 for Wellington City Council Emergency Works Cyclone Dovi Storm Event February 2022 at a FAR of 56.86% (NLTF $558,745). | 982739 | 558745 |  |  |  |  | Cyclone Dovi - Storm Event Feb. 22 | 281718 |  | 118062
2022-06-30 | June 2022 Review | New approval | Local road maintenance | Emergency works | Whanganui District Council | December 2021 Emergency Works - Whanganui District | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | As recommended by Regional Office | 1172383 | 715154 |  |  |  |  | Request for emergency works funding | 281211 |  | 117244
2022-06-09 | June 2022 Review | New approval | Local road maintenance | Emergency works | Whangarei District Council | EW - Whangarei District - March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | refer to NZTA report in supporting docs. | 1179313 | 625036 | [5 empty] | 281439 |  | 117564
2022-06-22 | June 2022 Review | New approval | Local road improvements | New roads | Hamilton City Council | Ruakura - Eastern Transport Corridor | Detailed Business Case | Business Case | HHL | MHM | N | 5 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | This project primarily enables a shift of freight from road to rail. It also looks to provide a mode neutral transport network that gives residents a choice of transport modes including cycling and walking resulting in a community well-connected to employment opportunities at Ruakura in addition to the Hamilton area | 500000 | 255000 | The strategic case is endorsed by the Regional Manager System Design (Waikato, Bay of Plenty) before the business case proceeds to the economic, financial, commercial and management cases |  |  |  |  | 276918 |  | 117582
2022-06-23 | June 2022 Review | New approval | Public transport services | Passenger services - bus | Environment Canterbury | PT Futures enhanced frequency | Implementation |  | VHML | VHHVH | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | Part of PT Futures Package of Work | 5785498 | 2950604 |  |  | 1.7 | 1 | implementation | 278078 |  | 117266
2022-06-23 | June 2022 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | Auckland Transport | Electric Vehicle Uptake PBC | Programme business case |  | VHHL | HML | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | See PoE | 430199 | 219401 |  |  |  |  | 4.2811 | 281120 |  | 117422
2022-06-13 | June 2022 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | New Plymouth District Council | NPDC Integrated Transportation Strategic Plan | Programme business case |  | HHM | VHHVH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Recommend that the Chief Financial Officer approve funding for the Integrated Transport Strategic (ITS) Plan 2021 - 2051 Programme Business Case with a total cost of $490,000 and NLTF share of $249,900 at a FAR of 51% from the Investment Management activity class and work category Transport Planning WC004 | 490000 | 249900 | [5 empty] | 279812 |  | 117802
2022-06-22 | June 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Canterbury) | SH1 Ashley to Belfast - (William St to Saltwater Creek) | Property | SH1 Ashley to Belfast Saltwater-William | HHL | HHH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This application is for the property phase of the project (which is currently progressing through the pre-implementation phase) to enable both the engagement of the property consultant and the purchase of land necessary for this project. The property phase amount may differ if the engagement requires total purchase of the property at Woodend Rd due to effect on the property. Under the PWA a property owner can require us to purchase the whole of their property if they consider the effects on the property are significant. The P95 cost has been estimated to include the cost of this property. A PLA will be submitted if required to cover this additional cost. The expected property cost (P50) is $1.465m. The P95 property cost if $2.2m (this includes an estimate for the full cost of the property at Woodend Road, if required). These property requirements were expected and appear to be in line with the originally approved funding application. Implementation funding is included as a Probable activity in the 21-24 NLTP and the activity outcomes continue to be aligned with GPS priorities. Engagement with property owners at this pre-implementation stage is consistent with the risk treatment of early engagement proposed in the original SSI Funding Application. No previous funding conditions are evident in TIO. These expected property costs should be approved so that this activity can continue as previously approved. | 1545868 | 1545868 |  |  | 0 | 1.6 |  | 278316 | 60060542 | 117650
2022-06-30 | June 2022 Review | New approval | Public transport services | Public transport operations and management | Greater Wellington | Wellington Regional Hospital TDM Initative | Implementation | Implementation | VHLM | HMM | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | Implementation of agreed TDM measures | 3861000 | 839460 | Subject to condition subsequent that an MOU is in place between Capital Coast District Health Board and Greater Wellington Regional Council |  | 3.5 | 3.5 | WBS | 269717 |  | 118333
2022-06-16 | June 2022 Review | New approval | Coastal shipping | Sea freight operations | NZ Transport Agency | Coastal Shipping - 2021-24 | Implementation | Coastal Shipping - OPEX | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 32540000 | 32540000 |  |  | 1 | 1 | 60067633 | 280818 |  | 118088
2022-06-22 | June 2022 Review | New approval | Investment management (incl. Transport Planning) | Transport model development | Whangarei District Council | Whangarei District Transportation Model Update | Programme business case |  | V__ | H__ | N |  | Approved | Approved by Chief Financial Officer (CFO) | This will enable delivery of more public transport and walking & cycling projects in Whangarei by enhancing the evidence base for investment in these modes. The update will also provide more confidence for investment decisions due to improvements in the quality and relevance of data used for planning and investigation. | 150000 | 79500 | [5 empty] | 277662 |  | 117306
2022-06-28 | June 2022 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Activity management planning improvement | Horizons Manawatu | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow change to account for effort this FY to complete review of RPTP | 0 | 0 |  |  |  |  | Regional Activity Management Planning MNWI | 275955 |  | 118143
2022-06-17 | June 2022 Review | Cash flow adjustment | Debt Funding | Advance property purchase | Hamilton City Council | 2018 Southern Links Peacocke Arterials HIF | Property | North - South Arterial Land | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow adjustment | 0 | 0 |  |  | 2.4 | 2.4 | 3200.2, 3200.3, 3200.4, 3200.5 | 262016 |  | 118043
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 58406 | 29787 | [5 empty] | 274717 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Cycle path maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | 1 | [5 empty] | 274704 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Cycle path renewal | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | 0 | [5 empty] | 274720 |  | 117943
2022-06-08 | June 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Hawkes Bay) | Prebensen Hyderabad Intersection upgrade | Implementation | Construction (Walking & Cycling) | M_H | MHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Pleaae move $856,747 from 2022 to 2023 | -2 | -2 |  |  | 14.6 | 14.6 |  | 270062 | 60056702 | 117807
2022-06-14 | June 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Waikato) | SH1 Hamilton to Cambridge Cycle Connection - Section 1 | Implementation |  | HHM | HHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow Request as Landscape Maintenance cost that was forecasted amount for 2023 till 2025 is less than the actual quote received from the contractor. | -4 | -4 |  |  | 0 | 3.3 | 60048487 | 254736 | 60048487 | 117959
2022-06-08 | June 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | Petone to Melling Walking Cycling Link | Implementation | Implementation - NLTF | HHVL | HHL | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please make a cashflow adjustment to reallocate $3,588,547 into the next financial year. | 0 | 0 |  |  | 0 | 2.5 | 60045916 | 250462 | 60045916 | 117854
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | 0 | [5 empty] | 274714 |  | 117943
2022-06-20 | June 2022 Review | Cash flow adjustment | Local road maintenance | Emergency works | South Wairarapa District Council | Cape Palliser Rd Swell Damage May 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | That the Regional Manager Wellington/Top of the South, Transport Services: Approves $358,354 ($358,354 NLTF) at a FAR 100% for South Wairarapa District Council Cape Palliser Road Swell Damage May 2022. | 0 | 0 |  |  |  |  | initial response and reinstate rock revetments | 281619 |  | 118184
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | -221343 | -112884 | [5 empty] | 274707 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Environmental renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 624 | 318 | [5 empty] | 274718 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Footpath maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | 0 | [5 empty] | 274705 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Footpath renewal | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 41532 | 21180 | [5 empty] | 274721 |  | 117943
2022-06-04 | June 2022 Review | Cash flow adjustment | Walking and cycling improvements | Low cost / low risk improvements | Far North District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | SH11 Footpath costs exceeded the amount carryforward from 2020/2021. Program Monitor captured this amendment and cashflow adjustment now completed to bring back $116k from 2022/2023 to cover this spend in 2021/2022. | 0 | 0 | [5 empty] | 276126 |  | 117786
2022-06-15 | June 2022 Review | Cash flow adjustment | Road to Zero | Low cost / low risk improvements | NZTA (Gisborne) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 0 | 0 | [5 empty] | 276257 | 60061857 | 118073
2022-06-15 | June 2022 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Manawatu/Whanganui) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1 | -1 |  |  |  |  | 60061773 | 276266 | 60061773 | 118079
2022-06-15 | June 2022 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Tasman) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 0 | 0 | [5 empty] | 276291 | 60061873 | 118104
2022-06-15 | June 2022 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (West Coast) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1 | -1 | [5 empty] | 276304 | 60061880 | 118113
2022-06-21 | June 2022 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Investment in the Funding Allocation System (IFAS) | Implementation | 2021-24 NLTP 3 year programme | HHVH | HHVH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funds between years | 0 | 0 |  |  | 1 | 1 |  | 278317 |  | 118189
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Minor events | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | 0 | [5 empty] | 274706 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | -17675 | -9014 | [5 empty] | 274711 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Network operations | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | 0 | [5 empty] | 274709 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | -100000 | -51000 | [5 empty] | 274708 |  | 117943
2022-06-29 | June 2022 Review | Cash flow adjustment | State highway improvements | New activities influencing users of the transport system | NZTA (Wellington) | LGWM Managing Travel Demand | Detailed Business Case |  | VHMM | VHMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | covid delays and related impacts very minor adjustment $1k 2023 | -1 | -1 |  |  | 1.2 | 1 |  | 280236 | 60066113 | 118163
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | New activities influencing users of the transport system | NZTA (Wellington) | LGWM Managing Travel Demand | Detailed Business Case |  | VHMM | VHMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Covid delay | 0 | 0 |  |  | 1.2 | 1 |  | 280236 | 60066113 | 117948
2022-06-17 | June 2022 Review | Cash flow adjustment | Debt Funding | New roads | Hamilton City Council | 2018 Southern Links Peacocke Arterials HIF | Implementation | All Peacocke HIF arterials implementation | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow adjustment between 21/22 and 22/23 | 0 | 0 |  |  | 2.4 | 2.4 | Design, Consents and Construction | 262020 |  | 118042
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Auckland) | Hobsonville Deviation | Construction |  | M_M | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Defect liability | 0 | 0 |  |  | 0 |  | 60201428 | 180375 | 60201428 | 117877
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Auckland) | Puhoi to Wellsford RoNS Development | Investigation |  | M_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Planning appeals taking longer to resolve than anticipated | -3 | -3 |  |  | 1.1 | 1.1 | 60216905 | 202323 | 60216905 | 117836
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Auckland) | SH1 Additional Waitemata Harbour Connections | Investigation |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow adjustment | -1 | -1 |  |  | 0.6 | 0.6 | 60210952 | 194476 | 60210952 | 117855
2022-06-07 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (BOP) | Hairini Link - Stage 4 | Construction | Construction | H_L | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow adjustments due to covid delays in delivery | -2 | -2 |  |  | 2.1 | 2.5 | 60217219 | 194905 | 60217219 | 117871
2022-06-07 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Canterbury) | CHCH Southern Motorway HJR to Rolleston (Stage 2 & 3) | Construction | Implementation | H_M | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflowing $3,522,272 to nxt FY for completion of project. | -5 | -5 |  |  | 2.4 | 1.5 | 60215381 | 200236 | 60215381 | 117815
2022-06-07 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Canterbury) | Christchurch RoNS Programme Management | Investigation | Programme Management Costs | H_M | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflowing balance $209,375 to nxt FY | 0 | 0 |  |  | 0 | 0 | 60217567 | 210116 | 60217567 | 117838
2022-06-29 | June 2022 Review | Cash flow adjustment | External funding | New roads | NZTA (Taranaki) | SH3 Mt Messenger Bypass | Detailed Business Case | Detailed Business Case - ARSHP | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0.5 | 0.5 | 60038412 | 270179 | 60038412 | 118238
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Cambridge Section | Construction | . | H_L | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Physical works (pavement repairs & minor civil works circa $288k) planned for CY will now be scheduled for early YR1 due to contractor resource availability | 0 | 0 |  |  | 1.4 | 1.4 | 60203948 | 173265 | 60203948 | 118085
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Huntly Section | Construction | Construction | H_L | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow $291,051 from Y1 to CY - additional costs this FY to complete handover works | -2 | -2 |  |  | 1.8 | 1.8 | 60203871 | 195982 | 60203871 | 117819
2022-06-29 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Long Swamp Section | Construction |  | H_L | MML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Delay in negotiating with landowners on settlement issues | 1 | 1 |  |  | 1.3 | 1.3 |  | 270039 | 60210358 | 118198
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Ngaruawahia Section | Construction |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow $401,189 from CY to Y1 - due to delays to pavement repairs (Impact of COVID) | 45 | 45 |  |  | 0 | 1 | 60202552 | 173253 | 60202552 | 117973
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | New traffic management facilities | NZTA (Waikato) | Waikato SEDF | Implementation | NLTF-SH Improvements | M_H | LHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $1,193,321 to Y1. The Project has been stalled due to iwi negotiations being on hold for the moment. | 0 | 0 |  |  | 12 | 12 | 60217125 | 278781 | 60217125 | 118084
2022-06-08 | June 2022 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Hawkes Bay) | SH5 Napier To Taupo | Programme business case |  | HML | HMM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | it is anticipated that all project allocations will be spent in FY2022/23 | 0 | 0 | [5 empty] | 277810 | 60039010 | 117839
2022-06-08 | June 2022 Review | Cash flow adjustment | External funding | Property purchase (State highways) | NZTA (Auckland) | NZUP Mill Road Corridor | Property | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow $2,113,321 to next year | -3 | -3 |  |  | 1.2 | 1.2 |  | 269743 | 60056118 | 117876
2022-06-16 | June 2022 Review | Cash flow adjustment | External funding | Property purchase (State highways) | NZTA (Auckland) | NZUP Northern Pathway (Westhaven to Akoranga) | Property | NZ Upgrade Programme | VH_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow adjustment | -1 | -1 |  |  | 1.3 | 1.3 |  | 269721 | 60056053 | 117955
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | Northern Corridor Improvements (NCI) | Property | Property acquistion | H_M | H_M | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Carry balance forward to reflect cashflow and progress | -3 | -3 |  |  | 3 | 3 | 60027516 | 227710 | 60027516 | 118049
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Additional Waitemata Harbour Connections | Property |  | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow adjustment | 1 | 1 |  |  | 0.6 | 0.6 | 60429252 | 194477 | 60429252 | 117853
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Warkworth to Wellsford RoNS - Detailed Design and Const | Property |  | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | delayed aquisitions | -3 | -3 |  |  | 1.1 | 1.1 | 60044441 | 197915 | 60044441 | 117840
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH16 Brigham Creek to Waimauku Safety Enhancements | Property |  | HML | HML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Aligning allocations with forecast as per current programme. | -13 | -13 |  |  | 0 | 1.1 |  | 263303 | 60049276 | 117952
2022-06-07 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (BOP) | Hairini Link - Stage 4 | Property |  | H_L | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow adjustments due to covid delays | 0 | 0 |  |  | 2.1 | 2.5 | 60462702 | 194904 | 60462702 | 117875
2022-06-29 | June 2022 Review | Cash flow adjustment | Road to Zero | Property purchase (State highways) | NZTA (Canterbury) | SH1 Ashley to Belfast - (William St to Saltwater Creek) | Property | SH1 Ashley to Belfast Saltwater-William | HHL | HHH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflowing $488,426 to next year as there were delays in funding being approved | 0 | 0 |  |  | 0 | 1.6 |  | 278316 | 60060542 | 118239
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | Prebensen Hyderabad Intersection upgrade | Property |  | M_H | MHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $5,000 from 2022 to 2023, to cover Proprty close out cost in Q1 FY-22/23 | 0 | 0 |  |  | 14.6 | 14.6 | 60452462 | 247468 | 60452462 | 117873
2022-06-29 | June 2022 Review | Cash flow adjustment | External funding | Property purchase (State highways) | NZTA (Hawkes Bay) | SH2 Inter-Reg connections: Passing Opps | Property | PGF | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | alinging SAP & TIO | 7 | 7 |  |  | 1 | 0.8 | Property | 269815 | 60056370 | 118334
2022-06-29 | June 2022 Review | Cash flow adjustment | External funding | Property purchase (State highways) | NZTA (Hawkes Bay) | SH2 Inter-Reg connections: Passing Opps | Property | PGF | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $152,935 from 2022 to 2023, Property acquisition taking longer that originaly expected. | -7 | -7 |  |  | 1 | 0.8 | Property | 269815 | 60056370 | 118244
2022-06-14 | June 2022 Review | Cash flow adjustment | New & improved infrastructure for State highways | Property purchase (State highways) | NZTA (Hawkes Bay) | SH2 Napier Road Intersection | Property | Property | H_M | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0 | 4.5 | 60455442 | 236830 | 60455442 | 117951
2022-06-29 | June 2022 Review | Cash flow adjustment | External funding | Property purchase (State highways) | NZTA (Hawkes Bay) | Waikare Gorge | Property | PGF | H__ | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $225,000 from 2022 to 2023 & $1,957,956 from 2022 to 2024, Properry phase on hold until Implementation phase is fully funded | 0 | 0 |  |  | 0 | 1.3 | Property | 269816 | 60056381 | 118212
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Marlborough) | New ÅŒpaoa River Bridge | Property | Property - NLTF Funding | M_H | MLL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | settlement of Top 10 compensation not achieved in 21/22. Cashflow approx 570k to 22/23 | -2 | -2 |  |  | 0 | 1.4 | 60044433 | 264242 | 60044433 | 117996
2022-06-13 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Northland) | SH1 Loop Road North to Smeatons Hill Safety Improvement | Property | NLTF-SH Improvements | HHL | HHL | N | 5 | Approved | Approved by Auckland Transport Chief Financial Officer | Aligning allocations with forecast. | -1 | -1 |  |  | 0 | 1.2 | 60437382 | 278792 | 60437382 | 117950
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Otago) | Beaumont bridge replacement | Property | Beaumont Bridge Property | H__ | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Minor increase to be reviewed once proerty consulted | -10 | -10 |  |  | 0 | 12 | 60465362 | 214531 | 60465362 | 117789
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Taranaki) | Normanby Overbridge Realignment | Property | 2649 | L_H | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $652,085 from 2022 to 2023, Property owner proving difficult | -2 | -2 |  |  | 4.1 | 4.1 | 60409872 | 194410 | 60409872 | 117872
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Taranaki) | SH3 Vickers Road to City Upgrade | Property | Property 331 | M_H | M_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $54,506 from 2022 to 2023 to cover property close out costs | 0 | 0 |  |  | 0 | 3.7 |  | 270322 | 60460252 | 117874
2022-06-29 | June 2022 Review | Cash flow adjustment | Road to Zero | Property purchase (State highways) | NZTA (Taranaki) | SH3/3A Waitara to Bell Block | Property | R2Z 331 | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $1,567,016 from 2022 to 2023, $380,909 from 2022 to 2024, $1,742,532 from 2023 to 2024, Due to ongoing delays in Property negotiations. | -10 | -10 |  |  | 1.1 | 1.1 |  | 280905 | 60062276 | 118233
2022-06-14 | June 2022 Review | Cash flow adjustment | External funding | Property purchase (State highways) | NZTA (Tasman) | CIP SH60 Motueka Project | Property | CIP SH60 Motueka Project | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashlow 48k from 21/22 to 22/23 | -79 | -79 |  |  | 3.3 | 3.3 | Property Purchase | 271800 | 60059421 | 117904
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | Hamilton Southern Links | Property | Hamilton Southern Links | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Property acquisition delayed by Negotiation and Valuation process | 1 | 1 |  |  | 2 | 2 | 60442432 | 197204 | 60442432 | 117994
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 Wex Cambridge Section | Property |  | H_L | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Property related costs not realised this FY | 0 | 0 |  |  | 1.4 | 1.4 | 60413082 | 194403 | 60413082 | 117816
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 Wex Long Swamp Section | Property | 16837 | H_L | MML | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $181,192 from 2022 to 2023 due to extended negotiation with landowners | -2 | -2 |  |  | 1.3 | 1.3 | 60404372 | 194966 | 60404372 | 117883
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 Wex Rangiriri Section | Property |  | H_L | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow $1,835,532 from CY to Y2, final property acquisition still to be determined and completed. | -7 | -7 |  |  | 1.4 | 1.8 | 60444212 | 194408 | 60444212 | 117884
2022-06-17 | June 2022 Review | Cash flow adjustment | Debt Funding | Property purchase (local roads) | Hamilton City Council | 2018 Southern Links Peacocke Arterials HIF | Property | Property for projects implemented as part of HIF | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow adjustment | 0 | 0 |  |  | 2.4 | 2.4 | EW Arterial, Wairere extension | 262018 |  | 118044
2022-06-29 | June 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | DELETE LGWM CS CBD to Kilbirnie and Miramar | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | covid delays tsfer $589k 2023, $3.4m to 2024 | 0 | 0 |  |  | 1.2 | 1 |  | 280363 | 60066135 | 118164
2022-06-29 | June 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM Early Delivery Golden Mile | Pre-implementation* | Golden Mile Pre-Implementation | VHMM | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow 600k Y1 due to covid delays | 0 | 0 |  |  | 1.2 | 1 |  | 267815 | 60054793 | 117808
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Rail level crossing warning devices maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | 0 | [5 empty] | 274710 |  | 117943
2022-06-29 | June 2022 Review | Cash flow adjustment | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Canterbury) | PT Futures MRT | Indicative Business Case |  | VHLL | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer of $494,872 from FY 21/22 to FY 22/23 to match current forecast. Project was put on hold for the first half of FY 21/22 awaiting for Spatial Plan to be developed by project partners. Project was recently kicked off again with consultants. | 0 | 0 |  |  | 1 | 1 |  | 268114 | 60054249 | 118242
2022-06-17 | June 2022 Review | Cash flow adjustment | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Wellington) | LGWM Mass Rapid Transit | Indicative Business Case | LGWM Mass Rapid Transit IBC | VHML | VHHH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | covid delays and related impacts move $2.4m to Y1 | -4 | -4 |  |  | 1.2 | 0.8 |  | 267831 | 60055746 | 118128
2022-06-28 | June 2022 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Regional land transport planning management | Hawkes Bay Regional Council | Regional Land Transport Planning Management 2021-24 | Implementation |  | V__ | V__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funding from year 3 to year 1 to meet increased activity in year 1 of programme. | 0 | 0 | [5 empty] | 278058 |  | 118052
2022-06-13 | June 2022 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | SH12 Matakohe Bridges | Implementation | NLTF-SH Improvements | H_L | MHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Aligning to forecast as per schedule for project close-out activities. Note - different total project cost | -1 | -1 |  |  | 1.3 | 1.3 | 60040765 | 278774 | 60040765 | 117958
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Otago) | Beaumont bridge replacement | Implementation | Beaumont Construction | H__ | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Zero Sum Delay in award & procurement delays pushing cashflow out | 0 | 0 |  |  | 0 | 12 | 60217046 | 213142 | 60217046 | 117837
2022-06-29 | June 2022 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Otago) | Beaumont bridge replacement | Implementation | Beaumont Construction | H__ | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | End of year Y0 cashflow to Y1, Y2 & Y3 (zero sum) | -2 | -2 |  |  | 0 | 12 | 60217046 | 213142 | 60217046 | 118234
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH25 Pepe Stream Bridge Replacement | Single-Stage Business Case | Single Stage Business Case | HHL | HHVH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustment | 0 | 0 |  |  | 1.3 | 1 |  | 270922 | 60058458 | 117887
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH30 Kopaki Bridge Replacement | Implementation |  | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | EOY reconciliation. Work this month greater than forecast | 0 | 0 |  |  | 99 | 99 |  | 254885 | 60052983 | 117997
2022-06-08 | June 2022 Review | Cash flow adjustment | External funding | Resilience improvements | NZTA (West Coast) | RIO SH67 Granity Seawall Protection | Implementation |  | HML | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflow some of the allocation to 22/23 FY | 0 | 0 |  |  |  |  | Construction | 250497 | 60046085 | 117588
2022-06-30 | June 2022 Review | Cash flow adjustment | External funding | Resilience improvements | NZTA (West Coast) | RIO SH67 Granity Seawall Protection | Pre-implementation* |  | HML | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | Design | 269713 | 60056029 | 118294
2022-06-26 | June 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | TNFG - North West,, | Pre-implementation* | TNFG - North West | VHHVL | VHHVL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 2 | 1 |  |  |  | 0.7 | 324.2505 | 250457 |  | 118273
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Christchurch City Council | Cluster 4: Moorhouse Ave: Detailed Business Case | Detailed Business Case |  | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project is ongoing however work scheduled to occur next financial year. | 0 | 0 |  |  | 2 | 2 |  | 251076 |  | 118000
2022-06-04 | June 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Christchurch City Council | Intersection Safety: Gasson/ Madras/ Moorhouse (1) | Construction | Design and construction | H_M | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further safety improvements are planned at this intersection next financial year. | 0 | 0 |  |  | 0 | 5.1 |  | 233479 |  | 117805
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation Programme | Pre-implementation* | Auckland System Optimisation SH - Stage 1 | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please distribute allocation as per current forecast. This change is due to delay funding approval | -1 | -1 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056410 | 254838 | 60056410 | 117818
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation Programme | Single-Stage Business Case | AKL Opt SSBC | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $237,321 from FY2022 to FY2023 for Programme Management costs | 1 | 1 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056366 | 254837 | 60056366 | 117823
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Preventing Wrong Way Drivers on Auckland Motorways | Implementation | Implementation | H_L | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The pre implementation is on hold, so the implementation phase will not commence as planned. Moving the entire budget $7,797,272 to next FY | 0 | 0 |  |  | 2.4 | 2.4 |  | 269883 | 60057070 | 117920
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Preventing Wrong Way Drivers on Auckland Motorways | Pre-implementation* | Pre-Imp | H_L | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project is on Hold so Moving Funds $520323 into the next FY. | 0 | 0 |  |  | 2.4 | 2.4 |  | 269882 | 60057069 | 117919
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | SH16 Brigham Creek to Waimauku Safety Enhancements | Implementation |  | HML | HML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Aligning allocations with forecast as per current programme. | -4 | -4 |  |  | 0 | 1.1 | 60040043 | 261620 | 60040043 | 117964
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | SH16 Brigham Creek to Waimauku Safety Enhancements | Pre-implementation* | 60040042 | HML | HML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Aligning allocations with forecast as per current programme. | 1 | 1 |  |  | 0 | 1.1 | 60040042 | 261619 | 60040042 | 117963
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | SH16/18 Connections | Detailed Business Case |  | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moved the funds $803834 from CY to next FY as the project is on hold. | 0 | 0 |  |  | 3.5 | 3.5 | 60044214 | 247331 | 60044214 | 117918
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | SH20A to Airport | Construction | Construction | H_L | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow to reflect extended landscape maintenance period | 0 | 0 |  |  | 3.1 | 3.1 | 60216937- moved to Crown Funded Phase | 199866 | 60216937 | 117993
2022-06-17 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Auckland) | SH22: SH1 Drury to Paerata - (corridor improvements) | Pre-implementation* |  | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Placed on hold duirng FY22 as part of coordination exercise, phasing and boundaries to be agreed, design to re-commence once scope is fully understood - expected to be in FY23. | 0 | 0 |  |  | 0 | 1.6 |  | 278494 | 60062159 | 118002
2022-06-07 | June 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (BOP) | CIP SH30 Eastern Corridor, Rotorua | Construction | Crown Infrastructure Partners | M_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustments | 0 | 0 |  |  | 0 | 4.1 |  | 271547 | 60059176 | 117880
2022-06-07 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (BOP) | SH2 Wainui Rd to Opotiki, NSRRP | Implementation |  | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustments | 2 | 2 |  |  | 1 | 1 |  | 278518 | 60062263 | 117869
2022-06-17 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | SH2: Baypark to Bayfair Link Upgrade (was MGI) | Construction | Implementation | H_H | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow of $1,344,912 from 21/22 into 22/23 year - Covid delays | 1 | 1 |  |  | 2.5 | 2.5 | 60209881 | 194043 | 60209881 | 118126
2022-06-17 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (BOP) | SH30 Awakeri to Whakatane | Pre-implementation* | SH30 Awakeri to Whakatane | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow - ~$300k to next year and moving ~$1M from Y2 to Y1 | -2 | -2 |  |  | 10 | 10 | 49 | 277254 | 60060860 | 118129
2022-06-07 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (BOP) | SH33 (Te Ngae Junction to Paengaroa), NSRRP | Implementation |  | H_H | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustment | -4 | -4 |  |  | 1.2 | 1.2 |  | 278523 | 60062268 | 117870
2022-06-07 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Canterbury) | Rakaia to Ashburton Safety Improvements - SSI | Pre-implementation* |  | MHL | HHM | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Repackage excercise underway | 0 | 0 |  |  | 0 | 1.6 |  | 278549 | 60062294 | 117787
2022-06-07 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Rakaia to Ashburton CI - Stage 2 | Pre-implementation* |  | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Repackage excercise underway | 1 | 1 |  |  | 0 | 1.6 |  | 278557 | 60062300 | 117788
2022-06-29 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Canterbury) | SH7 Waipara to Waikari Safety Improvement | Implementation | NLTF-SH Improvements | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cashflowing $269,712 as job will be finished nxt FY as advised by MnO | 0 | 0 |  |  | 1.2 | 1.2 | 60031518 | 278803 | 60031518 | 118214
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Hawkes Bay) | Prebensen Hyderabad Intersection upgrade | Implementation | NLTF-SH Improvements | M_H | MHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Pleaae move $983,942 from 2022 to 2023 | 0 | 0 |  |  | 14.6 | 14.6 | 60214528 | 278795 | 60214528 | 117806
2022-06-08 | June 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Hawkes Bay) | RIO SH02 College Rd-Silverstream IMPR | Implementation | Construction | L_M | MLM | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Pleaae move $1,928,433 from 2022 to 2023 | -1 | -1 |  |  | 1 | 1 | 60207438 | 269700 | 60207438 | 117809
2022-06-29 | June 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Hawkes Bay) | RIO SH02 Tahaenui Bridge Widening | Implementation | Construction | M_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $172,880 from 2022 to 2023 and $79,384 from 2022 to 2024, due to contractor being moved onto Boost projects. | -3 | -3 |  |  | 1 | 1 | 60056028 | 269712 | 60056028 | 118243
2022-06-29 | June 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Hawkes Bay) | SH2 Inter-Reg connections: Passing Opps | Implementation | PGF | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $1,104,538 from 2022 to 2023 Construction delayed to next year due to Covid and slow progress. | -3 | -3 |  |  | 1 | 0.8 | Implementation | 264871 | 60052056 | 118237
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Hawkes Bay) | SH5 Hawkes Bay RB to SH2 | Pre-implementation* | SH5 Hawkes Bay RB to SH2 | HML | VHHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please transfer across $304,348 from 2023 to 2022 due to actual feasibility design fees. Please also move funds sitting in Y3 into Y1 | -3 | -3 |  |  | 10 | 10 | 15 | 277286 | 60060909 | 117824
2022-06-17 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North Levin - SH1/57 - southern section | Implementation |  | VHHL | HHVH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $6,503,726 from 2022 to 2023, due to Covid delays | -3 | -3 |  |  | 0 | 1.6 |  | 278530 | 60062283 | 118048
2022-06-17 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North of Levin - SH1/SH57 - northern section | Pre-implementation* | R2Z | HHL | HHH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $540,235 from 2022 to 2023, due to covid delays | -2 | -2 |  |  | 0 | 1.6 |  | 278533 | 60062282 | 118047
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Palmerston North Integrated Transport Improvements | Detailed Business Case | Detailed Business Case Stage 1 | HML | MML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $78,639 from 2022 to 2023 Project delayed, communications now schedule for Q1 FY22/23 | -1 | -1 |  |  | 1 | 1 | Detailed Business Case Stage 1 | 264176 | 60050244 | 117905
2022-06-29 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Whirokino Trestle and Manawatu River Bridge Replacement | Implementation | NLTF-SH Improvements | H_L | MHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $1,135,995 from 2022 to 2023 due to late completion of Bridge demolition works | 0 | 0 |  |  | 1.5 | 1.5 |  | 278777 | 60216478 | 118210
2022-06-14 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Nelson - (median barrier) | Pre-implementation* | R2Z | VHML | VHHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | slow start to design phase as internal approvals delayed start. Cashflow approx 372k to 22/23 | 1 | 1 |  |  | 0 | 1.6 |  | 278544 | 60062290 | 117945
2022-06-14 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Nelson - (median barrier) | Property |  | VHML | VHHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | slow startr to property phase- cashflow approx 241k from 21/22 to 22/23 as per forecast | -1 | -1 |  |  | 0 | 1.6 |  | 277073 | 60059599 | 117960
2022-06-13 | June 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Northland) | RIO SH11 & SH10 Puketona RND | Implementation | Implementation | M_H | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Aligning to forecast as per schedule for project close-out activities. | -1 | -1 |  |  | 1 | 1 | 60055987 | 236536 | 60055987 | 117953
2022-06-13 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Northland) | SH1 Loop Road North to Smeatons Hill Safety Improvement | Implementation | NLTF-SH Improvements | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Aligning allocations with forecast as per current schedule; had to continue constructing some parts of the dual lane corridor as part of the scope change from 19/20 to provide a safe corridor for the public while the remaining stages are under construct. | -6 | -6 |  |  | 0 | 1.2 | 60210807 | 278791 | 60210807 | 117974
2022-06-07 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Northland) | SH1N Port Marsden Highway to Te Hana improvements | Detailed Business Case | Single stage IBC/DBC | H__ | VHML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project is on hold and hence, need to cashflow the allocation of $5,670 from 2021/22 to 2028/29 | 0 | 0 |  |  | 0.9 | 0.9 | 60042313 | 249234 | 60042313 | 117790
2022-06-29 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Otago) | SH6 Hardware Ln to McDowell Dr | Pre-implementation* |  | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflowing $724,585 to next FY waiting on resourcing consideration way forward on project | 0 | 0 |  |  | 10 | 10 | 177 | 277331 | 60061015 | 118248
2022-06-29 | June 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Southland) | CIP SH94 Homer Tunnel | Implementation | CIP SH94 Homer Tunnel | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflowing as project is delayed to nxt FY$777,479 | -2 | -2 |  |  | 0 | 0 |  | 275306 | 60059181 | 118247
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Southland) | SH1S Bluff Highway/Elles Road I/S Improvement | Implementation |  | M_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | COVID claims L4 (13,327) L3 (3,670) also contingency that can not be changed. Rail delays, transfer $2,106,410 into next year | 0 | 0 |  |  | 2.4 | 2.4 |  | 278541 | 60062305 | 117850
2022-06-08 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Taranaki) | Normanby Overbridge Realignment | Implementation | Implementation - NLTF funding | L_H | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $1,261,576 from 2022 to 2023, Property owner proving difficult | -1 | -1 |  |  | 4.1 | 4.1 |  | 264232 | 60202649 | 117878
2022-06-02 | June 2022 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Taranaki) | SH3/3A Waitara to Bell Block | Detailed Business Case | Waitara to Bell Block Route Imp: SH3/3A to Waitara | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This request is now cancelled as it Regional Improvements output. | 0 | 0 |  |  | 1.1 | 1.1 | 60041305 | 232681 | 60041305 | 117634
2022-06-29 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Taranaki) | SH3/3A Waitara to Bell Block | Pre-implementation* | NZTA-R2Z | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $274,730 from 2023 to 2022 to cover accelerated spend in current Financial year | 1 | 1 |  |  | 1.1 | 1.1 |  | 278528 | 60062275 | 118232
2022-06-14 | June 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Tasman) | CIP SH60 Motueka Project | Implementation | CIP SH60 Motueka Investigation Project | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project substantial complete but some additional works may be undertaken at CIP request so cashflow funding not spent from 21/22 to 22/23 aprox 826k | 0 | 0 |  |  | 3.3 | 3.3 |  | 276583 | 60059407 | 117906
2022-06-14 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | Hamilton Ring Road - Wairere/Cobham Interchange | Implementation | Interchange implementation | HHM | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Progress delayed from beam quality dispute. More expenditure pushed into next financial year | -1 | -1 |  |  | 7.6 | 7.6 | 16-015 | 262942 | 60048597 | 117886
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Implementation |  | VHML | VHLL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustment | 0 | 0 |  |  | 0 | 1.6 |  | 278490 | 60062182 | 117867
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Pre-implementation* |  | VHML | VHLL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustment. | 0 | 0 |  |  | 0 | 1.6 |  | 278491 | 60062183 | 117868
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 ETA Corridor Improvements | Implementation | NZTA-R2Z | VHML | VHML | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow into next financial year | 0 | 0 |  |  | 2.6 | 2.6 |  | 278477 | 60062184 | 117813
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Piarere to Tokoroa Safer Corridor | Pre-implementation* | R2Z | VHHL | HHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustment | 0 | 0 |  |  | 0 | 1.6 |  | 278506 | 60062206 | 117863
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Tokoroa to Taupo Safer Corridor | Implementation | R2Z | H_L | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustment. | 0 | 0 |  |  | 0 | 1.6 |  | 278486 | 60062207 | 117864
2022-06-29 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Tokoroa to Taupo Safer Corridor | Implementation | R2Z | H_L | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Wet weather caused delay in construction works | 0 | 0 |  |  | 0 | 1.6 |  | 278486 | 60062207 | 118230
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Tokoroa to Taupo Safer Corridor | Pre-implementation* |  | H_L | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end cashflow adjustment | -2 | -2 |  |  | 0 | 1.6 |  | 278487 | 60062208 | 117865
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH2 and SH27 IS | Pre-implementation* |  | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please transfer $367,925 from 2022 to 2023 due to project still in feasibility phase | 0 | 0 |  |  | 10 | 10 | 23138 | 277351 | 60061063 | 117828
2022-06-14 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH23 and SH39 IS | Pre-implementation* | SH23 and SH39 IS | VHHH | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $363,860 from 2022 to 2023 due to delays caused by various reasons (feasibility gateway, etc.). | 0 | 0 |  |  | 10 | 10 | 20573 | 277348 | 60061054 | 117888
2022-06-15 | June 2022 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Waikato) | SH27 (SH26 to SH24), NSRRP | Implementation | SH27 (SH26 to SH24), NSRRP | H_H | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.3 | 1.3 | 60028110 | 231714 | 60028110 | 117885
2022-06-14 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH29 Piarere to SH28 | Pre-implementation* | SH29 Piarere to SH28 | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $157,814 from Y1 to current FY due to close out of feasibility report costs | 0 | 0 |  |  | 10 | 10 | 38 | 277244 | 60060852 | 117921
2022-06-17 | June 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Implementation | Construction implementation | H_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow $166,562 from CY to Y1 due to uncompleted works in this season. | 0 | 0 |  |  | 0.8 | 0.8 | 60038686 | 246371 | 60038686 | 117856
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH3 Awakino to Mt Messenger Corridor Improvements (Waikato) | Implementation | NZTA-R2Z | MML | HHL | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow$1,042,018 from CY to Y1 due to further works extended to next financial year | 0 | 0 |  |  | 1.5 | 1.5 |  | 278481 | 60062213 | 117866
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH3 and Raynes Rd IS | Pre-implementation* |  | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please transfer $261,522 from 2022 to 2023 due to project still in feasibility phase | -1 | -1 |  |  | 10 | 10 | 23093 | 277359 | 60061075 | 117830
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH3 and SH4 IS | Pre-implementation* |  | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please transfer $326,237 from 2022 to 2023 due to project still in feasibitlity phase | -2 | -2 |  |  | 10 | 10 | 20621 | 277354 | 60061064 | 117829
2022-06-29 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH5 (Mihi to Wairakei), NSRRP | Implementation |  | HHM | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Works to be carried out next FY | -4 | -4 |  |  | 1.6 | 1.6 |  | 278540 | 60062308 | 118231
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH5 Taupo to Hawkes Bay RB | Pre-implementation* |  | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | year end Cashflow adjustment. | -2 | -2 |  |  | 10 | 10 | 18119 | 277357 | 60061076 | 117831
2022-06-29 | June 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Wellington) | LGWM Strategic Highway Improvements | Indicative Business Case | LGWM Strategic Highway Improvements IBC | VHML | VHHH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | covid delays and related impacts move $2.3m to Y1 | -1 | -1 |  |  | 1.2 | 1 |  | 267842 | 60055745 | 118127
2022-06-08 | June 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Hutt Valley | Implementation | SH2 Fergusson Rd to Whakatiki St | VHMH | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | please transfer $2,469,260 from 2022 to 2023 financial year to reflect anticipated forecasts. | 0 | 0 |  |  | 10 | 10 | 101 | 277322 | 60060977 | 117827
2022-06-28 | June 2022 Review | Cash flow adjustment | Road to Zero | Road policing | NZ Transport Agency | Tackling Unsafe Speeds | Pre-implementation* | Safety camera IBC. DBC & Pre-Imp | VH_L | VHHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow $2m from 22/23 to 23/24 due to timeline delays | 0 | 0 |  |  | 1.3 | 1.3 | WBS80002655 - Richard Stewart | 280055 |  | 118298
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | -1 | [5 empty] | 274702 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 248014 | 126487 | [5 empty] | 274700 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | -100000 | -50999 | [5 empty] | 274715 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | -1 | [5 empty] | 274713 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 5822 | 2969 | [5 empty] | 274716 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | 0 | [5 empty] | 274703 |  | 117943
2022-06-16 | June 2022 Review | Cash flow adjustment | External funding | Technology to improve effectiveness of public transport systems | Auckland Transport | Community Connect - Auckland Trial | Implementation | Community Connect - Set Up Costs | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As advised to Waka Kotahi, this work will now slip due to the revised timing to allow for the start of a National scheme. While the final projected costs are slightly less than approved, we will retain the full approval until requirements and costs are finalised. | 0 | 0 |  |  |  |  | 554.2774 | 277400 |  | 117728
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 2 | 0 | [5 empty] | 274719 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 84618 | 43155 | [5 empty] | 274701 |  | 117943
2022-06-17 | June 2022 Review | Cash flow adjustment | Local road maintenance | Unsealed road metalling | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | One network maintenance contract rates re-negotiated due to the need for a contract extension due to current delivery with the SH NOC and while WBOPDC's future delivery model is reviewed /confirmed. | 0 | -1 | [5 empty] | 274712 |  | 117943
2022-06-29 | June 2022 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Indicative Business Case | LGWM City Streets | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | covid delays and related impacts move $684k to 2023 | -3 | -3 |  |  | 1.2 | 1 |  | 267838 | 60053840 | 118169
2022-06-29 | June 2022 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM ED Central City and SH1 walking cycling and safer speed | Single-Stage Business Case | Central City And SH1 Walking Cycling + Safer Speed | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | covid delays and related impacts move $280k to 2023 | -1 | -1 |  |  | 1.2 | 1 |  | 267817 | 60054792 | 118168
2022-06-14 | June 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Westhaven to CBD (NLTF) | VHHH | HHH | Y | 4 | Approved | Approved by Auckland Transport Chief Financial Officer |  | 3384105 | 1725893 |  |  | 0 | 6.8 | 452.2503 | 250337 |  | 117902
2022-06-22 | June 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - Links to Public Transport | Implementation | UCP - ACN Links to PT - NL to Avondale - IMP(NLTF) | H_M | MHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Additional designs have been identified to meet the final resource consent conditions which led to the cost and scope changes. The IQA of this project in November 2018 noted at the time that consenting could be a risk for the project. Other contributing factors to the cost/scope increase include: â€¢ Amendments to the original design due to omissions and errors in the drawings for the Issued for Construction (IFC), which included the stormwater locations. â€¢ Additional designs* on the retaining walls, underpass and necessary remedial works. | 5821365 | 2968896 |  |  | 0 | 4.1 | 452.2416 | 241554 |  | 117267
2022-06-27 | June 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Kaipara District Council | Mangawhai Shared Path | Implementation | Mangawhai Shared Path - Phase 2 | VHHL | VHHVH | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1512042 | 937466 |  |  | 1.4 | 1.4 | Shared Path LTP 1 | 270524 |  | 118170
2022-06-16 | June 2022 Review | Cost Decrease | External funding | Cycling facilities | NZTA (Auckland) | NZUP Northern Pathway (Westhaven to Akoranga) | Detailed Business Case |  | VH_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $1,499,999 from 60066010 (DBC), $20,594,933 from 60056052 (Imp) to 60056054 (Pre-Imp) to cover $22,094,931 (overspend) in Pre-Imp. | -1552500 | -1552500 |  |  | 1.3 | 1.3 |  | 280036 | 60066010 | 117946
2022-06-16 | June 2022 Review | Cost Decrease | External funding | Cycling facilities | NZTA (Auckland) | NZUP Northern Pathway (Westhaven to Akoranga) | Implementation | NZ Upgrade Programme | VH_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $1,499,999 from 60066010 (DBC), $20,594,933 from 60056052 (Imp) to 60056054 (Pre-Imp) to cover $22,094,931 (overspend) in Pre-Imp. | -21315755 | -21315755 |  |  | 1.3 | 1.3 |  | 269720 | 60056052 | 117954
2022-06-16 | June 2022 Review | Cost Increase | External funding | Cycling facilities | NZTA (Auckland) | NZUP Northern Pathway (Westhaven to Akoranga) | Pre-implementation* | NZ Upgrade Programme | VH_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $1,499,999 from 60066010 (DBC), $20,594,933 from 60056052 (Imp) to 60056054 (Pre-Imp) to cover $22,094,931 (overspend) in Pre-Imp. | 22868254 | 22868254 |  |  | 1.3 | 1.3 |  | 269719 | 60056054 | 117956
2022-06-28 | June 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Tauranga City Council | Primary cycle route Area B (Otumoetai/Bellevue/Brookfield)Â | Single-Stage Business Case | SSBC - Area B | VHHL | HHH | N | 2 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | This funding enables the completion of a significant mode-shift related business case for Tauranga City. As this is a business case, there is no BCR to change. | 674002 | 343741 | Inform the applicant that no further cost increases will be considered for this phase. |  | 2.7 | 2.7 | SSBC - Area B | 276667 |  | 117645
2022-06-13 | June 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Wellington City Council | Transitional Cycleways Programme (ex Accelerated)(SfP) | Single-Stage Business Case | Brooklyn Hill Improvements SSBC | HHL | VHHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Amending phase to WCC Cycleways Transformational | -498000 | -253980 |  |  |  | 3.5 | Brooklyn Hill Improvements SSBC | 281059 |  | 117909
2022-06-27 | June 2022 Review | Cost Increase | Local road maintenance | Emergency works | Auckland Transport | E/W - West Auckland - 31 August 2021 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Transport Services) | Refer to delegation committee submission of June 2022. | 1778942 | 907261 |  |  |  |  | 141.28 | 279955 |  | 117782
2022-06-17 | June 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Christchurch City Council | EW - Earthquake Events - NLTP funding | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Return of $m under Pain/Gain agreement. | -1023223 | -1023223 |  |  |  |  | 721* | 211617 |  | 118142
2022-06-07 | June 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW SH73 Otira Shelter Rockfall 20211017 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -1538 | -1538 | [5 empty] | 280257 | 60066144 | 117814
2022-06-10 | June 2022 Review | Cost Increase | Local road maintenance | Emergency works | Waimakariri District Council | EW - May 2021 Flood Event Waimakariri District | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | Notes The additional cost of $168,895 relates to the discovery of a collapsed culvert and the professional services and physical works cost for its reinstatement and a bypass road. | 168895 | 119916 |  |  |  |  | E/W Flood damage 20/21 reinstatement com | 280295 |  | 117289
2022-06-13 | June 2022 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Masterton District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cash neutral cost adjustment. Transitional FAR impacts overall dollars. | 0 | 1050 | [5 empty] | 276236 |  | 117783
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Auckland) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation June 2022 | 323029 | 323029 | [5 empty] | 276243 | 60061851 | 118064
2022-06-15 | June 2022 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Auckland) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -4417900 | -4417900 | [5 empty] | 276244 | 60061849 | 118065
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Auckland) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 432001 | 432001 | [5 empty] | 276246 | 60061850 | 118066
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (BOP) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 2346118 | 2346118 | [5 empty] | 276250 | 60061852 | 118067
2022-06-15 | June 2022 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (BOP) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 1329601 | 1329601 | [5 empty] | 276247 | 60061854 | 118069
2022-06-15 | June 2022 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (BOP) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1183600 | -1183600 | [5 empty] | 276247 | 60061854 | 118070
2022-06-15 | June 2022 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (BOP) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -402687 | -402687 | [5 empty] | 276249 | 60061853 | 118068
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Canterbury) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 9266 | 9266 | [5 empty] | 276254 | 60061844 | 118071
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Canterbury) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 134754 | 134754 | [5 empty] | 276252 | 60061842 | 118072
2022-06-15 | June 2022 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Gisborne) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1237680 | -1237680 | [5 empty] | 276258 | 60061855 | 118075
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Hawkes Bay) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 153329 | 153329 | [5 empty] | 276261 | 60061858 | 118076
2022-06-15 | June 2022 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Hawkes Bay) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1225326 | -1225326 | [5 empty] | 276260 | 60061859 | 118077
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Manawatu/Whanganui) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 682074 | 682074 | [5 empty] | 276263 | 60061775 | 118078
2022-06-15 | June 2022 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Manawatu/Whanganui) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -3756 | -3756 | [5 empty] | 276264 | 60061774 | 118080
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Marlborough) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 324524 | 324524 | [5 empty] | 276270 | 60061864 | 118081
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Marlborough) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 17728 | 17728 | [5 empty] | 276269 | 60061865 | 118082
2022-06-15 | June 2022 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | NZTA (Nelson) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1049053 | -1049053 | [5 empty] | 276271 | 60061778 | 118083
2022-06-15 | June 2022 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Nelson) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 7653476 | 7653476 | [5 empty] | 276272 | 60061776 | 115255
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Nelson) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 21884 | 21884 | [5 empty] | 276274 | 60061777 | 118087
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Northland) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 1172924 | 1172924 | [5 empty] | 276278 | 60061845 | 118091
2022-06-15 | June 2022 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Northland) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1279800 | -1279800 | [5 empty] | 276276 | 60061847 | 118092
2022-06-15 | June 2022 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Northland) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1826107 | -1826107 | [5 empty] | 276275 | 60061846 | 118089
2022-06-15 | June 2022 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | NZTA (Otago) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -214106 | -214106 | [5 empty] | 276280 | 60061869 | 118094
2022-06-15 | June 2022 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Otago) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 2505385 | 2505385 | [5 empty] | 276282 | 60061867 | 118095
2022-06-15 | June 2022 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Otago) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -20539 | -20539 | [5 empty] | 276279 | 60061868 | 118096
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Southland) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 636206 | 636206 | [5 empty] | 276284 | 60061870 | 118097
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Southland) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Error of $100 in earlier review in year 21/22. This review is to fix it. | 108 | 108 | [5 empty] | 276284 | 60061870 | 118099
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Southland) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 15123 | 15123 | [5 empty] | 276286 | 60061871 | 118098
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (Taranaki) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 831920 | 831920 | [5 empty] | 276288 | 60061863 | 118101
2022-06-15 | June 2022 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Taranaki) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1457587 | -1457587 | [5 empty] | 276290 | 60061861 | 118102
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Taranaki) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 1487516 | 1487516 | [5 empty] | 276287 | 60061862 | 118103
2022-06-15 | June 2022 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | NZTA (Tasman) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -16551 | -16551 | [5 empty] | 276292 | 60061875 | 118105
2022-06-15 | June 2022 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | NZTA (Waikato) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -718801 | -718801 | [5 empty] | 276297 | 60061835 | 118106
2022-06-15 | June 2022 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Waikato) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -1709532 | -1709532 | [5 empty] | 276296 | 60061837 | 118107
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Waikato) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 496802 | 496802 | [5 empty] | 276295 | 60061836 | 118108
2022-06-15 | June 2022 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | NZTA (Wellington) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -4665326 | -4665326 | [5 empty] | 276301 | 60061876 | 118109
2022-06-15 | June 2022 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Wellington) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | -202361 | -202361 | [5 empty] | 276300 | 60061879 | 118110
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Wellington) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 248904 | 248904 | [5 empty] | 276299 | 60061878 | 118111
2022-06-15 | June 2022 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | NZTA (West Coast) | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 184345 | 184345 | [5 empty] | 276303 | 60061883 | 118112
2022-06-15 | June 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (West Coast) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Programme review & reconciliation in June 2022 | 613982 | 613982 | [5 empty] | 276305 | 60061882 | 118114
2022-06-17 | June 2022 Review | Cost Decrease | Public transport infrastructure | Low cost / low risk public transport improvements | Hawkes Bay Regional Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | surplus funds | -23000 | -11730 | [5 empty] | 276163 |  | 118050
2022-06-27 | June 2022 Review | Cost Decrease | Local road maintenance | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation | Roll out of data standard | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please match funding to forecast and move excess allocation to 60057155 | -537730 | -537730 |  |  |  | 4.4 | LR Maintenance part of funding, SAP item 60067372 | 277727 |  | 118280
2022-06-27 | June 2022 Review | Cost Decrease | State highway maintenance | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation | Nationally Delivered Activity AMDS Implementation | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please match funding to forecast and move excess allocation to 60057155 as requested by Michaela | -537730 | -537730 |  |  |  | 4.4 | SAP Item 60067460 | 281639 |  | 118281
2022-06-03 | June 2022 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Wellington) | Asset Management Data Standard (DEfT) | Implementation | Nationally Delivered Activity AMDS Implementation | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -26222400 | -26222400 |  |  | 0 | 4.4 | SAP item 60066022 | 277720 |  | 117859
2022-06-17 | June 2022 Review | Cost Increase | Local road improvements | New roads | Hamilton City Council | 2018 Hamilton Ring Road - Wairere/Cobham Interchange | Construction | Construction - COVID | HHH | VHHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds being moved from Crown funding (which is no longer available) to NLTF. | 284381 | 145034 |  |  | 4.4 | 4.4 |  | 275824 |  | 118022
2022-06-30 | June 2022 Review | Cost Increase | External funding | New roads | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Detailed Business Case | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $3,275,012 from Pre-Implementation (60057047) to Detailed Business Case (60057046) due to DBC extended by 6-12 months due to NZUP additional requirements | 3389638 | 3389638 |  |  | 1.4 | 1.4 | 60057046 | 270297 | 60057046 | 118235
2022-06-30 | June 2022 Review | Cost Decrease | External funding | New roads | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Pre-implementation* | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $3,275,012 from Pre-Implementation (60057047) to Detailed Business Case (60057046) due to DBC extended by 6-12 months due to NZUP additional requirements | -3389638 | -3389638 |  |  | 1.4 | 1.4 | 60057047 | 254803 | 60057047 | 118236
2022-06-04 | June 2022 Review | Cost Increase | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (7) - SH1 Peka Peka to Otaki Expressway | Construction |  | MHL | MHM | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer from Pre-Imp (ID 60217004) to Construction (60217005) of $368,102. | 397543 | 397543 |  |  | 0.6 | 0.6 | 60217005 | 203544 | 60217005 | 117852
2022-06-04 | June 2022 Review | Cost Decrease | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (7) - SH1 Peka Peka to Otaki Expressway | Design |  | MHL | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer from Pre-Imp (ID 60217004) to Construction (60217005) of $368,102. | -397550 | -397550 |  |  | 0.6 | 0.6 | 60217004 | 203543 | 60217004 | 117851
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Auckland Transport | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 14327680 | 14327680 |  |  | 0 | 0 | 511.2716 | 271627 |  | 118144
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Bay of Plenty Regional Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 57423 | 57423 |  |  | 0 | 0 |  | 271638 |  | 118147
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Environment Canterbury | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 651548 | 651548 |  |  | 0 | 0 |  | 271664 |  | 118146
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Gisborne District Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 34638 | 34638 |  |  | 0 | 0 |  | 271644 |  | 118156
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Greater Wellington | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 6473873 | 6473873 |  |  | 0 | 0 |  | 271653 |  | 118145
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Hawkes Bay Regional Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 124340 | 124340 |  |  | 0 | 0 |  | 271647 |  | 118151
2022-06-17 | June 2022 Review | Cost Decrease | Public transport services | Passenger services - bus | Hawkes Bay Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funds from WC 517, 519 and 521 to WC 524. Moving funds equal to Year 1 Living wage costs from year 2 to year 1($214,936). Year 2 Living wage costs = $214,936 Year 3 Living wage costs = $214,936 | 0 | -1 | [5 empty] | 272719 |  | 118045
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Horizons Manawatu | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H_H | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 155487 | 155487 |  |  | 0 | 0 |  | 271650 |  | 118150
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Invercargill City Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 23857 | 23857 |  |  | 0 | 0 |  | 271670 |  | 118155
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Marlborough District Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 5802 | 5802 |  |  | 0 | 0 |  | 271661 |  | 118157
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Nelson City Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 62364 | 62364 |  |  | 0 | 0 |  | 271658 |  | 118154
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Northland Regional Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 102018 | 102018 |  |  | 0 | 0 |  | 271632 |  | 118153
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Otago Regional Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 494430 | 494430 |  |  | 0 | 0 |  | 271667 |  | 118149
2022-06-29 | June 2022 Review | Cost Increase | Public transport services | Passenger services - bus | Otago Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment for WC511 2022/23 and 2023/24 to include Living wage estimates of $1,165,800 per year based on current rate of $22.75/hour. | 2331600 | 1189116 | [5 empty] | 273705 |  | 117835
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Taranaki Regional Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 103581 | 103581 |  |  | 0 | 0 |  | 271641 |  | 118152
2022-06-23 | June 2022 Review | Cost Increase | Public transport services | Passenger services - bus | Tasman District Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Pro Rata Costs from NCC for increases in living wage and rest and meal breaks | 70358 | 35882 | [5 empty] | 274266 |  | 117363
2022-06-17 | June 2022 Review | Cost Increase | External funding | Passenger services - bus | Waikato Regional Council | COVID-19 Public Transport response | Implementation | Bus Services - Crown Supplement | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Distribution of Crown funding to support PT services. | 1082959 | 1082959 |  |  | 0 | 0 |  | 271635 |  | 118148
2022-06-04 | June 2022 Review | Cost Decrease | Public transport services | Passenger services - rail | Waikato Regional Council | Addendum to Te Huia SSBC-Interregional rail access post CRL | Single-Stage Business Case | Addendum to Te Huia SSC | HHL | VHHVH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -6043 | -3082 |  |  | 0.5 | 0.5 | Addendum to Te Huia SSBC | 280356 |  | 117810
2022-06-17 | June 2022 Review | Cost Decrease | Public transport services | Payments for Total Mobility wheelchair hoists and ramps | Hawkes Bay Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funds from WC 517, 519 and 521 to WC 524. Moving funds equal to Year 1 Living wage costs from year 2 to year 1($214,936). Year 2 Living wage costs = $214,936 Year 3 Living wage costs = $214,936 | -98604 | -98604 | [5 empty] | 272724 |  | 118045
2022-06-22 | June 2022 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Transport-related Digital Initiatives | Programme business case |  | H__ | V__ | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | No longer required in Regions but only in NZTA | -250000 | -250000 |  |  |  |  | 60060482 | 275785 |  | 118219
2022-06-28 | June 2022 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Transport-related Digital Initiatives | Programme business case |  | H__ | V__ | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | this funding was removed in error but reinstated in this review. | 250000 | 250000 |  |  |  |  | 60060482 | 275785 |  | 118295
2022-06-30 | June 2022 Review | Cost Decrease | External funding | Property purchase (State highways) | NZTA (Northland) | SH10 Waipapa Corridor Improvements | Property | PGF | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $296,112 from 60452292 (Property) to 60214480 (Construction) to cover overspend in Construction | -296112 | -296112 |  |  | 3.2 | 3.2 | PGF - Property | 270203 | 60452292 | 118124
2022-06-08 | June 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Taranaki) | Normanby Overbridge Realignment | Property | 2649 | L_H | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updating historical actuals | 84385 | 84385 |  |  | 4.1 | 4.1 | 60409872 | 194410 | 60409872 | 117924
2022-06-17 | June 2022 Review | Cost Increase | Public transport services | Public transport operations and management | Hawkes Bay Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funds from WC 517, 519 and 521 to WC 524. Moving funds equal to Year 1 Living wage costs from year 2 to year 1($214,936). Year 2 Living wage costs = $214,936 Year 3 Living wage costs = $214,936 | 224241 | 114363 | [5 empty] | 272725 |  | 118045
2022-06-16 | June 2022 Review | Cost Decrease | Local road improvements | Resilience improvements | Wellington City Council | Road Resilience Improvement 2015/25 - Ngaio Gorge/Wadestown | Construction |  | HHH | HHH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -1301996 | -664018 |  |  |  |  | Construction â€“ Grant Road | 257753 |  | 117462
2022-06-04 | June 2022 Review | Cost Decrease | Local road improvements | Road improvements | Christchurch City Council | Northern Arterial Extension and Cranford Street Upgrade | Pre-implementation* | CCC design fees | H_L | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2021/22 as activity is claiming complete | -122411 | -62429 |  |  | 2.3 | 2.3 |  | 250592 |  | 117804
2022-06-04 | June 2022 Review | Cost Decrease | External funding | Road improvements | Far North District Council | PGF Redevelopment of Strategic Rds in FN Priority 1 Routes | Construction | PGF - Ngapipito and Peria Roads | VH__ | VHHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Signed variation agreement with MBIE for transfer of $1M from Ngapipito and Peria Roads PGF to Ruapekapeka Road PGF. | -1000000 | -1000000 |  |  | 1 | 1 | PGF - Priority 1 Routes Ngapipito and Peria Roads | 271624 |  | 117784
2022-06-04 | June 2022 Review | Cost Increase | External funding | Road improvements | Far North District Council | PGF Redevelopment of Strategic Roads in FN Ruapekapeka Road | Construction | PGF - Ruapekapeka Road | VH_L* | VH_L* | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Signed variation agreement with MBIE for transfer of $1M from Ngapipito and Peria Roads PGF to Ruapekapeka Road PGF. There is also a projected carry forward for Ruapekapeka from 2021/22 of $1,050,607. | 1000000 | 1000000 |  |  | 1 | 1 | PGF - Priority 1 Routes Ruapekapeka Road | 271625 |  | 117785
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland SH Speed Management Guide Implementation | Implementation | Auckland SH Speed Management Implementation | VH_L* | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -495458 | -495458 |  |  | 0 | 4.6 |  | 264426 | 60052740 | 117966
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland SH Speed Management Guide Implementation | Pre-implementation* | Auckland SH Speed Management Pre-Implementation | VH_L* | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -189757 | -189757 |  |  | 0 | 4.6 |  | 264425 | 60052739 | 117965
2022-06-14 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | SH16/18 Connections | Detailed Business Case |  | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | updating 2017/18 actual in TIO to match SAP actual | -100 | -100 |  |  | 3.5 | 3.5 | 60044214 | 247331 | 60044214 | 118053
2022-06-07 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | Bay of Plenty SH Speed Management Guide Implementation | Implementation | BOP SH Speed Management Implementation | VH_L* | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -227774 | -227774 |  |  | 0 | 4.6 |  | 264445 | 60053160 | 117821
2022-06-07 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | Bay of Plenty SH Speed Management Guide Implementation | Pre-implementation* | BOP SH Speed Management Pre-Implementation | VH_L* | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -274530 | -274530 |  |  | 0 | 4.6 |  | 264444 | 60053159 | 117820
2022-06-07 | June 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (BOP) | RIO SH05 & SH36 Ngongotaha IS IMPR | Implementation | Construction | M_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus $2.2 as per the request of Programme Manager and Sponsor | -2200000 | -2200000 |  |  | 1 | 1 | 60056022 | 269696 | 60056022 | 117822
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | Canterbury SH Speed Management Guide Implementation | Implementation | Canterbury SH Speed Management Implementation | VH__ | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -1937362 | -1937362 |  |  | 0 | 4.6 |  | 264471 | 60053150 | 117976
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | Canterbury SH Speed Management Guide Implementation | Pre-implementation* | Canterbury SH Speed Management Pre-Implementation | VH__ | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -734633 | -734633 |  |  | 0 | 4.6 |  | 264470 | 60053149 | 117975
2022-06-30 | June 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Brougham St Corridor Improvements | Detailed Business Case | NZ Upgrade Programme | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1,696,334 from WC 60056968 to WC 60057015 to cover Pre-Imp works done during the BC phase, and also to cover BC Managed Costs. | 1755705 | 1755705 |  |  | 4 | 4 | 60057015 | 246831 | 60057015 | 118217
2022-06-30 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | NZUP Brougham St Corridor Improvements | Implementation | NZUP Brougham St Corridor Improvements | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1,696,334 from WC 60056968 to WC 60057015 to cover Pre-Imp works done during the BC phase, and also to cover BC Managed Costs. | -1755705 | -1755705 |  |  | 4 | 4 | 60056968 | 231610 | 60056968 | 118213
2022-06-30 | June 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Rolleston Access Improvements | Detailed Business Case | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1,633,825 from WC 60057117 to WC 60057113 to cover DBC shortfall due to contract variation and journaled costs. | 1691009 | 1691009 |  |  | 1.2 | 1.2 |  | 263129 | 60057113 | 118194
2022-06-30 | June 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP Rolleston Access Improvements | Implementation | NZUP Rolleston Access Improvements | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1,633,825 from WC 60057117 to WC 60057113 to cover DBC shortfall due to contract variation and journaled costs. | -1691009 | -1691009 |  |  | 1.2 | 1.2 |  | 231732 | 60057117 | 118195
2022-06-27 | June 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Implementation | NZUP Tinwald Corridor Improvements | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $107,754 from WC 60057077 to WC 60057075 to cover BC shortfall. | -111525 | -111525 |  |  | 4.6 | 4.6 | 60057077 | 238976 | 60057077 | 118246
2022-06-27 | June 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Single-Stage Business Case | NZ Upgrade Programme | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Earlier review incorrectly actioned. An amount of $39K should be crown funded (supplementary). | -40424 | -79482 |  |  | 4.6 | 4.6 | 60057075 | 246649 | 60057075 | 118275
2022-06-27 | June 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Single-Stage Business Case | NZ Upgrade Programme | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $107,754 from WC 60057077 to WC 60057075 to cover BC shortfall. | 71100 | 71100 |  |  | 4.6 | 4.6 | 60057075 | 246649 | 60057075 | 118245
2022-06-27 | June 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Single-Stage Business Case | NZ Upgrade Programme | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $107,754 from WC 60057077 to WC 60057075 to cover BC shortfall. Additional $39k for third party funding | 40424 | 40424 |  |  | 4.6 | 4.6 | 60057075 | 246649 | 60057075 | 118274
2022-06-30 | June 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Detailed Business Case | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $207,114 from WC 60031531 to WC 60031529 to cover DBC Managed Costs. | 214363 | 214363 |  |  | 1.2 | 1.2 |  | 263131 | 60031529 | 118215
2022-06-30 | June 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Implementation | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $207,114 from WC 60031531 to WC 60031529 to cover DBC Managed Costs. | -214363 | -214363 |  |  | 1.2 | 1.2 | 60031531 | 239003 | 60031531 | 118216
2022-06-30 | June 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | NZUP SH75 Halswell Rd Imps | Implementation |  | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reverting back to original approval $ at PM request due to error made in cashflowing from this project to 3 other phases -Contingency drawdown of $2,398,310 from 60063224 to 60031601, 60031610, & 60063199 because of contract variation and increase in property costs. | 2482251 | 2482251 |  |  | 2 | 2 |  | 278966 | 60063224 | 118355
2022-06-30 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | NZUP SH75 Halswell Rd Imps | Implementation |  | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contingency drawdown of $2,398,310 from 60063224 to 60031601, 60031610, & 60063199 because of contract variation and increase in property costs. | -2482251 | -2482251 |  |  | 2 | 2 |  | 278966 | 60063224 | 118193
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Gisborne) | Gisborne SH Speed Management Guide Implementation | Implementation | Gisborne SH Speed Management Implementation | VH_L* | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -126112 | -126112 |  |  | 0 | 4.6 |  | 264448 | 60052841 | 117968
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Gisborne) | Gisborne SH Speed Management Guide Implementation | Pre-implementation* | Gisborne SH Speed Management Pre-Implementation | VH_L* | VH_L | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Project Close | -120925 | -120925 |  |  | 0 | 4.6 |  | 264447 | 60052840 | 117967
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Hawkes Bay) | Hawkes Bay SH Speed Management Guide Implementation | Implementation | Hawkes Bay SH Speed Management Implementation | VH_L | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -128685 | -128685 |  |  | 0 | 4.6 |  | 264454 | 60053175 | 117982
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Hawkes Bay) | Hawkes Bay SH Speed Management Guide Implementation | Pre-implementation* | Hawkes Bay SH Speed Management Pre-Implementation | VH_L | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -178599 | -178599 |  |  | 0 | 4.6 |  | 264453 | 60053174 | 117981
2022-06-08 | June 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Hawkes Bay) | Prebensen Hyderabad Intersection upgrade | Implementation | NLTF-SH Improvements | M_H | MHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | updating historic actuals fro years 17/18 to 20/21 from SAP | 467377 | 467377 |  |  | 14.6 | 14.6 | 60214528 | 278795 | 60214528 | 117922
2022-06-15 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Hawkes Bay) | SH2 Napier Road Intersection | Implementation | NLTF-SH Improvements | H_M | HHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -105561 | -105561 |  |  | 0 | 4.5 | 60215323 | 256656 | 60215323 | 117949
2022-06-30 | June 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Hawkes Bay) | SH2 Pakipaki to Waipukurau | Implementation | NZTA-R2Z | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 191135 | 191135 |  |  | 1.7 | 1.7 |  | 278516 | 60062270 | 118332
2022-06-07 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Otamaraho Curve P/L Extension | Construction | Otamaraho Curve P/L Extension | H_M | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Closed, Undistributed Allocation can be surplused. | -299372 | -299372 |  |  | 2.2 | 2.2 | 60212314 | 214354 | 60212314 | 117879
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Marlborough) | Marlborough SH Speed Management Guide Implementation | Implementation | Marlborough SH Speed Management Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -183711 | -183711 |  |  | 0 | 4.6 |  | 264467 | 60052876 | 117970
2022-06-13 | June 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Marlborough) | Marlborough SH Speed Management Guide Implementation | Pre-implementation* | Marlborough SH Speed Management Pre-Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 432 | 432 |  |  | 0 | 4.6 |  | 264466 | 60052875 | 117969
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Nelson) | Nelson SH Speed Management Guide Implementation | Implementation | Nelson SH Speed Management Implementation | VH_L | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close | -115309 | -115309 |  |  | 0 | 4.6 |  | 264475 | 60053190 | 117987
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Nelson) | Nelson SH Speed Management Guide Implementation | Pre-implementation* | Nelson SH Speed Management Pre-Implementation | VH_L | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -469660 | -469660 |  |  | 0 | 4.6 |  | 264474 | 60053189 | 117986
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Northland) | Northland SH Speed Management Guide Implementation | Implementation | Northland SH Speed Management Implementation | VH_L | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -418473 | -418473 |  |  | 0 | 4.6 |  | 264376 | 60053155 | 117978
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Northland) | Northland SH Speed Management Guide Implementation | Pre-implementation* | Northland SH Speed Management Pre-Implementation | VH_L | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -9380 | -9380 |  |  | 0 | 4.6 |  | 264374 | 60053154 | 117977
2022-06-30 | June 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Northland) | SH10 Waipapa Corridor Improvements | Implementation | PGF | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $296,112 from 60452292 (Property) to 60214480 (Construction) to cover overspend in Construction | 296112 | 296112 |  |  | 3.2 | 3.2 | PGF - Implementation | 241049 |  | 118367
2022-06-07 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Northland) | SH1N Port Marsden Highway to Te Hana improvements | Detailed Business Case | Single stage IBC/DBC | H__ | VHML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Align historic $$ with SAP $$ | -421 | -421 |  |  | 0.9 | 0.9 | 60042313 | 249234 | 60042313 | 117910
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Otago) | Otago SH Speed Management Guide Implementation | Implementation | Otago SH Speed Management Implementation | VH__ | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -526447 | -526447 |  |  | 0 | 4.6 |  | 264477 | 60053170 | 117980
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Otago) | Otago SH Speed Management Guide Implementation | Pre-implementation* | Otago SH Speed Management Pre-Implementation | VH__ | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -550718 | -550718 |  |  | 0 | 4.6 |  | 264476 | 60053169 | 117979
2022-06-30 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Southland) | Edendale Realignment | Implementation |  | MHM | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move 100K into 22/23 for speed management. Surplus the rest. | -46212 | -46212 |  |  | 1.2 | 1.2 |  | 278941 | 60211840 | 118240
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Southland) | Southland SH Speed Management Guide Implementation | Implementation | Southland SH Speed Management Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -228183 | -228183 |  |  | 0 | 4.6 |  | 264479 | 60053200 | 117990
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Southland) | Southland SH Speed Management Guide Implementation | Pre-implementation* | Southland SH Speed Management Pre-Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -85307 | -85307 |  |  | 0 | 4.6 |  | 264478 | 60053199 | 117989
2022-06-08 | June 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Taranaki) | Normanby Overbridge Realignment | Implementation | Implementation - NLTF funding | L_H | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | updating historical actuals for 14/15 to 16/17 | 17115790 | 17115790 |  |  | 4.1 | 4.1 |  | 264232 | 60202649 | 117923
2022-06-08 | June 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Taranaki) | SH3/3A New Plymouth to Hawera | Pre-implementation* | SH3/3A New Plymouth to Hawera | HHVH | VHHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $383,865 from 2023 to 2022 to cover extra costs through feasibility phase | -48293 | -48293 |  |  | 10 | 10 | 7 | 277292 | 60060921 | 117825
2022-06-02 | June 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Taranaki) | SH3/3A Waitara to Bell Block | Implementation | NZTA-R2Z | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstating $21,473 funding removed in earlier review as per PM request | 23190 | 23190 |  |  | 1.1 | 1.1 |  | 278527 | 60062274 | 117849
2022-06-02 | June 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Taranaki) | SH3/3A Waitara to Bell Block | Implementation | NZTA-R2Z | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $21,473 from 60062274 - Construction to 60041305 Detailed Business Case, to cover costs coded to the Fees WBS this year, this will allow the DBC phase to be closed. | -23192 | -23192 |  |  | 1.1 | 1.1 |  | 278527 | 60062274 | 117631
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Taranaki) | Taranaki SH Speed Management Guide Implementation | Implementation | Taranaki SH Speed Management Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -175010 | -175010 |  |  | 0 | 4.6 |  | 264458 | 60053180 | 117984
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Taranaki) | Taranaki SH Speed Management Guide Implementation | Pre-implementation* | Taranaki SH Speed Management Pre-Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -258544 | -258544 |  |  | 0 | 4.6 |  | 264457 | 60053179 | 117983
2022-06-13 | June 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Tasman) | Tasman SH Speed Management Guide Implementation | Implementation | Marlborough SH Speed Management Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 26192 | 26192 |  |  | 0 | 4.6 |  | 264469 | 60052881 | 117972
2022-06-13 | June 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Tasman) | Tasman SH Speed Management Guide Implementation | Pre-implementation* | Marlborough SH Speed Management Pre-Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close. | 14464 | 14464 |  |  | 0 | 4.6 |  | 264468 | 60052880 | 117971
2022-06-23 | June 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Wellington) | Asset Management Data Standard (DEfT) | Pre-implementation* | Pre Implementation | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Overall cost neutral transfer - Extra allocation from 60067460 & 60067372. | 1161496 | 1161496 |  |  | 0 | 4.4 |  | 270380 | 60057155 | 118026
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Wellington) | Wellington SH Speed Management Guide Implementation | Pre-implementation* | Wellington SH Speed Management Pre-Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -275991 | -275991 |  |  | 0 | 4.6 |  | 264461 | 60053184 | 117985
2022-06-13 | June 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (West Coast) | West Coast SH Speed Management Guide Implementation | Pre-implementation* | West Coast SH Speed Management Pre-Implementation | VH_L* | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -233198 | -233198 |  |  | 0 | 4.6 |  | 264472 | 60053194 | 117988
2022-06-17 | June 2022 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | Hawkes Bay Regional Council | Public Transport Programme 2021-24 - AC 23 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | agreed as stated | -45624 | -48904 | [5 empty] | 272729 |  | 118046
2022-06-16 | June 2022 Review | Cost Decrease | Coastal shipping | Sea freight expenditure | NZ Transport Agency | Coastal Shipping - 2021-24 | Implementation | Coastal Shipping - CAPEX | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -30000000 | -30000000 |  |  | 1 | 1 | SAP 60066907 | 280335 |  | 118086
2022-06-17 | June 2022 Review | Cost Decrease | Public transport services | Total Mobility wheelchair hoists and ramps | Hawkes Bay Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funds from WC 517, 519 and 521 to WC 524. Moving funds equal to Year 1 Living wage costs from year 2 to year 1($214,936). Year 2 Living wage costs = $214,936 Year 3 Living wage costs = $214,936 | -1960 | -1176 | [5 empty] | 272723 |  | 118045
2022-06-17 | June 2022 Review | Cost Decrease | Public transport services | Total mobility operations | Hawkes Bay Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving funds from WC 517, 519 and 521 to WC 524. Moving funds equal to Year 1 Living wage costs from year 2 to year 1($214,936). Year 2 Living wage costs = $214,936 Year 3 Living wage costs = $214,936 | -123677 | -74206 | [5 empty] | 272722 |  | 118045
2022-06-09 | June 2022 Review | Support for activity management plan |  |  | Wellington City Council | Activity Management Plan 2021-24 | Support for AMP |  | ___ |  | N |  | Endorsed | Endorsed by Chief Financial Officer (CFO) | AMP is a primary document for the management of the transport network | 0 | [6 empty] | 274660 |  | 116803