## WBS-Physical Works
NZTA Work Breakdown Structure (WBS)
Civils and Transportation Infrastructure Works - First Edition 2025
Level 1 | Category | Level 2 | Sub-Category | Description
1 | Construction Preliminary and General |  |  | These are on-site overheads, meaning site-wide setup and general activities required for project management and execution. These costs are not attributable to a specific area or construction activity, and include items such as site office management, supervision, and security.
|  | 1.01 | Site Establishment | Initial setup of site facilities and infrastructure, including site welfare facilities, storage compound, laydown areas, site offices and associated utilities and security. Includes set up of site testing facility, if applicable. Any operational costs following on from set up to be included in site operation.
|  | 1.02 | On Site Management and Supervision of Works - Construction Period | The people component involved in the oversight of construction activities. Includes oversight-related roles to prepare and implement health and safety plans, quality plans (includes ITPs) and/or stakeholder management plans, incident and investigation reports, staff training, toolbox, workshops, inductions and the like, Photo Records, Aerial Photography, Video Recording and/or Site Surveillance Cameras, liaising with stakeholder, iwi, communications management, other contractors, emergency services, Network Utility Operators (NUO's) and local authorities, etc., environmental management, accomodation costs and LAFH allowance, site administration, and Quality Assurance. Excludes efforts associated with ISC reporting as this goes under Environmental Compliance.
|  | 1.03 | On Site Management - Post Construction Period | The people component involved after practical completion. This includes handover efforts after practical completion and defects liability.
|  | 1.04 | Provision for Insurances and Bonds | Obtaining necessary insurance coverage for contractor risks. Can include setup fees, excess allowances, and legal costs associated with insurance and/or bonds for the contract works.
|  | 1.05 | Site Operating Costs | Regular ongoing costs related to the operation of the site, excluding personnel. This includes expenses such as security, utilities, services, Portaloo's, portico rentals, operation of testing facility, barriers and fencing around the site offices for safety, Temporary Lighting and Protection of Existing Structures, Cartage, Shipping and/or Transportation and Delivery Costs, etc. It does not include Temporary Traffic Management.
|  | 1.06 | Site Maintenance During Construction | Maintenance activities performed by the project team within the construction site limits once the project team has taken over the site. This includes tasks such as pothole repairs, weeding, spraying, and footpath maintenance—activities typically handled by NZTA, KiwiRail, or other authorities prior to construction.
|  | 1.07 | Survey and Set-Out | Conducting measurements and assessments to guide construction activities. Includes setting out, topographical surveys, bed scanning, dilapidation surveys, as-built surveys, deformation monitoring, volume surveys, boundary surveys, Registration of new boundaries with LINZ, Protection of all other survey marks, Survey control for bridge works or other and aerial or drone surveys. Excludes settlement monitoring as this is to be included under Ground Improvements.
|  | 1.08 | As-Built Handover Documentation | All records and documentation during construction, including final documentation and transfer of completed works (i.e. As-builts, RAMM, CCTV Records, Certification by Registered Surveyor, Testing and Commissioning, including Operation Manuals, Training, etc.).
|  | 1.09 | Site Disestablishment | The process of dismantling and removing temporary welfare facilities, plant yards, laydown areas, etc. including disconnecting, removing and abandoning disused services and restore, rehabilitate/reinstate the site after completion (to a similar state it was before), and finalising demobilisation activities.
2 | Environmental Compliance |  |  | Activities to meet environmental regulations, standards, and consents, including ongoing monitoring, management for compliance, and mitigation measures.
|  | 2.01 | Consenting Costs | Fees and charges related to construction activities and services provided by regulatory authorities for inspection, monitoring, and ensuring compliance with relevant environmental standards and regulations. Excludes the people management relating to consenting as this is considered under Preliminary and General - On Site Management.
|  | 2.02 | Erosion and Sedimentation Controls | Activities to prevent soil erosion, manage sediment, and treat stormwater runoff at the construction site. This includes to prepare, implement and maintain Environmental Management Plan, installation and maintenance of sedimentation retention ponds, (including decanting earth bunds), silt fences, silt socks, bunds (topsoil, clay, etc.), diversion channels, etc., and other temporary control measures to prevent runoff and sediment discharge into surrounding areas. Includes both temporary and permanent solutions.
|  | 2.03 | Noise and Vibration Monitoring and Mitigation | All costs associated with noise and/or vibration monitoring and mitigation during construction, on site, for the contract duration, including noise and vibration surveys, monitoring equipment/devices, plant and materials.
|  | 2.04 | Dust Monitoring and Mitigation | All costs directly or indirectly involved in the dust monitoring and mitigation/suppression during construction on site for the contract duration, including dust monitoring equipment, plant and materials (including wheel washdowns).
|  | 2.05 | Field Ecology Works | Activities to protect and manage local ecosystems, including wildlife temporary and/or permanent relocation, sanctuaries, etc. (including engaging specialist consultants), pest control, and managing vegetation. This includes activities in both terrestrial and marine environments. This includes both permanent and temporary activities, such as temporary stream and river diversions, necessary to facilitate construction while protecting the environment.
|  | 2.06 | Archaeological Works | Activities for preservation and management of archaeological findings and sites during construction. This includes monitoring, excavation, and protection of historical or culturally significant artifacts and sites.
|  | 2.07 | Marine Controls | Activities related to controlling the impact of construction on seawater and marine environments, including turbidity control, plume management and spill control. Excludes any sea/river bed scanning as this should be included in survey. Any animal-related activities should be covered under ecology works.
|  | 2.08 | Sustainability and ISC Requirements | Time, resources, and costs associated with complying with ISC (Infrastructure Sustainability Council) requirements, carbon tracking, sustainability reporting, and other environmental impact reporting obligations.
3 | Site Clearance |  |  | Activities which prepare the site for construction by removing existing elements (such as structures and vegetation) to provide a clear area for new works.
|  | 3.01 | General Site Clearance and Demolition | Removal and/or disposal of debris, rubbish and the like off-site, disposal of salvaged materials, remove existing kerb and/or channel, barriers, drainage structures (manholes, catchpits, headwalls, scruffy domes, etc.), signage, footpath and/or shared paths, traffic islands, fences, gates and/or letterboxes, etc.
|  | 3.02 | Demolition of Major Structures (Retaining Walls, Bridges, Buildings, Misc. Structures) | Dismantling and removing existing retaining walls, bridge structures, buildings/properties, tunnel structures/viaducts and other miscellaneous structures (incl. testing and removal of asbestos and other hazardous materials removal).
|  | 3.03 | Demolition of Minor Structures (Gantries) | Remove existing gantry structures including foundations and bases, including disposal of salvaged materials into stockpiles at nominated storage areas.
|  | 3.04 | Tree Felling and Vegetation Clearance | Remove and disposal of trees and vegetation including stump grinding, chipping, splitting, mulching, slashing, including protection/preservation of retained trees and/or vegetation. Excludes removal of topsoil (to be managed as an earthworks movement).
|  | 3.05 | Removal of Services and Lighting | Decommissioning and removal of existing underground services and utility assets, including overhead and underground power distribution, water supply, wastewater, stormwater, gas, redundant culverts, pipes, street lighting and other lighting, groundwater wells, etc.
|  | 3.06 | Removal of Pavement | Removing existing road surfaces, including asphalt and concrete pavements. Includes milling, scarifying and saw cutting done within the pavement category. (Note - includes testing and removal of hazardous substances such as coal tar).
4 | Temporary Traffic Management |  |  | For managing the movement of traffic (vehicles, pedestrians, animals) around and through the construction site, including traffic control for temporary diversions, signage, and safety measures. Excludes any earthworks or pavement work for temporary diversions.
|  | 4.01 | Traffic Management Designs and Plans (TMP) | Development and approval of Contractor's Traffic Management Plan and site specific TMPs, Traffic impact assessments, Traffic Modelling and monitoring, TTM toolbox, workshops, inductions and the like, auditing, etc.
|  | 4.02 | Implementation and Maintenance of Temporary Traffic Management (TTM) | Implement, shifting, maintenance and subsequent removal of TTM in accordance with the approved TMP's, including Pedestrian and cyclist management, detour routes, etc.
5 | Site-Wide Temporary Works and Plant |  |  | Includes temporary structures, works and services that support several construction activities. Can include temporary staging, temporary jetties, scaffolding, accessways, crane pads, where they are used for 'Site-Wide' purposes. For example temporary staging/works that is only used for a specific bridge construction should be allocated to the temporary works subcategory under 'Bridge and Viaduct Structures', similarly with Temporary Drainage Works, Temporary Works for Pavement and Surfacing, etc. Can include items such as bridge segment launching gantry, tunnel boring machine, project site sheet piling, etc. (Excludes any temporary traffic management setups or maintenance as this would be covered under 'Temporary Traffic Management').
|  | 5.01 | Temporary Works Design | Specific design related costs for Temporary Staging and any other Site-Wide Temporary Platforms/Works (usually Contractor Managed Design Works).
|  | 5.02 | Other Site-Wide Temporary Works | Erecting, maintaining and removing any other temporary works relating to the project works that cannot be measured under specific Categories.
6 | Earthworks |  |  | Involves modifying site terrain through excavation, filling, grading, and compaction, forming the foundation for further construction activities.
|  | 6.01 | Earth Movements | Includes all earthworks movements - this includes 'Strip Topsoil's', 'Undercut' (Undercut Soft and Unsuitable Material), 'Cut to Waste', 'Cut to Stockpile', 'Cut to Fill', 'Import to Fill', etc. including 'Reclamation Works' (i.e. to Dams, Lakes, Rivers, Sea, etc.). Note - includes all excavation, hydro excavation, shaping, disposal off-site, transport/hauling, grading, levelling, disposal off-site, benching/shoring, imported (i.e. quarry supply) fill materials, including temporary stockpiling, placement and compaction, conditioning, keeping excavations free of water and testing. (Note - for Common and Shared Service Trenching refer to 'Utilities' and/or 'Drainage').
|  | 6.02 | Extra Over for Disposal of Contaminated Materials | Extra Over to transport and dispose of contaminated materials to a managed facility, including testing, double handling, H&S requirements, etc.
|  | 6.03 | Temporary Earthworks | Includes haul roads, any containment areas, temporary stockpile areas. Includes warning height systems, signage for haul roads (Excludes wheel wash - this is to be included under Environmental Compliance).
|  | 6.04 | Rock Breaking | Excavate in rock, including site trials of plant, shaping, grading, levelling, disposal/stockpiling, benching/shoring, blasting, drilling, percussion hammers, transport/hauling, etc.
|  | 6.05 | Soil Conditioning | Plant, labour and materials required to improve earth, including subgrade strengthening and stabilisation.
7 | Ground Improvements |  |  | Improves and stabilise the ground's physical properties to support elements such as structures and pavement.
|  | 7.01 | Ground Investigation and Settlement Monitoring and Instruments | All ground investigation works required within the NZGS Guidelines for ground investigations, including equipment for testing, reporting, lab testing and sample storage. Settlement monitoring includes the supply, installation and removal of ground monitoring equipment, reporting, inspections and maintenance, repairs or replacements, etc. (Note - any traffic controls need to be in Temporary Traffic Management).
|  | 7.02 | Geotextile / Geogrid | Geotextile - Synthetic fabrics used to reinforce soil and improve ground stability / Geogrid - Grids made from polymers used to reinforce and stabilise soil.
|  | 7.03 | Stone Columns | Insertion of compacted stone aggregate into the ground, includes temporary works to access the work area, drilling or pre-boring, supply and installation of aggregate, compaction, generators, water pumps and other auxiliary equipment necessary for the operation.
|  | 7.04 | Soil Mixing | Includes deep soil, shallow soil, in-situ soil, horizontal soil, cement or bentonite mixing, including site preparation, work platforms (not already included elsewhere), plant and labour, soil mixing materials, testing and quality controls, demob, etc.
|  | 7.05 | Site Decontamination | Treatments to remove or neutralise hazardous substances from the soil or groundwater.
|  | 7.06 | Wick and Sand Drains | Aka Prefabricated Vertical Drains - Vertical drains installed to accelerate soil consolidation by removing water, includes site preparation, work platforms (not already included elsewhere), supply, delivery and installation, reinstatement, etc.
|  | 7.07 | Buttress Drains | Aka Trench Drains or Counterfort Drains - Drainage systems installed to support and stabilise slopes and embankments.
|  | 7.08 | Dynamic/Rapid Impact and Vibro Compaction | Repeated dropping of a heavy weight to compact soil or by vibration method.
|  | 7.09 | Ground/Soil Freezing | A construction technique that uses a system of pipes to freeze soil and create a solid, impermeable material. Used to support excavations, shafts, tunnels, groundwater barrier controls, etc.
|  | 7.1 | Grouting | Includes compensation, pressure, jet or permeation grouting, including site preparation, work platforms (not already included elsewhere), plant and labour, grouting materials, testing and quality controls, demob, etc.
|  | 7.11 | Load Transfer Platform (LTP) | Platform consisting of one or more layers of geosynthetic reinforcement placed above stone columns, piles or other, including supply, installation and compaction, basal reinforcement layers, bedding and levelling layers, etc.
8 | Drainage |  |  | Permanent elements that manage surface and sub-surface water to prevent flooding and water damage, including stormwater systems and subsoil drainage. Note - all drainage excavations shall be included under Earthworks unless otherwise specified.
|  | 8.01 | Temporary Drainage Works | Construction and removal of temporary drainage for the site. Includes item relating to dewatering site works, including sump pumps, submersible pumps, channelling, wellpoints, holding tanks, temporary ponds to control water during the construction phase, etc. (Note - also includes temporary dredging works).
|  | 8.02 | Culverts / Pipes | Includes stormwater, culverts, etc. bedding, pipework and fittings, cutting, laying, jointing, sealants, backfill, compaction, flushing and cleaning, etc. (Includes Well discharge pipes). Covers different types of pipes used for drainage, as well as excavation, disposal of materials, and trenchless methods (such as thrusting, directional drilling, pipe ramming, directional drilling, etc.). Note - all drainage excavations shall be included under Earthworks unless otherwise specified.
|  | 8.03 | Drainage Structures | Components including manholes, cesspits, catchpits, scruffy domes, soak wells, siphons, sumps, stormwater treatment devices, headwalls, wingwalls, storage tanks, reservoirs, etc. - including bedding, concrete, formwork, reinforcement, precast concrete, construction and expansion joints, joint fillers, surface finishes and treatment of concrete faces, lids, connections, and inlet and outlet structures, backfilling, compaction, flushing and cleaning, etc. Note - all drainage excavations shall be included under Earthworks unless otherwise specified.
|  | 8.04 | Surface Drains and Stockwater Races | Channels that collect and direct surface water to the drainage system, including vegetated/rock lined/concrete conveyance, v-dish channel cut-off drains, overland flow bunds, trench drains, land drains, stockwater races (including inlets/outlets), etc.
|  | 8.05 | Flumes and Rip Rap Erosion Protection | Open channels that convey and control stormwater, includes excavation and disposal of surplus materials, prep, shaping and trimming, rip rap installation, half pipe flumes, geotextile linings, etc.
|  | 8.06 | Kerb and Channel | Edge restraints and channels that guide water along roadways to drainage inlets, including excavation, shaping and trimming, basecourse prep, forming and finishing kerbs, expansion joints, reinstatement, etc.
|  | 8.07 | Rain Gardens and Swales | Vegetated depressions/swales designed to absorb and filter or infiltrate stormwater runoff.
|  | 8.08 | Subsoil Drains | Aka 'French Drains', a drainage system that is used to remove excess water from the ground or soil around a building/structure (e.g. Nova Flow Drain), includes excavation and disposal of surplus material, shaping and trimming, bedding and backfilling, drainage coil, filter cloth, flushing eyes/clean out points, drainage chip, etc. (Note - this is if subsoil drains haven't been included already under another Category such as 'Structural Walls and Protection Works', etc.).
9 | Pavement and Surfacing |  |  | All layers from Sub-Grade Fill/Sub-Grade Improvement Layer up to create a permanent surface for users, including vehicles and pedestrians, including subbase, base course, stabilized layers and surfacing materials, including jointing, trial testing, etc. Note - undercuts and other earthworks to be measured under 'Earthworks - Earth Movements'.
|  | 9.01 | Temporary Works for Pavement and Surfacing | Constructing temporary access/diversion roads and pathways for access during construction. Includes potholing, pavement construction, surfacing & line markings (Note - any traffic controls need to be in Temporary Traffic Management).
|  | 9.02 | Sub-Grade Fill / SIL | The layer of fill material (imported Pit Run or other) once undercut is completed to build up levels for Subbase, includes Sub-grade Preparation works, incudes all testing requirements (Note SIL = Sub-Grade Improvement Layer).
|  | 9.03 | Subbase | The layer of material above the sub-grade fill or natural ground to provide support for the basecourse, includes subbase preparation works and most often includes using imported aggregates or recycled materials such as concrete or asphalt, incudes all testing requirements.
|  | 9.04 | Basecourse | The next layer above the Subbase course or the course layer immediately below the Surfacing, providing structural support, includes basecourse preparation works and most often includes using imported aggregates or materials, incudes all testing requirements.
|  | 9.05 | Stabilised Layers | Stabilised Layers - this relates to stabilisation and modification in pavement layers such as cement, lime, foamed bitumen, polymer, fly ash, etc.
|  | 9.06 | Surfacing | The top layer of design mix pavement designed to provide a smooth driving surface (such as Asphaltic Concrete, SMA, OGPA, and similar materials), includes prep works, abutting surfaces (including batters/feathered edges), protection of kerbs and other finished surfaces, temporary raised pavement markers, tack coats, blinding, levelling, longitudinal and traverse joints, paving tape, modified blinders, other pavement instrumentation/devices, etc. Also includes Sealing Layers - a protective layer applied to the pavement surface to prevent water ingress. Includes all trial section testing and all other testing and reporting requirements.
10 | Bridge and Viaduct Structures |  |  | Bridge and Viaduct Structures that span over obstacles (e.g. water, roads, valleys) to provide access for users, including vehicles and pedestrians. This includes all components forming the overall structure, including finishes, but excludes 'Utilities', 'Street Lights', 'ITS', 'Hard and Soft Landscaping', etc. (Note - Construction 'Type' of bridge/viaduct to be listed).
|  | 10.01 | Temporary Works for Bridge Structures | Temporary structures or staging used during the construction or repair of bridge components. These may include staging platforms, scaffolding, formwork, temporary lighting towers, falsework, or supports needed for the construction or renovation of the bridge.
|  | 10.02 | Foundations | The base construction for the structure including piling, columns and footings, detailed excavation, and localised filling that transfers loads to the ground, including mob/demob of piling plant, casings, reinforcing, piling materials, auguring, temporary works for the piling or columns, etc. (Note - Applies to both new builds and repairs).
|  | 10.03 | Substructure | The parts of the bridge below the main deck, including piers, abutments, shear keys, wingwalls, etc. that support the superstructure and transfer the loads to the foundations.
|  | 10.04 | Superstructure | This is the portion above substructure which supports roadway & traffic, including deck, beams/girders, bearings, settlement slabs, diaphragms, trusses, expansion joints, cables (for suspension and/or cable stayed bridges), and including ancillary items such as anti-throw screens/safety nets, parapets/railings, anti-graffiti protection, painting, cultural design elements, bridge and wingwall safety barriers (PC/in-situ), handrailing's, bridge footpaths, service ducts/pipes, bridge streetlight brackets (if not measured under 'Traffic Services - Streetlights'), bridge name plates, etc.
11 | Structural Walls and Protection Works |  |  | Structures that aren’t part of Bridge, Viaducts or Tunnels, Subways Structures and Rockfall Shelters, to hold back soil and prevent erosion to maintain stability of elevated or sloped areas, and/or provide noise mitigation.
|  | 11.01 | Temporary Works for Structural Walls and Protection Works | Temporary works and/or structures, supports, etc. installed during the construction of walls. These may include temporary staging and scaffolding, temporary bracing or shoring, dewatering systems, temporary retaining structures, temporary lighting towers, falsework, etc.
|  | 11.02 | Anchored/Bored Pile Retaining Walls | Form and construct Anchored Retaining Walls/Soldier Pile, including Bored or Continuous Flight Auger (CFA) piles, excavation, imported fill, backfilling and compaction, anchors, anchor blocks/beams, anchored soldier piled, drainage (Note - if not measured separately under 'Drainage'), geotextile reinforcement, facing units, temporary works, formwork, materials for wall construction, etc. including testing as required. (Note - this includes Micro Pile Walls).
|  | 11.03 | Post and Panel Walls | Form and construct Post and Panel Walls, including piled/strip foundations, mob/demob of piling plant, casings, piling materials, pile driving, augering, imported fill, bedding, blinding layer, temporary works, formwork, reinforcement, curing, joints, fillers, fabrication and installation of panel and posts, etc. including testing as required.
|  | 11.04 | Noise Walls | Form and construct Noise Walls, including piled/strip foundations, mob/demob of plant, casings, piling materials, pile driving, augering, imported fill, bedding, blinding layer, temporary works, formwork, reinforcement, curing, joints, fillers, fabrication, supply and installation/construction of noise wall, drainage (Note - if not measured separately under 'Drainage'), etc. including testing as required.
|  | 11.05 | Crib Retaining Walls | Form and construct Crib Retaining Walls (Concrete or Timber), including excavation, imported fill, backfilling and compaction, anchors, pegs/stakes, drainage (Note - if not measured separately under 'Drainage'), geotextile reinforcement, facing units, temporary works, formwork, materials for wall construction, etc. including testing as required.
|  | 11.06 | Gravity Retaining Walls (Mass Concrete and Gabion Walls) | Form and construct Gravity Retaining Walls, including clearing, topsoil removal, excavation, imported fill, backfilling, drainage (Note - if not measured separately under 'Drainage'), bedding, blinding layer, temporary works, formwork, reinforcement, curing, joints, fillers, materials/aggregate for wall construction, etc. including testing as required.
|  | 11.07 | L-Shaped Rigid Barrier Walls | Form and construct Precast Concrete or In-Situ Concrete Rigid Barrier Walls, including excavation, imported fill, backfilling and compaction, drainage (Note - if not measured separately under 'Drainage'), geotextile reinforcement, etc. including testing as required.
|  | 11.08 | Mechanically Stabilised Earth (MSE) Walls | Form and construct MSE Walls, including excavation, backfilling and compaction, temporary works, geotextile reinforcement, imported materials/aggregate for wall construction, drainage (Note - if not measured separately under 'Drainage'), facing units, surface finishes, etc. including testing as required.
|  | 11.09 | Reinforced Soil Slope/Earth Wall | A Reinforced Soil slope/Earth Wall is defined as a compacted fill embankment that incorporates geosynthetic reinforcement to increase the soil shear to enhance the stability of the embankment, includes imported aggregates, bidum, drainage (Note - if not measured separately under 'Drainage'), jute/hessian cloth, pegs/stakes, etc.
|  | 11.1 | Rockfall Barriers/Catch Fences | Rockfall barrier fence/catch fence systems (including Mesh Canopies) are designed to intercept falling rocks which have detached from the rock face above which may cause damage to structures/passing traffic below, construction includes mob/demob, steel cables, steel mesh/drape netting (Maccaferri or other approved), wire rope cables, soil nails, rock bolts/anchors, spot bolts, posts, hand scaling, abseiling works, other fixings/fittings, etc.
|  | 11.11 | Embankment Erosion Protection Systems | Form and construct protection systems (including scour protection) relating to shoreline, streams, rivers, canals, lakes, bridge abutments and piers, etc. using materials such as Xblock, rip rap, rock armour, rock/boulder walls, concrete collars, rock filter bags, etc. including excavation, imported fill, backfilling and compaction, anchors, pegs/stakes, drainage (Note - if not measured separately under 'Drainage'), geotextile reinforcement, materials for protection construction, etc. including testing as required.
|  | 11.12 | Shotcrete Walls | The method of applying concrete projected at high velocity primarily onto a vertical surface, including reinforcing, concrete, bidum, drainage (Note - if not measured separately under 'Drainage'), jute/hessian cloth, grout, plant for spraying, imported fill, backfilling, etc.
|  | 11.13 | Timber Retaining Walls | Form and construct Timber Retaining Walls, including piled/strip foundations, mob/demob of plant, casings, piling materials, pile driving, augering, imported fill, bedding, blinding layer, drainage (Note - if not measured separately under 'Drainage'), temporary works, formwork, reinforcement, curing, joints, fillers, fabrication, supply and installation/construction of timber wall, etc. including testing as required.
12 | Utilities |  |  | Services including water, gas, electricity, and telecommunications, typically owned and maintained by external service providers. This includes the temporary and permanent relocation of networks, coordination efforts with service providers, and the civil works typically performed by the contractor.
|  | 12.01 | Civil Works for Utilities | Civil works including Common and Shared Service Trenching, potholing, location of existing services (air/hydro excavation, hand digging), protection of existing services, bedding, ducting (includes joints and welding), pipe bedding preparation, backfilling and compacting. These tasks apply to both temporary and permanent utilities. (Note - this includes Civils Works relating to Street Lights under 'Traffic Services', but for existing Utilities Services and Street Light Removals refer to 'Site Clearance').
|  | 12.02 | Water Reticulation | The relocation or new supply and installation of the Watermain, including temp shutdowns, stand overs, tracer wires, warning tape, joints, connections, tie-ins to existing supply, pressure testing, chlorination, testing and commissioning, etc. (Note - Excludes any Civils Works).
|  | 12.03 | Electrical Supply | The relocation or new supply and installation of the high voltage and/or low voltage Electrical Supply, including, temp shutdowns, stand overs, installation of electrical distribution conductor/cable, earthing, warning tape, jointing, warnings signs, other electrical assets such as kiosks, transformers, overhead poles, distribution boxes, etc., including testing and commissioning, etc. (Note - Excludes any Civils Works).
|  | 12.04 | Gas Reticulation | The relocation or new supply and installation of the Gas Line, including temp shutdowns, stand overs, tracer wires, warning tape, joints, connections, tie-ins to existing supply, pressure testing, testing and commissioning, etc. (Note - Excludes any Civils Works).
|  | 12.05 | Communications | The relocation or new supply and installation of the Communications Network (e.g. Chorus, Spark, One NZ, Vocus, Veolia, etc), including temp shutdowns, stand overs, installation of communication cables, tracer wires, warning tape, jointing, warnings signs, other communication assets such as cabinets, etc., including testing and commissioning, etc. (Note - Excludes any Civils Works).
|  | 12.06 | Waste Water Reticulation | The relocation or new supply and installation of the Wastewater Line, including, temp shutdowns, stand overs, joints, connections, tie-ins to existing supply, testing and commissioning, etc. (Note - Excludes any Civils Works).
13 | Traffic Services |  |  | Permanent traffic control systems and infrastructure to manage network usage and safety, this includes Vehicles, Bicycles, Public Transport and Pedestrian Traffic. (Note - construction works relating to Maintenance Bays / Emergency Stopping Bays is to measured under 'Earthwork' and 'Pavement and Surfacing').
|  | 13.01 | Temporary Works for Traffic Services | Any temporary traffics services installed during the works.
|  | 13.02 | Signage (New and Relocation of Existing) | Road signs for traffic control, information, and direction, including excavation, backfilling and compaction, foundation footings, concrete, reinforcement, formwork, poles, ground sockets, support and bracing to sign panels, corrosion protection, graffiti guard, painting, temporary screening, etc.
|  | 13.03 | Gantries | Road gantry framework or structure spanning a roadway, used to support various equipment such as signs, signals, cameras, lights, or sensors, facilitating traffic management, enforcement, and safety measures, including graffiti guard.
|  | 13.04 | Safety Barriers | The removal, relocation or new supply and installation of physical barriers used to separate traffic lanes or other as to improve safety, including precast concrete, W-Beam barrier, Three-Beam barrier, In-situ Concrete, Wire Rope barrier, transitions, end terminals, crash cushions, etc. Includes excavation, base prep, backfilling and compaction, graffiti guard, fittings/fixings and installation.
|  | 13.05 | Lighting | The relocation or new supply and installation of the permanent street lighting, yard lighting and/or lighting towers including temp shutdowns, stand overs, installation of light poles, luminaires, cables, foundations, earthing, painting, outreach arms, brackets, fuses blocks, etc., including testing and commissioning, etc. (Note - all Civils Works relating to Street Lights, refer to 'Utilities').
|  | 13.06 | Road Crossings and Raised Safety Table | Construction of Cycle, Pedestrian, Pram Crossings and/or Raised Safety Table Crossings , including site prep, clearing, excavation, backfilling and compaction, subgrade prep, bedding, trimming, levelling, formwork, reinforcement, curing, joints, joint fillers, protection, pedestrian crossing signage, graffiti guard, etc. (Note - excludes 'Pavement & Surfacing' works).
|  | 13.07 | Traffic Island/Roundabout Infill and Kerb and Channel | Construction of precast concrete/in-situ concrete traffic islands and/or roundabouts, including site prep, clearing, excavation, backfilling and compaction, subgrade prep, bedding, trimming, levelling, formwork, reinforcement, curing, joints, joint fillers, protection, graffiti guard, etc.
|  | 13.08 | Roadmarkings / Pavement Markings | Removal of existing road/pavement markings, both temporary and new painted road markings, audio tactile markings, rumble strips, thermoplastic long life markings, symbols, RRPM's, RPM's, etc. (Note - this also includes markings to Footpaths, Shared User Paths and Cycleways).
|  | 13.09 | Delineation | Markings and devices used to define the edges of roadways and lanes, including safe hit posts, edge marker posts, surface prep/cleaning, etc.
|  | 13.1 | Tactile Ground Surface Indicators | Specialised textured ground surface indicators which assist visually impaired pedestrians to navigate spaces, includes warning tile indicators, leading/directional tactile indicators, site prep, excavation, backfilling and compaction, subgrade prep, bedding, trimming, levelling, formwork, reinforcement, curing, joints, joint fillers, protection, graffiti guard, etc.
14 | Intelligent Transport Systems (ITS) |  |  | Any technology applied to transport and infrastructure to transfer information between systems, and to transport users, for improved safety, efficiency and environmental outcomes. | NZTA Traffic Management Systems documentation
|  | 14.01 | Traffic Signals | Signal lights used to control vehicle and pedestrian traffic at intersections, includes signal lanterns, signal poles, outreach arms, call boxes, traffic loops, power supply (if not included under 'Utilities' section), testing and commissioning. | https://www.nzta.govt.nz/assets/userfiles/transport-data/Intelligent%20Transport%20Systems.pdf
|  | 14.02 | Advanced Traffic Management Systems | Also known as 'Active or Intelligent Traffic Management Systems' - Technology applied to transport and infrastructure to transfer information between systems, and to transport users, for improved safety, efficiency and environmental outcomes, includes ramp metering signals (RMS loops), traffic monitoring services (TMS loops), cables, conduits and pits/chambers for ITS, electronic signs such as Variable Message Signs (VMS), Variable Speed Limits (VSL) systems, lane and carriageway signs, mobile VMS signs, Speed Cameras, power supply (if not included under 'Utilities' section), testing and commissioning.
|  | 14.03 | Closed Circuit Television (CCTV) Monitoring Cameras | Non-Intrusive' Surveillance and traffic monitoring cameras, including supply and installation of CCTV cameras and supports, fixings, power and communications supply (if not included under 'Utilities' section).
|  | 14.04 | Tolling Roadside Systems | Road Tolling installation includes Gantries, VDX Sensors such as Vehicle Detection and Classification (VDC) and Vehicle Registration Sensors (VR’s), Tolling System Controllers (TSC’s), Data Concentrator Systems, Monitoring and Control Systems (MCS’s) such as High Level Monitoring (HLM) System Interface, Tolling Monitoring Tool (TOMO), Scada, Generators, Rack Consoles, IP Switches, Cabinet Switches, Uninterrupted Power Supply (UPS), Security Cameras, Maintenance Laptops, etc.
15 | Hard and Soft Landscaping |  |  | Enhances the visual and environmental quality of the project site with plants and other aesthetic features, including both soft and hard landscaping elements. Includes maintenance of these features.
|  | 15.01 | Temporary Landscaping | Constructing temporary paths, cycleways, accessways and/or vehicle crossings, including any temporary planting or turfing as required (Note - any traffic controls need to be in Temporary Traffic Management).
|  | 15.02 | Stockpiled and Imported Materials | Materials brought in such as screened topsoil, sand, gravel, decorative pebbles, stone chip, bark nuggets, and mulch specifically relating to landscaping works, this includes treatment/conditioning of existing stockpiled materials.
|  | 15.03 | Planting and Turfing | The installation, preparation, and maintenance of seeding, turf, planting, trees and other vegetation until they are handed over to the asset owner, including irrigation, weed/pest control, maintenance period during defects liability period for each separable portion.
|  | 15.04 | Paths | Pathways designed to accommodate the movement of pedestrians and cyclists such as footpaths, shared use paths, cycleways/paths, board walks, timber walkways and bridleways. This includes all site prep, clearing, excavation, backfilling and compaction, subgrade prep, bedding, trimming, levelling, formwork, reinforcement, curing, joints, joint fillers, sealing, protection, decorative finishes, graffiti guard, etc. (Note - For items negotiated with private landowners refer to Accommodation Works).
|  | 15.05 | Vehicle Crossings / Private and Common Accessways | Construction of permanent concrete/asphalt vehicle crossings or private/common accessways/driveways, including site prep, clearing, excavation, backfilling and compaction, subgrade prep, bedding, trimming, levelling, formwork, reinforcement, curing, joints, joint fillers, protection, graffiti guard, etc.
|  | 15.06 | Fencing, Trellis and Gates | Supply and installation of fencing, gates, and trellis specifically relating to the Project Works, includes timber post and rail, timber/concrete/ metal post and wire, timber paling, metal guard rails, road restraint system, stiles, deer fencing, bloodstock fencing, timber/metal gates, timber/metal trellis, steel wire trellis systems, etc.
|  | 15.07 | Street Furniture | Functional and decorative items like cycle handrails, cycle separators, benches/seats, bollards, balustrades, rubbish bins, tables, bicycle stands, drink fountains, playground equipment, etc.
|  | 15.08 | Cultural Elements | Sculptures, art installations, integrated public art, and other cultural specific elements that reflect local culture.
16 | Tunnels, Subway Structures and Rockfall Shelters |  |  | Ways that pass under or over obstacles (e.g. roads, railways, embankments) to provide safe access for users, including vehicles, pedestrians, and water. This category includes tunnels, subways/underpasses, rockfall shelters and standalone culverts not part of a pipe network. This works encompass all earth movements such as excavations, foundations, structural elements, finishes and services.
|  | 16.01 | Temporary Works for Tunnels, Subways Structures and Rockfall Shelters | Temporary works associated with tunnels, subways structures and rockfall shelter construction. Includes items such as dewatering, ventilation, seepage control, temporary works for the piling or columns, temporary supports and safe access, temporary lighting towers, sheet piles, false work, etc.
|  | 16.02 | Tunnelling | The process of creating a near horizontal hole in the earth. Includes methods like micro-tunnelling, tunnel boring, road headers, drilling and blasting. Excludes cut and cover.
|  | 16.03 | Earthworks Movements | Items for excavation shall be deemed to include disposal of excavated and hauling material off the Site and removal of dead services unless otherwise stated in item descriptions, includes excavations for tunnels/shafts in rock or other stated earth materials.
|  | 16.04 | Foundations | The base construction for the structure including piling, columns and footings, that transfers loads to the ground, including mob/demob of piling plant, casings, reinforcing, piling materials, auguring, imported fill, backfilling, etc. (i.e. Tunnels, Subways, Rockfall Shelters and/or Culverts that are not included under 'Bridges' or 'Structural Walls and Protection Works').
|  | 16.05 | Structure | Form and construct all the structural components that are above the foundations, including excavation, imported fill, backfilling and compaction, in-situ linings, preformed segmental linings, support and stabilization, drainage (Note - if not measured separately under 'Drainage'), geotextile reinforcement, facing units, temporary works, formwork, other materials for construction, etc. including testing as required.
|  | 16.06 | Services | Services for the tunnels, subways and/or viaducts including lighting, ventilation, HVAC, electrical, fire suppression, deluge system, plant room services, etc. (Note - items of works that are not included elsewhere e.g. 'Utilities', 'Traffic Services', 'ITS', etc.)
17 | Buildings |  |  | This category involves the construction and fit-out of permanent, vertical structures designed to provide facilities for intended occupants. Buildings include office buildings, depots, operational centres for NZTA and other stakeholders, public buildings such as bus terminals, rest areas, or information centres, and vertical structures with functional spaces for public use, like parking buildings or tolling booths. The fit-out of these structures, such as HVAC systems, plumbing, electrical systems, interior partitions, flooring, and lighting, is also included, as are exterior components like roof cladding, exterior walls, windows, and doors as part of the building envelope. Excludes temporary structures used during construction, such as site offices or shelters. It also excludes any works done for private landowners as part of mitigation or settlement agreements (such as driveways, fencing, or landscaping features) as they belong in Accommodation Works.
|  | 17.01 | Temporary Works for Buildings | Temporary structures and systems required to facilitate the construction or renovation of a building. This includes scaffolding, temporary accessways, formwork, temporary supports, safety nets, and temporary enclosures to protect the site from weather. Also includes crane pads that serve the specific needs of building construction. Excludes temporary utility connections, which go under Utilities.
|  | 17.02 | Foundations | The base for the structure including piles and footings, that transfers loads to the ground.
|  | 17.03 | Structure | The components that transfer loads safely to the foundation and protect the building's interior from external forces like wind, weather, and seismic activity. These components that are above the foundations, including slabs, structural walls, columns, beams, roof structure and covering, structural steelwork, formwork, reinforcing, external windows and doors, stairs, landings, expansion joints, concrete cutting and all other features forming part of the structural envelope.
|  | 17.04 | Fit-Out | Fit-out refers to all interior work required to make the building functional and ready for use. This includes partition walls, ceilings, flooring, finishes, fixtures, fittings, cabinetry, interior doors and windows, painting, as well as any specialised features or equipment necessary for the occupants.
|  | 17.05 | Building Services | Building services encompass all the essential systems that provides a building's functionality and comfort, including electrical systems, heating, ventilation, air conditioning (HVAC), plumbing, fire protection, lighting, hydraulics, CCTV, security surveillance, earthing, anti-lightning protection, lifts, escalators, travelators, ICT (Information and Communication Technology) systems and any other items relating to Building Services Installation.
18 | Sundry Items |  |  | Sundry Item costs may include special items relating to accommodation works on private land, landowner agreements, temporary relocation of residents or stakeholders, costs associated with EOT's, and all other project specific outlier costs (Note - all items to be clearly listed and quantified).
|  | 18.01 | Accommodation Works on Private Land / Landowner Agreements Settled | Accommodation works include any temporary or one-off works negotiated with private landowners as part of project agreements. These works are not part of the core, permanent infrastructure but are added to accommodate specific landowner needs or as mitigation for project impacts. They are generally related to private property enhancement or restoration and do not contribute to long-term maintenance by NZTA. Includes construction, relocation and restoration activities as agreed with the landowner that may relate to items such as Groundwater Wells, Fencing (post & rail, deer fencing, bloodstock fencing, high noise fencing/walls, post & wire, etc), Planting Trees and Shrubs, Grassing, Gates, Property Accessways, Letter Boxes, Signage, Washing Lines, Chicken Coops or anything else agreed with the landowner.
|  | 18.02 | Temporary Relocation of Residents/Stakeholders | Temporary Relocation of Residents/Stakeholders.
|  | 18.03 | Cost Escalation | Cost Escalation costs as agreed under terms of the contract (apportioned to the Category and Sub-Category project works where possible).
|  | 18.04 | Prolongation/Extension of Time Claims | Costs relating to Prolongation/Extension of Time Claims.
|  | 18.05 | Rebates | Rebates
|  | 18.06 | Contractors Risk | Contractors Risk (apportioned to the Category and Sub-Category project works where possible).
|  | 18.07 | Cost Shares | Cost-Shares (i.e. with Developers, Local Councils, Utility Companies, etc.) need to be identified (for all forms of procurement).
|  | 18.08 | Broader Outcomes | Broader Outcomes
|  | 18.09 | Other Project Specific Outliers | Items of works or installation of any other project specific items that cannot be included under any other Category above - must be listed and described.
19 | Commercials |  |  | Contractual Agreements
|  | 19.01 | On-Site Overheads (or equivalent for hard dollar contracts) | For variations only, expressed as a percentage
|  | 19.02 | Off-Site Overheads and Profit / Margin (or equivalent for hard dollar contracts) | For variations only, expressed as a percentage
|  | 19.03 | Limb 1 Multipliers (or equivalent for target cost contracts) | Expressed as a percentage
|  | 19.04 | Limb 2 Multipliers (or equivalent for target cost contracts) | Expressed as a percentage